## APMC_PMR 1st Sem CY 23
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (APMC) Procurement Monitoring Report as of June 30, 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | [5 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO
COMPLETED PROCUREMENT ACTIVITIES
5-02-05-020-01 | S/D of 230 Globe Cellcard 500 and 1 Other | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-02-28 | 2023-02-28 | 2023-04-27 | 2023-05-09 | 2023-05-09 | GoP | 189500 | 189500 | 0 | 189310.5 | 189310.5 | 0 | N/A
5-02-03-990-00 | S/D of 2000 Bottled Water 500ml and 16 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-02-28 | 2023-02-28 | 2023-04-03 | 2023-04-12 | 2023-04-12 | GoP | 301500 | 301500 | 0 | 300862 | 300862 | 0 | N/A
5-02-99-050-04 | Rental Services of Photocopier | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-03-14 | 2023-03-14 | 2023-05-03 | 2023-05-19 | 2023-05-19 | GoP | 102000 | 102000 | 0 | 99000 | 99000 | 0 | N/A
5-02-99-050-04 | Rental Services of Printer | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-03-14 | 2023-03-14 | 2023-05-03 | 2023-05-19 | 2023-05-19 | GoP | 84000 | 84000 | 0 | 81000 | 81000 | 0 | N/A
5-02-99-030-00 | 1 lot Catering Services Food Packs | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-03-14 | 2023-03-14 | 2023-05-03 | 2023-05-19 | 2023-05-19 | GoP | 914500 | 914500 | 0 | 912500 | 912500 | 0 | N/A
5-02-13-040-01 | S/D of 100 pcs Metal Furring 1''x2''x16'' and 42 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-03-14 | 2023-03-14 | 2023-04-24 | 2023-05-08 | 2023-05-08 | GoP | 996179 | 996179 | 0 | 991769 | 991769 | 0 | N/A
5-02-05-020-01 | S/D of 266 Globe Cellcard 500 and 3 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-04-04 | 2023-04-04 | 2023-05-15 | 2023-05-26 | 2023-05-26 | GoP | 278600 | 278600 | 0 | 277984 | 277984 | 0 | N/A
Total Alloted Budget of Procurement Activities | [29 empty] | 2866279
Total Contract Price of Procurement Actitvites Conducted | [32 empty] | 2852425.5
Total Savings (Total Alloted Budget - Total Contract Price) | [29 empty] | 13853.5
0N-GOING PROCUREMENT ACTIVITIES
5-02-99-030-00 | 1 lot Catering Services Food Packs | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-04-24 | 2023-04-24 | N/A | N/A | N/A | GoP | 632400 | 632400 | 0 | 630000 | 630000 | 0 | N/A
5-02-13-040-01 | S/D of 36 pcs Hardiflex and 34 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-04-24 | 2023-04-24 | N/A | N/A | N/A | GoP | 542707 | 542707 | 0 | 541540.5 | 541540.5 | 0
5-02-13-040-01 | S/D of 18 pcs Angle Bar 1/4''x2''x2''x20'' and 70 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-03-28 | 2023-03-28 | N/A | N/A | N/A | GoP | 658680 | 658680 | 0 | 656292 | 656292 | 0
5-02-13-040-01 | S/D of 305 Metal Furring 1'' x 2'' x 16'' and 48 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-04-24 | 2023-04-24 | 2023-06-21 | N/A | N/A | GoP | 400000 | 400000 | 0 | 396565 | 396565 | 0
5-02-03-210-03 | 5 set Desktop Computer and 5 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-05-05 | 2023-05-05 | N/A | N/A | N/A | GoP | 506850 | 506850 | 0 | 505850 | 505850 | 0
5-02-99-050-04 | 1 lot Rental Services Printer | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-05-05 | 2023-05-05 | N/A | N/A | N/A | GoP | 84000 | 84000 | 0 | 81000 | 81000 | 0
5-02-13-040-01 | 20 pcs Metal Furring and 51 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-05-05 | 2023-05-05 | N/A | N/A | N/A | GoP | 330000 | 330000 | 0 | 329180 | 329180 | 0
5-02-03-990-00 | 2300 btl Mineral Water 500ml and 16 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-05-05 | 2023-05-05 | N/A | N/A | N/A | GoP | 338412 | 338412 | 0 | 336552 | 336552 | 0
5-02-03-210-03 | 1 unit Conference System Central Unit and 10 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-05-11 | 2023-05-11 | N/A | N/A | N/A | GoP | 522306.92 | 522306.92 | 0 | 521306.92 | 521306.92 | 0
5-02-13-040-01 | 300 pcs Metal Furring 1 x2 x16 and 40 Others | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-05-11 | 2023-05-11 | N/A | N/A | N/A | GoP | 980000 | 980000 | 0 | 976587 | 976587 | 0
5-02-99-030-00 | Catering Services | [19 empty] | APMC | NO | NP-53.9 - Small Value Procurement | 2023-05-11 | 2023-05-11 | N/A | N/A | N/A | GoP | 879800 | 879800 | 0 | 783200 | 783200 | 0
Total Alloted Budget of On-going Procurement Activities | [29 empty] | 5875155.92
| Prepared by: | [24 empty] | Certified Correct By | [6 empty] | Noted By
| Reynato F Borbo | [24 empty] | LEO L CADALIG | [6 empty] | PATRICK B DE VILLA
| Sgt (OS) PA | [24 empty] | Major (QMS) PA | [6 empty] | Colonel INF (GSC) PA
| Logistics NCO | [24 empty] | Logistics Officer | [6 empty] | Director

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement