## PMR-2nd QTR
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | 113TH CONTRACTING OFFICE-TRADOC, PA-PROJECT MONITORING REPORT from 01 January 2023 to 30 June 2023
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 | Procurement of Vision Blocks and View Blocks for Armored Vehicles | [18 empty] | Armor Div PA | Armor Div |  | Public Bidding Negotiated 53.9 | 2022-10-06 | 2022-10-06 | 2022-10-14 |  | 2022-10-28 |  | 2022-11-10 |  | 2023-01-24 |  | 2023-06-27 |  |  |  | 9606462.5 | SPCL REL |  | 9605950 | SPCL REL | [8 empty] | Complete Delivery / TIAC dated 27 June 2023
2 | Procurement of Batteries for Armored Vehicles | [18 empty] | Armor Div PA | Armor Div |  | Public Bidding Negotiated 53.9 | 2022-10-06 | 2022-10-06 | 2022-10-14 |  | 2022-10-28 |  | 2022-11-10 |  | 2023-02-16 |  | 2023-06-26 |  |  |  | 4950000 | SPCL REL |  | 4602624 | SPCL REL
3 | Procurement of Tire Run Flat Inserts | [18 empty] | Armor Div PA | Armor Div |  | Public Bidding Negotiated 53.9 | 2022-10-06 | 2022-10-06 | 2022-10-14 |  | 2022-10-28 |  | 2022-11-10 |  | 2023-01-24 | [5 empty] | 7000000 | SPCL REL |  | 6299000 | SPCL REL
4 | Procurement of Replacement part for Mounted Armaments (12.7mm RCWS 1st and 2nd Generation) | [18 empty] | Armor Div PA | Armor Div |  | Public Bidding Negotiated 53.9 | 07 Oct 22/21 Nov 22 | 07 Oct 22/21 Nov 22 | 14 Oct 22/29 Nov 22 |  | 28 Oct 22/13 Dec 22 | [9 empty] | 40378400 | SPCL REL |  |  | SPCL REL | [8 empty] | >For reprogramming >Failure of two (2) biddings due to unavailability of bidder >For amendment of PPMP/ POE >To be scheduled for Pre-Procurement
5 | Procurement of Periscope M17 for APC/ARV/AIFV | [18 empty] | Armor Div PA | Armor Div |  | Public Bidding Negotiated 53.9 | 2022-10-13 | 2022-10-13 | 2022-10-20 |  | 2022-11-08 |  | 2022-11-23 |  | 2023-01-24 |  | 2023-06-05 |  |  |  | 6000000 | SPCL REL |  | 6000000 | SPCL REL | [8 empty] | Complete Delivery / TIAC dated 05 June 2023
6 | Procurement of Replacement Parts for M113 APC/AIFV/ARV | [18 empty] | Armor Div PA | Armor Div |  | Public Bidding Negotiated 53.9 | 2022-10-13 | 2022-10-13 | 2022-10-20 |  | 2022-11-08 |  | 2022-11-23 |  | 2023-01-24 | [5 empty] | 13904500 | SPCL REL |  | 13899500 | SPCL REL
7 | Procurement of Replacement Parts for Cmdo V-150 | [18 empty] | Armor Div PA | Armor Div |  | Public Bidding Negotiated 53.9 | 2022-10-13 | 2022-10-13 | 2022-10-20 |  | 2022-11-08 |  | 2022-11-23 |  | 2023-01-24 | [5 empty] | 9104000 | SPCL REL |  | 9099000 | SPCL REL
8 | Procurement of Replacement Parts for SFV | [18 empty] | Armor Div PA | Armor Div |  | Public Bidding Negotiated 53.9 | 2022-10-13 | 2022-10-13 | 2022-10-20 |  | 2022-11-08 |  | 2022-11-23 |  | 2023-02-16 |  | 2023-07-03 |  |  |  | 3340000 | SPCL REL |  | 3340000 | SPCL REL
9 | Procurement of Track Assy T130 | [18 empty] | Armor Div PA | Armor Div |  | Public Bidding Negotiated 53.9 | 2022-10-28 | 2022-10-28 | 2022-11-07 |  | 2022-11-21 |  | 2022-11-29 |  | 2023-01-24 | [5 empty] | 8000000 | SPCL REL |  | 8000000 | SPCL REL
10 | Rubber Tracks Assembly | [18 empty] | Armor Div PA | Armor Div |  | Public Bidding Negotiated 53.9 | 2022-10-28 | 2022-10-28 | 2022-11-07 |  | 2022-11-21 | [9 empty] | 10500000 | SPCL REL |  |  | SPCL REL | [8 empty] | >For reprogramming >Failure of two (2) biddings due to unavailability of bidder > For amendment of PPMP/ POE >Waiting for the quotation from Larsen & Toubro Defence on or before 20 April 2023
11 | Detroit Diesel Engine Assembly 6V-53N (Power Pack) | [18 empty] | Armor Div PA | Armor Div |  | Public Bidding Negotiated 53.9 | 2022-10-28 | 2022-10-28 | 2022-11-07 |  | 2022-11-21 |  | 2022-11-29 |  | 2023-01-24 | [5 empty] | 14000000 | SPCL REL |  | 13992000 | SPCL REL
12 | Cummins Engine Assembly V8-504 (Power Pack) | [18 empty] | Armor Div PA | Armor Div |  | Public Bidding Negotiated 53.9 | 2022-10-28 | 2022-10-28 | 2022-11-07 |  | 2022-11-21 |  | 2022-11-29 |  | 2023-01-09 | [5 empty] | 33500000 | SPCL REL |  | 33495000 | SPCL REL
[38 empty] | 160283362.5 |  |  | 108333074
Total Alloted of Budget Procurement Activities | [36 empty] | 160283362.5
Total Contrct PriceOf Procurement Activites Conducted | [39 empty] | 108333074
Total Savings (Total Alloted Budget - Total Contract Price | [36 empty] | 51950288.5
[21 empty] | Prepared by: | [16 empty] | NOTED BY:
[21 empty] | Lyndon S Pimentel | [16 empty] | IAN KRISTIN D HAMLAG
[21 empty] | Sgt (Arm) PA | [16 empty] | Lt Colonel GSC (ARM) PA
[21 empty] | Admin NCO | [16 empty] | AC of S for Logisics, G4

## PMR-2nd QTR_EDITED
ANNEX A
ARMOR DIVISION PROCUREMENT MONITORING REPORT AS OF 30 JUNE 2023
Department of Budget and Management Annual Procurement Plan for FY 2006
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activities | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/ Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| Procurement of Vision Blocks and View Blocks for Armored Vehicles | [18 empty] | Requirements to maintain the serveciability of armored assets | Armor Div | Yes | Public Bidding | 2022-10-06 | 2022-10-06 | 2022-10-14 |  | 2022-10-28 |  | 2022-11-10 |  | 2023-01-24 |  | 2023-06-27 |  |  | GAA 2023 | 9606462.5 | 9606462.5 |  | 9605950 | 9605950 | [7 empty] | 2023-06-27 | Delivery Completed
| Procurement of Batteries for Armored Vehicles | [18 empty] | Armor Div PA | Armor Div | Yes | Public Bidding | 2022-10-06 | 2022-10-06 | 2022-10-14 |  | 2022-10-28 |  | 2022-11-10 |  | 2023-02-16 |  | 2023-06-26 |  |  | GAA 2023 | 4950000 | 4950000 |  | 4602624 | 4602624
| Procurement of Periscope M17 for APC/ARV/AIFV | [18 empty] | Armor Div PA | Armor Div | Yes | Public Bidding | 2022-10-13 | 2022-10-13 | 2022-10-20 |  | 2022-11-08 |  | 2022-11-23 |  | 2023-01-24 |  | 2023-06-05 |  |  | GAA 2023 | 6000000 | 6000000 |  | 6000000 | 6000000 | [7 empty] | 2023-06-05 | Delivery Completed
| Procurement of Replacement Parts for SFV | [18 empty] | Armor Div PA | Armor Div | Yes | Public Bidding | 2022-10-13 | 2022-10-13 | 2022-10-20 |  | 2022-11-08 |  | 2022-11-23 |  | 2023-02-16 |  | 2023-07-03 |  |  | GAA 2023 | 3340000 | 3340000 |  | 3340000 | 3340000
[38 empty] | 23896462.5 | 23896462.5 |  | 23548574 | 23548574
Total Alloted Budget Procurement Activities | [36 empty] | 23896462.5
Total Contract Price of Procurement Activites Conducted | [39 empty] | 23548574
Total Savings (Total Alloted Budget - Total Contract Price | [36 empty] | 347888.5
| Procurement of Tire Run Flat Inserts | [18 empty] | Armor Div PA | Armor Div | Yes | Public Bidding | 2022-10-06 | 2022-10-06 | 2022-10-14 |  | 2022-10-28 |  | 2022-11-10 |  | 2023-01-24 |  |  |  |  | GAA 2023 | 7000000 | 7000000 |  | 6299000 | 6299000
| Procurement of Replacement Parts for M113 APC/AIFV/ARV | [18 empty] | Armor Div PA | Armor Div | Yes | Public Bidding | 2022-10-13 | 2022-10-13 | 2022-10-20 |  | 2022-11-08 |  | 2022-11-23 |  | 2023-01-24 |  |  |  |  | GAA 2023 | 13904500 | 13904500 |  | 13899500 | 13899500
| Procurement of Replacement Parts for Cmdo V-150 | [18 empty] | Armor Div PA | Armor Div | Yes | Public Bidding | 2022-10-13 | 2022-10-13 | 2022-10-20 |  | 2022-11-08 |  | 2022-11-23 |  | 2023-01-24 |  |  |  |  | GAA 2023 | 9104000 | 9104000 |  | 9099000 | 9099000
| Procurement of Track Assy T130 | [18 empty] | Armor Div PA | Armor Div | Yes | Public Bidding | 2022-10-28 | 2022-10-28 | 2022-11-07 |  | 2022-11-21 |  | 2022-11-29 |  | 2023-01-24 |  |  |  |  | GAA 2023 | 8000000 | 8000000 |  | 8000000 | 8000000
| Detroit Diesel Engine Assembly 6V-53N (Power Pack) | [18 empty] | Armor Div PA | Armor Div | Yes | Public Bidding | 2022-10-28 | 2022-10-28 | 2022-11-07 |  | 2022-11-21 |  | 2022-11-29 |  | 2023-01-24 |  |  |  |  | GAA 2023 | 14000000 | 14000000 |  | 13992000 | 13992000
| Cummins Engine Assembly V8-504 (Power Pack) | [18 empty] | Armor Div PA | Armor Div | Yes | Public Bidding | 2022-10-28 | 2022-10-28 | 2022-11-07 |  | 2022-11-21 |  | 2022-11-29 |  | 2023-01-09 |  |  |  |  | GAA 2023 | 33500000 | 33500000 |  | 33495000 | 33495000
| Replacement parts for Mounted Armaments (12.7mm RCWS 1st Gen) | [19 empty] | Armor Div | No | Public Bidding | [13 empty] | GAA 2023 | 14508961 | 14508961 | [11 empty] | Reprogrammed PAPs (Approved by CGPA) For issuance of ASA
| Replacement parts for Mounted Armaments (12.7mm RCWS 2nd Gen) | [19 empty] | Armor Div | No | Public Bidding | [13 empty] | GAA 2023 | 22739439 | 22739439
| Replacement parts for Mounted Armaments (UTS 25mm Gun and MMS 81mm) | [19 empty] | Armor Div | No | Public Bidding | [13 empty] | GAA 2023 | 13630000 | 13630000
| Construction of Tank Maintenance Facility (Lot 1) | [19 empty] | Armor Div | No | Public Bidding | 2023-07-03 | 2023-07-04 | 2023-07-12 | [10 empty] | GAA 2023 | 99653227.33 |  | 99653227.33
| Construction of Tank Maintenance Facility (Lot 2) | [19 empty] | Armor Div | No | Public Bidding | 2023-07-03 | 2023-07-04 | 2023-07-12 | [10 empty] | GAA 2023 | 62954636.95 |  | 62954636.95
| Construction of Tank Maintenance Facility (Lot 3) | [19 empty] | Armor Div | No | Public Bidding | [13 empty] | GAA 2023 | 28043135.72 |  | 28043135.72 | [10 empty] | For finalization and approval of specs
Total Alloted Budget of Ongoing Procurement Activities | [37 empty] | 327037900 | 136386900 | 190651000 | 84784500 | 84784500
Prepared by:
NOTED BY:
Lyndon S Pimentel
| Sgt (Arm) PA | [43 empty] | IAN KRISTIN D HAMLAG
| Admin NCO | [43 empty] | Lt Colonel GSC (ARM) PA
AC of S for Logisics, G4