## pmr ASR
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | ARMY SIGNAL REGIMENT Procurement Monitoring Report as of June 30, 2023
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| S/D of 1 pc Audio Mixer & 5 others | [19 empty] | CSBn_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-04-24 | 2023-04-28 | 2023-04-28 | GoP | 172935 | 172935 | 0 | 172000 | 172000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 unit Printer Scanner L3110 and 2 Others | [19 empty] | CyberBN_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-03 | 2023-04-14 | 2023-04-25 | 2023-04-25 | GoP | 90000 | 90000 | 0 | 89550 | 89550 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 5 set all-in-one computer i5-12400 Xe Graphics 23.8" IPS 1920x1080 72%NTSC 16GB 512G | [19 empty] | NETBn_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-04-12 | 2023-04-18 | 2023-04-18 | GoP | 222050 | 222050 | 0 | 221000 | 221000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 109 gal Alcohol Ethyl Alcohol 70% Unscented and 3 Others | [19 empty] | NETBn_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-04-12 | 2023-04-25 | 2023-04-25 | GoP | 112700 | 112700 | 0 | 112296.35 | 112296.35 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 20 piece Broom, Soft (tambo) and 23 Others | [19 empty] | NETBn_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | 2023-05-04 | 2023-05-22 | 2023-05-22 | GoP | 65650 | 65650 | 0 | 65400 | 65400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 pcs Printer 3 in 1 & 2 Others | [19 empty] | OG4_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-04-03 | 2023-04-17 | 2023-04-17 | GoP | 77200 | 77200 | 0 | 76798 | 76798 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 btls Rear Differential Fluid for Mitubishi Strada & 32 Others | [19 empty] | OG4_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-04-03 | 2023-04-17 | 2023-04-17 | GoP | 100000 | 100000 | 0 | 99650 | 99650 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 pc Motor Compressor & 4 Others | [19 empty] | OG4_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | 2023-04-04 | 2023-04-18 | 2023-04-18 | GoP | 27000 | 27000 | 0 | 26800 | 26800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 set Injection Nozzle for KM450 #41 & 34 Others | [19 empty] | OG4_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-05-08 | 2023-05-10 | 2023-05-10 | GoP | 200000 | 200000 | 0 | 199800 | 199800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 30 bags Cement & 26 others | [19 empty] | OG4_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-04-24 | 2023-05-03 | 2023-05-03 | GoP | 204400 | 204400 | 0 | 203700 | 203700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 3 pcs Printer 3 in 1 & 3 Others | [19 empty] | OG4_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-04 | 2023-05-08 | 2023-05-18 | 2023-05-18 | GoP | 81700 | 81700 | 0 | 81350 | 81350 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 1353635
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 1348344.35
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 5290.65
0N-GOING PROCUREMENT ACTIVITIES
| Subscription of SG310 E-mail Security Appliance | [19 empty] | CyberBN_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-04-05 | 2023-06-19 | N/A | N/A | GoP | 300000 | 300000 | 0 | 299500 | 299500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 5 unit Desktop Computer Core i5 All-in-One and 2 others | [19 empty] | CyberBN_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | 2023-05-20 | 2023-06-02 | 2023-06-02 | GoP | 480514 | 480514 | 0 | 478264 | 478264 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 100 pcs Marine Plywood 3/4 x4 x 8 and 44 Others | [19 empty] | CyberBN_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-05 | 2023-05-05 | N/A | N/A | N/A | GoP | 500000 | 500000 | 0 | 498000 | 498000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1 Lot UTM Appliance 1XG450 DMZ (Subscription) | [19 empty] | CyberBN_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-05 | 2023-05-05 | N/A | N/A | N/A | GoP | 850000 | 850000 | 0 | 849500 | 849500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 1 lot Catering Services of NETBn | [19 empty] | NETBn_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | N/A | N/A | N/A | GoP | 150000 | 150000 | 0 | 148000 | 148000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of Desktop computer 21.5 inch Monitor 8GB RAM 128GB M.2 1TB HDD i5 11th GEN PROCESSOR and 1 other | [19 empty] | NETBn_ASR | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-05 | 2023-05-05 | N/A | N/A | N/A | GoP | 70000 | 70000 | 0 | 69590 | 69590 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 372 ROLLS OF BATTERY NICKLE STRIP (5MM) 10S AND 23 OTHERS | [19 empty] | OG4_ASR_PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-02 | N/A | N/A | N/A | GoP | 998000 | 998000 | 0 | 996140 | 996140 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 4 UNITS CROSS CUT PAPER SHREDDER REXEL 30L AND 1 OTHER | [19 empty] | CyberBn_ASR_PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-02 | N/A | N/A | N/A | GoP | 195000 | 195000 | 0 | 193750 | 193750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2 PCS DESKTOP COMPUTER ENTRY LEVEL & 1 OTHER | [19 empty] | OG4_ASR_PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-02 | N/A | N/A | N/A | GoP | 149371 | 149371 | 0 | 148850 | 148850 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 3 PIECE PROCESSOR AMD RYZEN 3 3200G SOCKET AM4 65W AND 9 OTHERS | [19 empty] | NETBn_ASR_PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-02 | N/A | N/A | N/A | GoP | 73950 | 73950 | 0 | 73575 | 73575 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1 LOT CATERING SERVICES (FOOD PACKS) | [19 empty] | NETBn_ASR_PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-02 | N/A | N/A | N/A | GoP | 1000000 | 1000000 | 0 | 997200 | 997200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 5 UNITS 3D PRINTER AND 5 OTHERS | [19 empty] | SIMBn_ASR_PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-02 | N/A | N/A | N/A | GoP | 997000 | 997000 | 0 | 994750 | 994750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 400 PCS CHB 4" X 8" X 16" AND 40 OTHERS | [19 empty] | SIMBn_ASR_PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-02 | N/A | N/A | N/A | GoP | 500000 | 500000 | 0 | 499116 | 499116 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ICT TRAINING EXPENSES | [19 empty] | TSS_ASR_PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-02 | 2023-05-02 | N/A | N/A | N/A | GoP | 150000 | 150000 | 0 | 149000 | 149000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 4 PCS LAPTOP 16" | [19 empty] | OG4_ASR_PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-12 | 2023-05-12 | N/A | N/A | N/A | GoP | 700000 | 700000 | 0 | 697300 | 697300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1 UNIT WASHING MACHINE INVERTER 8.0/5.0KGS WASHER & DRYER AND 1 OTHER | [19 empty] | CyberBn_ ASR_PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-12 | 2023-05-12 | N/A | N/A | N/A | GoP | 51650 | 51650 | 0 | 51500 | 51500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 8 UNIT FUSION MACHINE | [19 empty] | CSBn_ASR_PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-12 | 2023-05-12 | N/A | N/A | N/A | GoP | 360000 | 360000 | 0 | 358000 | 358000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1 PC SOLID STATE DRIVE 2TB - M.2 INTERNAL AND 2 OTHERS | [19 empty] | CyberBn_ASR_PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-12 | 2023-05-12 | N/A | N/A | N/A | GoP | 55000 | 55000 | 0 | 54800 | 54800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 5 PCS PRINTER 3 & 1 AND 10 OTHERS | [19 empty] | NETBn_ASR_PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-05-12 | 2023-05-12 | N/A | N/A | N/A | GoP | 915000 | 915000 | 0 | 913400 | 913400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1 UNIT SMART LED TV 70INC 4K UHD ANDROID | [19 empty] | CyberBn_ASR_PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-12 | N/A | N/A | N/A | GoP | 50000 | 50000 | 0 | 49650 | 49650 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| FOURTEEN (14) ALCOHOL 500ML | [19 empty] | OG4_ASR_PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-12 | N/A | N/A | N/A | GoP | 128800 | 128800 | 0 | 128269 | 128269 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 8674285
PREPARED BY: | [37 empty] | NOTED BY:
Mark Rowen T Amantoy | [37 empty] | SEFREDO A CONTIC
Cpl (OS) PA | [37 empty] | Major (QMS) PA
Assistant Procurement NCO | [37 empty] | AC of S for Logistics, G4, ASR, PA

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement