## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | FSRR, PA Procurement Monitoring Report as of 20 June 2023
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-02-03-070-00 | Drugs and Medicines | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | N/A | 2023-03-03 | 2023-03-07 | 2023-03-07 | GoP | 104465 | 104465 |  | 104075 | 104075 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-09 | Military Police and Security Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | N/A | 2023-03-03 | 2023-03-07 | 2023-03-07 | GoP | 237645 | 237645 |  | 237160 | 237160 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | N/A | 2023-03-03 | 2023-03-07 | 2023-03-07 | GoP | 85042 | 85042 |  | 84710 | 84710 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-01 | Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | N/A | 2023-03-03 | 2023-03-07 | 2023-03-07 | GoP | 973319.25 | 973319.25 |  | 972707 | 972707 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-02 | Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | N/A | 2023-03-03 | 2023-03-07 | 2023-03-07 | GoP | 324870.75 | 324870.75 |  | 324095 | 324095 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-03 | R/M of ICT Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | N/A | 2023-03-03 | 2023-03-07 | 2023-03-07 | GoP | 260749.5 | 260749.5 |  | 260000 | 260000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | N/A | 2023-03-03 | 2023-03-07 | 2023-03-07 | GoP | 737560 | 737560 |  | 736760 | 736760 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-07 | Semi Expendable Commo | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | N/A | 2023-03-23 | 2023-03-28 | 2023-03-28 | GoP | 594000 | 594000 |  | 593465 | 593465 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-03 | Semi Expendable ICT | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | N/A | 2023-03-23 | 2023-03-28 | 2023-03-28 | GoP | 750000 | 750000 |  | 748751 | 748751 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-03 | Semi Expendable ICT | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-03-23 | 2023-03-28 | 2023-03-28 | GoP | 450792 | 450792 |  | 450080 | 450080 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-07 | Semi Expendable Commo | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-04-28 | 2023-05-08 | 2023-05-08 | GoP | 273000 | 273000 |  | 272600 | 272600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | N/A | 2023-04-28 | 2023-05-08 | 2023-05-08 | GoP | 300000 | 300000 |  | 299550 | 299550 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | N/A | 2023-05-12 | 2023-05-18 | 2023-05-18 | GoP | 105520 | 105520 |  | 104945 | 104945 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-05-12 | 2023-05-18 | 2023-05-18 | GoP | 369515 | 369515 |  | 368910 | 368910 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Military, Police & Security Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-05-12 | 2023-05-18 | 2023-05-18 | GoP | 144600 | 144600 |  | 144165 | 144165 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-05-12 | 2023-05-18 | 2023-05-18 | GoP | 133590 | 133590 |  | 133068 | 133068 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Drugs and Medicines | [19 empty] | FSRR, PA | NO | Negotiated 53.10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | N/A | 2023-05-12 | 2023-05-18 | 2023-05-18 | GoP | 24000 | 24000 |  | 23745 | 23745 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | N/A | 2023-05-12 | 2023-05-18 | 2023-05-18 | GoP | 75000 | 75000 |  | 74630 | 74630 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-120-00 | Military Police and Traffic Supplies Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-05-12 | 2023-05-18 | 2023-05-18 | GoP | 144600 | 144600 |  | 144165 | 144165 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | N/A | 2023-05-18 | 2023-05-25 | 2023-05-25 | GoP | 53701 | 53701 |  | 53370 | 53370 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | N/A | 2023-05-19 | 2023-05-25 | 2023-05-25 | GoP | 83895 | 83895 |  | 83510 | 83510 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-03 | R/M of ICT Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-05-18 | 2023-05-25 | 2023-05-25 | GoP | 50700 | 50700 |  | 50400 | 50400 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | N/A | 2023-05-19 | 2023-05-25 | 2023-05-25 | GoP | 50000 | 50000 |  | 49700 | 49700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | N/A | 2023-05-19 | 2023-05-25 | 2023-05-25 | GoP | 997158 | 997158 |  | 996317 | 996317 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | N/A | 2023-05-19 | 2023-05-25 | 2023-05-25 | GoP | 83740 | 83740 |  | 83298 | 83298 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-01 | Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | N/A | 2023-05-18 | 2023-05-25 | 2023-05-25 | GoP | 68228 | 68228 |  | 67818 | 67818 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Semi Expendable Commo | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | N/A | 2023-05-19 | 2023-05-25 | 2023-05-25 | GoP | 80000 | 80000 |  | 79500 | 79500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | N/A | 2023-05-19 | 2023-05-25 | 2023-05-25 | GoP | 97500 | 97500 |  | 96970 | 96970 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-02 | Drugs and Medicines | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-29 | N/A | 2023-05-19 | 2023-05-25 | 2023-05-25 | GoP | 25000 | 25000 |  | 24580 | 24580 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Drugs and Medicines | [19 empty] | FSRR, PA | NO | Negotiated 53.10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | N/A | 2023-05-19 | 2023-05-25 | 2023-05-25 | GoP | 25000 | 25000 |  | 24580 | 24580 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-03 | R/M of Semi Expendable ICT Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | N/A | 2023-05-19 | 2023-05-25 | 2023-05-25 | GoP | 44955 | 44955 |  | 44340 | 44340 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-03 | Semi Expendable ICT | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | N/A | 2023-05-19 | 2023-05-25 | 2023-05-25 | GoP | 239900 | 239900 |  | 239350 | 239350 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | GoP | 140000 | 140000 |  | 139540 | 139540 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-210-03 | Semi Expendable ICT | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | GoP | 98010 | 98010 |  | 97700 | 97700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-07 | R/M of Semi Expendable Commo Equip | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | GoP | 63000 | 63000 |  | 62650 | 62650 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | GoP | 61900 | 61900 |  | 61470 | 61470 |  | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | GoP | 575000 | 575000 |  | 574220 | 574220 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | N/A | 2023-05-28 | 2023-06-01 | 2023-06-01 | GoP | 337500 | 337500 |  | 336805 | 336805 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | GoP | 84375 | 84375 |  | 84155 | 84155 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-00 | ICT Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | GoP | 91585 | 91585 |  | 91120 | 91120 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | GoP | 419035 | 419035 |  | 418375 | 418375 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | GoP | 60205 | 60205 |  | 59780 | 59780 |  | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | GoP | 191360 | 191360 |  | 190880 | 190880 |  | N/A
5-02-13-050-07 | Semi Expendable Commo Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | GoP | 99995 | 99995 |  | 99495 | 99495 |  | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | GoP | 364635 | 364635 |  | 364055 | 364055 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | GoP | 100000 | 100000 |  | 99429 | 99429 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | N/A | 2023-06-01 | 2023-06-09 | 2023-06-09 | GoP | 117660 | 117660 |  | 117167 | 117167 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | N/A | 2023-06-01 | 2023-06-09 | 2023-06-09 | GoP | 70000 | 70000 |  | 69533 | 69533 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | N/A | 2023-06-01 | 2023-06-09 | 2023-06-09 | GoP | 100000 | 100000 |  | 99480 | 99480 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | N/A | 2023-06-01 | 2023-06-09 | 2023-06-09 | GoP | 60000 | 60000 |  | 59830 | 59830 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-00 | Office Supplies | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | N/A | 2023-06-01 | 2023-06-09 | 2023-06-09 | GoP | 51778 | 51778 |  | 51370 | 51370 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-06-01 | 2023-06-09 | 2023-06-09 | GoP | 160000 | 160000 |  | 159500 | 159500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-07 | Semi Expendable Commo Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | N/A | 2023-06-01 | 2023-06-09 | 2023-06-09 | GoP | 599400 | 599400 |  | 598900 | 598900 |  | N/A
| Semi Expendable Commo | [19 empty] | FSRR, PA | NO | Negotiated 53.10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | N/A | 2023-06-01 | 2023-06-09 | 2023-06-09 | GoP | 50000 | 50000 |  | 49590 | 49590 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-06-01 | 2023-06-09 | 2023-06-09 | GoP | 149995 | 149995 |  | 149350 | 149350 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R/M of Building | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-06-01 | 2023-06-09 | 2023-06-09 | GoP | 95000 | 95000 |  | 94660 | 94660 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-06-09 | 2023-06-16 | 2023-06-16 | GoP | 221710 | 221710 |  | 221179 | 221179 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | N/A | 2023-06-09 | 2023-06-16 | 2023-06-16 | GoP | 20000 | 20000 |  | 19683 | 19683 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | N/A | 2023-06-09 | 2023-06-16 | 2023-06-16 | GoP | 344000 | 344000 |  | 343475 | 343475 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-06-09 | 2023-06-16 | 2023-06-16 | GoP | 161840 | 161840 |  | 161360 | 161360 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-06-09 | 2023-06-16 | 2023-06-16 | GoP | 80750 | 80750 |  | 80436 | 80436 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-06-09 | 2023-06-16 | 2023-06-16 | GoP | 50000 | 50000 |  | 49700 | 49700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Drugs and Medicines | [19 empty] | FSRR, PA | NO | Negotiated 53.11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | N/A | 2023-06-09 | 2023-06-16 | 2023-06-16 | GoP | 24001 | 24001 |  | 23746 | 23746 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical & Dental Expns | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | N/A | 2023-06-09 | 2023-06-16 | 2023-06-16 | GoP | 43180 | 43180 |  | 42805 | 42805 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Drugs and Medicines | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | N/A | 2023-06-09 | 2023-06-16 | 2023-06-16 | GoP | 24000 | 24000 |  | 23745 | 23745 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[38 empty] | 13097959.5 | 13097959.5 |  | 13066497 | 13066497 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 13097959.5
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 13066497
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 31462.5
0N-GOING PROCUREMENT ACTIVITIES
5-02-13-050-07 | Semi Expendable Office Equipment | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | N/A |  |  |  | GoP | 55000 | 55000 |  | 54700 | 54700 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Obligate Sign for Accountant
5-02-99-030-00 | Representation Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | N/A |  |  |  | GoP | 65000 | 65000 |  | 64596 | 64596 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Obligate Sign for Accountant
5-02-03-990-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | N/A |  |  |  | GoP | 50000 | 50000 |  | 49755 | 49755 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Obligate Sign for Accountant
5-02-03-990-00 | Other Supplies and Materials | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | N/A |  |  |  | GoP | 84375 | 84375 |  | 83914 | 83914 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Obligate Sign for Accountant
5-02-02-010-00 | Training Expenses | [19 empty] | FSRR, PA | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | N/A |  |  |  | GoP | 87920 | 87920 |  | 87530 | 87530 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Obligate Sign for Accountant
[44 empty] | N/A | [6 empty] | Obligate Sign for Accountant
[44 empty] | N/A | [6 empty] | Obligate Sign for Accountant
[44 empty] | N/A | [6 empty] | Obligate Sign for Accountant
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 342295
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | KENNETH R ESPLANA | [10 empty] | CARLO CANICO V IRIBERRI III | [10 empty] | ISAGANI O CRISTE
[21 empty] | MAJ (QMS) PA | [10 empty] | MAJ (INF) PA | [10 empty] | COL INF (GSC) PA
[21 empty] | AC of S for Logistics, G4 | [10 empty] | Acof S for FM, G10 | [10 empty] | Acting Regiment Commander

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement