## PMR December
ANNEX B
(LRR, PA) Procurement Monitoring Report as of January to June 2023
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-02-03-010-00 | Office Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | N/A | 2023-02-23 | 2023-03-08 | 2023-03-08 | GoP | 212865 | 212865 | N/A | 212370 | 212370 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Cellcard | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | N/A | 2023-02-08 | 2023-03-14 | 2023-03-14 | GoP | 128800 | 128800 | N/A | 128713.5 | 128713.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical & Dental & Laboratory Supplies Expenses | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | N/A | 2023-02-08 | 2023-02-14 | 2023-02-14 | GoP | 190800 | 190800 | N/A | 190400 | 190400 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair & Maintenance of Building | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | N/A | 2023-02-08 | 2023-02-14 | 2023-02-14 | GoP | 150000 | 150000 | N/A | 149500 | 149500 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair & Maintenance of Vehicle | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | N/A | 2023-02-08 | 2023-02-14 | 2023-02-14 | GoP | 294250 | 294250 | N/A | 293750 | 293750 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Semi-Expendable ICT Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | N/A | 2023-02-08 | 2023-02-14 | 2023-02-14 | GoP | 156040 | 156040 | N/A | 155540 | 155540 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | N/A | 2023-02-08 | 2023-02-14 | 2023-02-14 | GoP | 600000 | 600000 | N/A | 599200 | 599200 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | N/A | 2023-02-08 | 2023-02-14 | 2023-02-14 | GoP | 111750 | 111750 | N/A | 111350 | 111350 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military Equipment | 1LRC, LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-28 | N/A | 2023-03-23 | 2023-04-13 | 2023-04-13 | GoP | 30000 | 30000 | N/A | 29884 | 29884 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military Equipment | 6LRC,LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-27 | N/A | 2023-03-20 | 2023-03-27 | 2023-03-27 | GoP | 30000 | 30000 | N/A | 29750 | 29750 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military Equipment | 2LRC,LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-28 | N/A | 2023-03-20 | 2023-03-27 | 2023-03-27 | GoP | 30000 | 30000 | N/A | 29750 | 29750 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-99 | Other Structures(Water System) | LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-03 | N/A | 2023-03-20 | 2023-03-27 | 2023-03-27 | GoP | 178802 | 178802 | N/A | 178000 | 178000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical & Dental & Laboratory Supplies Expenses OSS | LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-03 | N/A | 2023-03-20 | 2023-03-27 | 2023-03-27 | GoP | 83066 | 83066 | N/A | 82620 | 82620 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-080-00 | Medical & Dental & Laboratory Supplies Expenses | LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-06 | N/A | 2023-03-20 | 2023-03-27 | 2023-03-27 | GoP | 81615 | 81615 | N/A | 81000 | 81000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair & Maintenance of Building | LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-06 | N/A | 2023-03-20 | 2023-03-27 | 2023-03-27 | GoP | 376000 | 376000 | N/A | 375300 | 375300 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair & Maintenance of Vehicle | LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-03 | N/A | 2023-03-20 | 2023-03-27 | 2023-03-27 | GoP | 359250 | 359250 | N/A | 385750 | 385750 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-990-00 | Other Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-03 | N/A | 2023-03-20 | 2023-03-27 | 2023-03-27 | GoP | 419140 | 419140 | N/A | 418540 | 418540 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Cellcard | LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-03 | N/A | 2023-03-20 | 2023-03-27 | 2023-03-27 | GoP | 128800 | 128800 | N/A | 128768.75 | 128768.75 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies | LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-06 | N/A | 2023-03-20 | 2023-03-27 | 2023-03-27 | GoP | 205415 | 205415 | N/A | 205000 | 205000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military Equipment | LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-03-06 | N/A | 2023-03-20 | 2023-03-27 | 2023-03-27 | GoP | 600000 | 600000 | N/A | 599425 | 599425 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-03 | Semi-Expendable ICT Equipment | LRS, LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-17 | N/A | 2023-03-31 | 2023-04-13 | 2023-04-13 | GoP | 53750 | 53750 | N/A | 53000 | 53000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-210-09 | Semi-Expendable Military Equipment | LRS, LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-15 | N/A | 2023-03-02 | 2023-03-08 | 2023-03-08 | GoP | 30000 | 30000 | N/A | 29700 | 29700 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-060-01 | Repair & Maintenance of Vehicle | LRS, LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-15 | N/A | 2023-03-02 | 2023-03-08 | 2023-03-08 | GoP | 40000 | 40000 | N/A | 39500 | 39500 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-05-020-01 | Mobile Cellcard | LRS, LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-15 | N/A | 2023-03-02 | 2023-03-08 | 2023-03-08 | GoP | 30000 | 30000 | N/A | 29970 | 29970 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-03-010-00 | Office Supplies | LRS, LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-15 | N/A | 2023-03-02 | 2023-03-08 | 2023-03-08 | GoP | 96250 | 96250 | N/A | 95860 | 95860 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5-02-13-040-01 | Repair & Maintenance of Building | LRS, LRR, PA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2023-02-17 | N/A | 2023-03-20 | 2023-03-27 | 2023-03-27 | GoP | 100000 | 100000 | N/A | 99400 | 99400 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
[19 empty] | 4716593 | 4716593 |  | 4732041.25 | 4732041.25
Total Alloted Budget of Procurement Activities | [18 empty] | 4716593
Total Contract Price of Procurement Activities Conducted | [21 empty] | 4732041.25
Total Savings (Total Alloted Budget - Total Contract Price) | [21 empty] | -15448.25
0N-GOING PROCUREMENT ACTIVITIES
5-02-03-010-00 | Office Supplies | LRS, LRR, PA | NO | NP-53.9 - Small Value Procurement | [14 empty] | 96250 | 96250 | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On-going
5-02-13-060-01 | Repair & Maintenance of Vehicle | LRS, LRR, PA | NO | NP-53.9 - Small Value Procurement | [14 empty] | 40000 | 40000 | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On-going
5-02-05-020-01 | Mobile Cellcard | LRS, LRR, PA | NO | NP-53.9 - Small Value Procurement | [14 empty] | 30000 | 30000 | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On-going
5-02-13-040-01 | Repair & Maintenance of Building | LRS, LRR, PA | NO | NP-53.9 - Small Value Procurement | [14 empty] | 150000 | 150000 | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On-going
5-02-03-210-03 | Semi-Expendable ICT Equipment | LRS, LRR, PA | NO | NP-53.9 - Small Value Procurement | [14 empty] | 53750 | 53750 | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On-going
Total Alloted Budget of On-going Procurement Activities | [18 empty] | 370000 |  |  |  | 370000
| Prepared by: | [11 empty] | Recommended for Approval by: | [10 empty] | APPROVED BY:
| PAUL BENEDICT R CRUZ | [11 empty] | MIGUEL KARLO E ALAMBRA | [10 empty] | JOSE JESUS C LUNTOK
| MAJ (OS) PA | [11 empty] | CPT (QMS) PA | [10 empty] | COL GSC (INF) PA
| AC of S for Logistics, G4 | [11 empty] | G10, LRR, PA | [10 empty] | Acting Regiment Commander

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement