## TRADOC PMR CY 2023
H E A D Q U A R T E R S
PHILIPPINE ARMY
TRADOC
Procurement Monitoring Report of TRADOC, PA (Jan - June 2023)
Code PAP | Procurement Project | PMO/ End User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre- Proc Conference | Ads/Post of IB (Invitation to submit quotation) | Pre-Bid Conf | Eligibility Check | Sub/Open of Bids (Abstract of Canvass) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable) |  | Remarks
COMPLETED PROCUREMENT ACTIVITIES
1 | Enhancement of PWD & Senior Citizen Ramp | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-03 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-04-10 | 2023-04-10 | 2023-04-17 | 2023-04-17 | GoP | 210000 | 210000 | - | 209600 | 209600 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
2 | Semi- Expendable Military Police and Security Equipment | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-31 | N/A | 2023-02-03 | 2023-02-03 | 2023-02-03 | N/A | N/A | 2023-02-03 | 2023-04-10 | 2023-04-10 | 2023-04-17 | 2023-04-17 | GoP | 155000 | 155000 | - | 152500 | 152500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
3 | Office & Janitorial Supplies | HTRADOC,PA | NO | Shopping 52.1(b) | N/A | 2023-03-03 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-04-26 | 2023-04-26 | 2023-05-03 | 2023-05-03 | GoP | 882896 | 882896 | - | 846211 | 846211 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
4 | ICT Office Supplies | HTRADOC,PA | NO | Shopping 52.1(b) | N/A | 2023-02-02 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-04-26 | 2023-04-26 | 2023-05-03 | 2023-05-03 | GoP | 58160 | 58160 | - | 57660 | 57660 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
5 | Furniture & Fixtures | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-02 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-04-25 | 2023-04-25 | 2023-05-02 | 2023-05-02 | GoP | 259000 | 259000 | - | 258500 | 258500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
6 | Enhancement of Office Equipment | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-02 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-04-25 | 2023-04-25 | 2023-05-02 | 2023-05-02 | GoP | 102887 | 102887 | - | 102700 | 102700 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
7 | Semi- Expendable ICT Equipment | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-02 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-04-25 | 2023-04-25 | 2023-05-02 | 2023-05-02 | GoP | 589500 | 589500 | - | 588000 | 588000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
8 | Repair & Maintenance of Motor Vehicle | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-16 | N/A | 2023-02-21 | 2023-02-21 | 2023-02-21 | N/A | N/A | 2023-02-21 | 2023-04-25 | 2023-04-25 | 2023-05-02 | 2023-05-02 | GoP | 360705 | 360705 | - | 359505 | 359505 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
9 | Repair & Maintenance of Female Barracks | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-02 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-05-15 | 2023-05-15 | 2023-05-19 | 2023-05-19 | GoP | 250000 | 250000 | - | 248200 | 248200 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
10 | Enhancement of Sewerage Line System | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-03 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-04-10 | 2023-04-10 | 2023-04-17 | 2023-04-17 | GoP | 200000 | 200000 | - | 199470 | 199470 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
11 | Enhancement of Quartermaster Equipment (Grasscutter) | ALDEC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-31 | N/A | 2023-02-03 | 2023-02-03 | 2023-02-03 | N/A | N/A | 2023-02-03 | 2023-04-13 | 2023-04-13 | 2023-04-26 | 2023-04-26 | GoP | 28500 | 28500 | - | 28000 | 28000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
12 | Support to Disaster Prevention and Mitigation activity equipment | ALDEC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-01 | N/A | 2023-02-03 | 2023-02-03 | 2023-02-03 | N/A | N/A | 2023-02-03 | 2023-04-13 | 2023-04-13 | 2023-04-26 | 2023-04-26 | GoP | 13300 | 13300 | - | 13100 | 13100 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
13 | Enhancement of PWD/Senior Citizen and Differently Abled Person's Equipment (Wheelchair) | ALDEC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-31 | N/A | 2023-01-31 | 2023-01-31 | 2023-01-31 | N/A | N/A | 2023-02-03 | 2023-04-13 | 2023-04-13 | 2023-04-26 | 2023-04-26 | GoP | 7000 | 7000 | - | 6500 | 6500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
14 | R&M of Facilities (Library; Admin office & PWD) | ALDEC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-09 | N/A | 2023-02-09 | 2023-02-09 | 2023-02-09 | N/A | N/A | 2023-02-14 | 2023-04-13 | 2023-04-13 | 2023-05-10 | 2023-05-10 | GoP | 189907 | 189907 | - | 189357 | 189357 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
15 | Support for Admin and losgistical Requirement | ALDEC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-14 | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-17 | 2023-05-02 | 2023-05-02 | 2023-05-16 | 2023-05-16 | GoP | 38235 | 38235 | - | 37854 | 37854 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
16 | R&M of Vehicle (Innova) | ALDEC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-28 | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | 2023-06-14 | 2023-06-14 | 2023-06-28 | 2023-06-28 | GoP | 43000 | 43000 | - | 43000 | 43000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
17 | Support to Office Hotline | CAC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-20 | N/A | 2023-02-23 | 2023-02-23 | 2023-02-23 | N/A | N/A | 2023-02-23 | 2023-05-10 | 2023-05-10 | 2023-05-17 | 2023-05-17 | GoP | 6000 | 6000 | - | 6000 | 6000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
18 | Other Supplies & Materials | CAC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-23 | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | 2023-05-10 | 2023-05-10 | 2023-06-22 | 2023-06-22 | GoP | 12350 | 12350 | - | 12350 | 12350 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
19 | Procurement of Dental Supplies | DENTAL TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-09 | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-04-03 | 2023-04-03 | 2023-04-17 | 2023-04-17 | GoP | 147900 | 147900 | - | 146300 | 146300 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
20 | Procurement of Drugs and Medicines Supplies | DENTAL TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-10 | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-04-03 | 2023-04-03 | 2023-04-17 | 2023-04-17 | GoP | 30000 | 30000 | - | 29400 | 29400 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
21 | Office enhancement | LWC,TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-10 | N/A | 2023-02-16 | 2023-02-16 | 2023-02-16 | N/A | N/A | 2023-02-16 | 2023-05-03 | 2023-05-03 | 2023-05-08 | 2023-05-08 | GoP | 84700 | 84700 | - | 84700 | 84700 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
22 | ICT Enhancement | LWC,TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-10 | N/A | 2023-02-16 | 2023-02-16 | 2023-02-16 | N/A | N/A | 2023-02-16 | 2023-05-15 | 2023-05-15 | 2023-05-18 | 2023-05-18 | GoP | 59000 | 59000 | - | 59000 | 59000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
23 | Procurement of Vaccines | MEDICAL, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-30 | N/A | 2023-02-03 | 2023-02-03 | 2023-02-03 | N/A | N/A | 2023-02-03 | 2023-05-15 | 2023-05-15 | 2023-05-22 | 2023-05-22 | GoP | 30000 | 30000 |  | 28900 | 28900 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
24 | Procurement of Drugs and Medicines | MEDICAL, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-30 | N/A | 2023-02-03 | 2023-02-03 | 2023-02-03 | N/A | N/A | 2023-02-03 | 2023-05-05 | 2023-05-05 | 2023-05-10 | 2023-05-10 | GoP | 190125 | 190125 |  | 189795 | 189795 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
25 | Procurement of Medical Supplies | MEDICAL, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-01 | N/A | 2023-02-03 | 2023-02-03 | 2023-02-03 | N/A | N/A | 2023-02-03 | 2023-04-10 | 2023-04-10 | 2023-04-17 | 2023-04-17 | GoP | 53148 | 53148 |  | 52648 | 52648 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
26 | R& M of Motorcycle & Toyota Hilux | MTS, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-09 | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-06-14 | 2023-06-14 | 2023-06-20 | 2023-06-20 | GoP | 101776 | 101776 | - | 101520 | 101520 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
27 | R&M of Facilities | MTS, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-09 | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | 2023-05-10 | 2023-05-10 | 2023-05-16 | 2023-05-16 | GoP | 179234 | 179234 | - | 178734 | 178734 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
28 | Support for Medical Dental and Labolatory Supplies Expenses and COVID-19 Mitigation and Prevention | NCOS,ALDEC,TRADOC PA | N/A | NP-53.9 - Small Value Procurement | N/A | 2023-02-16 | N/A | 2023-03-21 | 2023-04-21 | 2023-02-21 | N/A | N/A | 2023-02-21 | 2023-04-20 | 2023-04-20 | 2023-04-04 | 2023-05-04 | GoP | 64100 | 64100 | - | 63400 | 63400 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
29 | Support for Semi-Expendable - Office Equipment / Inverter Split Type Aircon, 1.5HP | NCOS,ALDEC,TRADOC PA | N/A | NP-53.9 - Small Value Procurement | N/A | 2023-02-16 | N/A | 2023-02-16 | 2023-02-16 | 2023-02-16 | N/A | N/A | 2023-02-16 | 2023-04-26 | 2023-04-26 | 2023-05-03 | 2023-05-03 | GoP | 49998 | 49998 | - | 49500 | 49500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
30 | Support for R&M of HILUX/ R&M of Motorcycle | NCOS,ALDEC,TRADOC PA | N/A | NP-53.9 - Small Value Procurement | N/A | 2023-02-17 | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | 2023-05-09 | 2023-05-09 | 2023-05-16 | 2023-05-16 | GoP | 41600 | 41600 | - | 41500 | 41500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
31 | Enhancement of Semi-Expendable (Office Equipment) | OCS, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-02 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-05-03 | 2023-05-03 | 2023-05-10 | 2023-05-10 | GoP | 81500 | 81500 | - | 81500 | 81500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
32 | Semi-Expendable MP & Security Equipment | OCS, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-27 | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | 2023-05-10 | 2023-05-10 | 2023-05-22 | 2023-05-22 | GoP | 43475 | 43475 | - | 43475 | 43475 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
33 | Semi-Expendable ICT Equipment | OCS, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-20 | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | 2023-04-26 | 2023-04-26 | 2023-05-10 | 2023-05-10 | GoP | 243500 | 243500 | - | 241750 | 241750 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
34 | Motor Vehicles | OCS, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-08 | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-05-10 | 2023-05-10 | 2023-05-24 | 2023-05-24 | GoP | 126615 | 126615 | - | 118115 | 118115 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
35 | Enhancement of office equipment | TAC,TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-02 | N/A | 2023-03-13 | 2023-03-13 | 2023-03-13 | N/A | N/A | 2023-03-13 | 2023-03-13 | 2023-06-13 | 2023-06-22 | 2023-06-22 | GoP | 12000 | 12000 | - | 12000 | 12000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
36 | Enhancement of CCTVs | TAC,TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-13 | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-06-13 | 2023-06-22 | 2023-06-22 | GoP | 25000 | 25000 | - | 25000 | 25000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
37 | Repair & Maintenance Vehicle (Hi-Lux) | TDC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-23 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-05-02 | 2023-05-02 | 2023-05-10 | 2023-05-10 | GoP | 53000 | 53000 | - | 52, 000.00 | 52, 000.00 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
38 | Office Enhancement | TDC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | 2023-05-10 | 2023-05-10 | 2023-05-22 | 2023-05-22 | GoP | 113600 | 113600 | - | 113300 | 113300 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
39 | COVID-19 Mitigation | TSSC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-27 | N/A | 2023-01-31 | 2023-01-31 | 2023-01-31 | NA | NA | 2023-01-31 | 2023-03-08 | 2023-03-08 | 2023-03-21 | 2023-03-21 | GoP | 30400 | 30400 | - | 29900 | 29900 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
40 | Enhancement of ICTE | TSSC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-26 | N/A | 2023-01-31 | 2023-01-31 | 2023-01-31 | NA | NA | 2023-01-31 | 2023-02-28 | 2023-02-28 | 2023-03-13 | 2023-03-13 | GoP | 218050 | 218050 | - | 216300 | 216300 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
41 | R & M of Vehicle | TSSC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-03 | N/A | 2023-01-31 | 2023-01-31 | 2023-01-31 | NA | NA | 2023-02-03 | 2023-04-03 | 2023-04-03 | 2023-04-17 | 2023-04-17 | GoP | 239000 | 239000 | - | 237980 | 237980 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
42 | Enhancement of Calugas Hall | TSSC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-31 | N/A | 2023-02-03 | 2023-02-03 | 2023-02-03 | NA | NA | 2023-02-03 | 2023-04-03 | 2023-04-03 | 2023-04-17 | 2023-04-17 | GoP | 184250 | 184250 | - | 183400 | 183400 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
43 | Enhancement of HADR Equipment | TSSC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-27 | N/A | 2023-01-31 | 2023-01-31 | 2023-01-31 | NA | NA | 2023-01-31 | 2023-02-28 | 2023-02-28 | 2023-03-14 | 2023-03-14 | GoP | 20000 | 20000 | - | 19450 | 19450 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
44 | Enhancement of Combo Equipment | TSSC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-27 | N/A | 2023-01-31 | 2023-01-31 | 2023-01-31 | NA | NA | 2023-01-31 | 2023-02-28 | 2023-02-28 | 2023-03-13 | 2023-03-13 | GoP | 145133 | 145133 | - | 143000 | 143000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
45 | Enhancement of Computer Software | TSSC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-27 | N/A | 2023-01-31 | 2023-01-31 | 2023-01-31 | NA | NA | 2023-01-31 | 2023-03-08 | 2023-03-08 | 2023-03-20 | 2023-03-20 | GoP | 32000 | 32000 | - | 31300 | 31300 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
46 | Enhancement of PWD Ramp | TSSC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-03 | N/A | 2023-02-03 | 2023-02-03 | 2023-02-03 | NA | NA | 2023-02-03 | 2023-04-03 | 2023-04-03 | 2023-04-17 | 2023-04-17 | GoP | 20500 | 20500 | - | 20500 | 20500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
47 | Refill of Fire Extinguisher | SC, TRADOC, PA | NO | Negotiated 53.9 | N/A | 2023-01-31 | N/A | 2023-02-03 | 2023-02-03 | 2023-02-03 | N/A | N/A | 2023-02-03 | 2023-04-10 | 2023-04-10 | 2023-04-17 | 2023-04-17 | GOP | 30000 | 30000 | - | 29000 | 29000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
48 | Office Supplies | C2C, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-07 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-04-20 | 2023-03-31 | 2023-03-31 | GOP | 14469.54 | 14469.54 | - | 14215 | 14215 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
49 | R & M Siphoning Tanks (Environment/ Sanitary Services) | C2C, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-26 | N/A | 2023-01-26 | 2023-01-26 | 2023-01-26 | N/A | N/A | 2023-01-27 | 2023-01-27 | 2023-03-16 | 2023-03-31 | 2023-03-31 | GOP | 42000 | 42000 | - | 41650 | 41650 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
50 | R & M of Structure (Path Walk Pavenment) | C2C, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-26 | N/A | 2023-01-26 | 2023-01-26 | 2023-01-26 | N/A | N/A | 2023-01-30 | 2023-01-30 | 2023-03-16 | 2023-03-31 | 2023-03-31 | GOP | 114575 | 114575 | - | 114375 | 114375 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
51 | R & M of Building (Female CR at Admin Bldg & Conference Room) | C2C, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-26 | N/A | 2023-01-26 | 2023-01-26 | 2023-01-26 | N/A | N/A | 2023-01-30 | 2023-01-30 | 2023-03-21 | 2023-03-31 | 2023-03-31 | GOP | 117907 | 117907 | - | 117500 | 117500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
52 | Medical, Dental and LaboratorySupplies Expenses | C2C, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-25 | N/A | 2023-01-25 | 2023-01-25 | 2023-01-25 | N/A | N/A | 2023-01-26 | 2023-01-26 | 2023-02-15 | 2023-02-24 | 2023-02-24 | GOP | 10000 | 10000 | - | 9800 | 9800 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
53 | Semi-Expendable Machinery & Equipment - ICT Equipment | C2C, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-26 | N/A | 2023-01-26 | 2023-01-26 | 2023-01-26 | N/A | N/A | 2023-01-30 | 2023-01-30 | 2023-03-14 | 2023-03-16 | 2023-03-16 | GOP | 160000 | 160000 | - | 159500 | 159500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
54 | Semi-Expendable ICT Expenses Military Police Security Equipment | C2C, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-25 | N/A | 2023-01-25 | 2023-01-25 | 2023-01-25 | N/A | N/A | 2023-01-26 | 14 Mar 232 | 14 Mar 232 | 2023-03-16 | 2023-03-16 | GOP | 30000 | 30000 | - | 29800 | 29800 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
55 | Telephone Expenses | C2C, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-25 | N/A | 2023-01-25 | 2023-01-25 | 2023-01-25 | N/A | N/A | 2023-01-26 | 2023-02-15 | 2023-02-15 | 2023-02-17 | 2023-02-17 | GOP | 5000 | 5000 | - | 4997.5 | 4997.5 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
56 | Semi-Expendable Machinery & Equipment - ICT Equipment | C2C, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-25 | N/A | 2023-01-25 | 2023-01-25 | 2023-01-25 | N/A | N/A | 2023-01-26 | 2023-01-27 | 2023-02-15 | 2023-02-24 | 2023-02-24 | GOP | 49038 | 49038 | - | 48938 | 48938 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
57 | Office Supplies Exp. | C2C, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-19 | N/A | 2023-04-19 | 2023-04-19 | 2023-04-19 | N/A | N/A | 2023-04-20 | 2023-06-01 | 2023-06-01 | 2023-06-15 | 2023-06-15 | GoP | 31880 | 31880 | - | 31630 | 31630 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
58 | Motor Vehicle (KM250, Hilux & Motorcycle) | C2C, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-19 | N/A | 2023-04-19 | 2023-04-19 | 2023-04-19 | N/A | N/A | 2023-04-20 | 2023-06-01 | 2023-06-01 | 2023-06-21 | 2023-06-21 | GoP | 158800 | 158800 | - | 158200 | 158200 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
59 | Medical, Dental and LaboratorySupplies Expenses | C2C, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-19 | N/A | 2023-04-19 | 2023-04-19 | 2023-04-19 | N/A | N/A | 2023-04-20 | 2023-04-21 | 2023-06-01 | 2023-06-15 | 2023-06-15 | GoP | 5000 | 5000 | - | 4885 | 4885 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
60 | Telephone Expenses | C2C, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-19 | N/A | 2023-04-19 | 2023-04-19 | 2023-04-19 | N/A | N/A | 2023-04-20 | 2023-06-14 | 2023-06-14 | 2023-06-21 | 2023-06-21 | GoP | 5000 | 5000 | - | 4998.5 | 4998.5 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
61 | Representation Expenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-06 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-02-17 | 2023-02-17 | 2023-02-22 | 2023-02-22 | GoP | 2500 | 2500 | - | 2470 | 2470 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
62 | R & M of Building | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-07 | N/A | 2023-02-10 | 2023-02-10 | 2023-02-10 | N/A | N/A | 2023-02-10 | 2023-02-23 | 2023-02-23 | 2023-03-02 | 2023-03-02 | GoP | 84894 | 84894 | - | 84495 | 84495 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
63 | R & M Motor Vehicles | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-07 | N/A | 2023-02-10 | 2023-02-10 | 2023-02-10 | N/A | N/A | 2023-02-10 | 2023-02-23 | 2023-02-23 | 2023-03-02 | 2023-03-02 | GoP | 104800 | 104800 | - | 104800 | 104800 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
64 | Semi Expendable other Machinery & Equipment Sports Equipment | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-07 | N/A | 2023-02-10 | 2023-02-10 | 2023-02-10 | N/A | N/A | 2023-02-10 | 2023-02-27 | 2023-02-27 | 2023-03-02 | 2023-03-02 | GoP | 74000 | 74000 | - | 73600 | 73600 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
65 | Cable Expenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-07 | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 | N/A | N/A | 2023-02-08 | 2023-02-17 | 2023-02-17 | 2023-02-22 | 2023-02-22 | GoP | 5000 | 5000 | - | 4997.5 | 4997.5 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
66 | Office Supplies Expenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-07 | N/A | 2023-02-10 | 2023-02-10 | 2023-02-10 | N/A | N/A | 2023-02-10 | 2023-02-23 | 2023-02-23 | 2023-03-02 | 2023-03-02 | GoP | 61475 | 61475 | - | 61125 | 61125 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
67 | Other Supplies & Materials Expenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-06 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-02-17 | 2023-02-17 | 2023-02-22 | 2023-02-22 | GoP | 20150 | 20150 | - | 20075 | 20075 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
68 | ICT Training Expenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-07 | N/A | 2023-03-10 | 2023-03-10 | 2023-03-10 | N/A | N/A | 2023-03-10 | 2023-03-23 | 2023-03-23 | 2023-03-30 | 2023-03-30 | GoP | 118419 | 118419 | - | 118000 | 118000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
69 | Training Expenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-07 | N/A | 2023-02-10 | 2023-02-10 | 2023-02-10 | N/A | N/A | 2023-02-10 | 2023-02-23 | 2023-02-23 | 2023-03-02 | 2023-03-02 | GoP | 67084 | 67084 | - | 66684 | 66684 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
70 | R & M Water Supply System | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-07 | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 | N/A | N/A | 2023-02-08 | 2023-02-23 | 2023-02-23 | 2023-03-02 | 2023-03-02 | GoP | 48419 | 48419 | - | 48200 | 48200 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
71 | Mobile Expenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-06 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-02-17 | 2023-02-17 | 2023-02-22 | 2023-02-22 | GoP | 8100 | 8100 | - | 8096.5 | 8096.5 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
72 | Semi Expendable ICT Equipment | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-07 | N/A | 2023-02-10 | 2023-02-10 | 2023-02-10 | N/A | N/A | 2023-02-10 | 2023-02-23 | 2023-02-23 | 2023-03-02 | 2023-03-02 | GoP | 187996 | 187996 | - | 187296 | 187296 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
73 | Semi Expendable Communication Equipment | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-06 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-02-17 | 2023-02-17 | 2023-02-22 | 2023-02-22 | GoP | 7500 | 7500 | - | 7450 | 7450 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
74 | Semi Expendable other Machinery & Equipment Disaster Response & Rescue Equipment | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-07 | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 | N/A | N/A | 2023-02-08 | 2023-02-17 | 2023-02-17 | 2023-02-22 | 2023-02-22 | GoP | 32000 | 32000 | - | 31700 | 31700 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
75 | Chemical & Filtering Supplies Espenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-06 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-07 | 2023-02-17 | 2023-02-17 | 2023-02-22 | 2023-02-22 | GoP | 20350 | 20350 | - | 20200 | 20200 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
76 | Semi Expendable Military Police & Security Equipment | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-07 | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 | N/A | N/A | 2023-02-08 | 2023-02-17 | 2023-02-17 | 2023-02-22 | 2023-02-22 | GoP | 20350 | 20350 | - | 20200 | 20200 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
77 | Representation Expenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-06 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-04-14 | 2023-04-14 | 2023-04-25 | 2023-05-17 | GoP | 47500 | 47500 | - | 47300 | 47300 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
78 | Other Supplies & Materials Expenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-07 | N/A | 2023-03-08 | 2023-03-08 | 2023-03-08 | N/A | N/A | 2023-03-08 | 2023-03-31 | 2023-03-31 | 2023-04-13 | 2023-06-22 | GoP | 27000 | 27000 | - | 26800 | 26800 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
79 | Training Supplies Expenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-08 | N/A | 2023-03-13 | 2023-03-13 | 2023-03-13 | N/A | N/A | 2023-03-13 | 2023-03-23 | 2023-03-23 | 2023-03-30 | 2023-04-17 | GoP | 80640 | 80640 | - | 80360 | 80360 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
80 | R & M Semi Expendable other Machinery & Equipment | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-07 | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-03-08 | 2023-04-28 | 2023-04-28 | 2023-05-11 | 2023-04-17 | GoP | 33000 | 33000 | - | 32820 | 32820 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
81 | Mobile Expenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-06 | N/A | 2023-02-16 | 2023-02-07 | 2023-02-16 | N/A | N/A | 2023-02-07 | 2023-02-17 | 2023-02-17 | 2023-02-22 | 2023-05-08 | GoP | 11600 | 11600 | - | 11591 | 11591 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
82 | Cable Expenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-07 | N/A | 2023-02-16 | 2023-02-08 | 2023-02-16 | N/A | N/A | 2023-02-08 | 2023-05-03 | 2023-05-03 | 2023-05-08 | 2023-05-18 | GoP | 5000 | 5000 | - | 4900 | 4900 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
83 | Semi Expendable ICT Equipment | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-08 | N/A | 2023-03-13 | 2023-03-13 | 2023-03-13 | N/A | N/A | 2023-03-13 | 2023-03-31 | 2023-03-31 | 13 Aprl 23 | 13 Aprl 23 | GoP | 252504 | 252504 | - | 252024 | 252024 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
84 | ICT Office Supplies Expenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-06 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | 2023-03-23 | 2023-03-23 | 2023-03-30 | 2023-03-30 | GoP | 3000 | 3000 | - | 2900 | 2900 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
85 | Semi Expendable other Machinery Equipment | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-08 | N/A | 2023-03-13 | 2023-03-13 | 2023-03-13 | N/A | N/A | 2023-03-13 | 2023-03-23 | 2023-03-23 | 2023-03-30 | 2023-03-30 | GoP | 97603 | 97603 | - | 97223 | 97223 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
86 | R & M Building | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-14 | N/A | 2023-03-17 | 2023-03-17 | 2023-03-17 | N/A | N/A | 2023-03-17 | 2023-04-28 | 2023-04-28 | 2023-05-11 | 2023-05-11 | GoP | 84330 | 84330 | - | 83955 | 83955 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
87 | Med,Den & Lab Supplies | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-18 | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-02-21 | 2023-04-28 | 2023-04-28 | 2023-05-11 | 2023-05-11 | GoP | 19400 | 19400 | - | 83955 | 83955 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
88 | Office Equipment | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-20 | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-03-21 | 2023-05-26 | 2023-05-26 | 2023-06-09 | 2023-06-09 | GoP | 15000 | 15000 | - | 26800 | 26800 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
89 | Office Supplies | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-31 | N/A | 2023-04-03 | 2023-04-03 | 2023-04-03 | N/A | N/A | 2023-04-03 | 2023-05-26 | 2023-05-26 | 2023-06-09 | 2023-06-09 | GoP | 38310 | 38310 | - | 38000 | 38000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
90 | Semi-Expendable ICT Equipment | FC, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-23 | N/A | 2027-01-27 | 2027-01-27 | 2027-01-27 | N/A | N/A | 2023-01-27 | 2023-02-08 | 2023-02-08 | 2023-02-23 | 2023-02-23 | GoP | 170450 | 170450 | - | 170130 | 170130 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
91 | R&M Buildings | FC, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-23 | N/A | 2027-01-27 | 2027-01-27 | 2027-01-27 | N/A | N/A | 2023-01-27 | 2023-02-08 | 2023-02-08 | 2023-02-23 | 2023-02-23 | GoP | 75850 | 75850 | - | 75480 | 75480 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
92 | Medical, Dental and Laboratory Supplies Expenses | FC, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-23 | N/A | 2027-01-27 | 2027-01-27 | 2027-01-27 | N/A | N/A | 2023-01-25 | 2023-02-08 | 2023-02-08 | 2023-02-23 | 2023-02-23 | GoP | 49328 | 49328 | - | 48928 | 48928 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
93 | R&M Other Machinery & Equipment | FC, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-01-23 | N/A | 2023-01-24 | 2023-01-24 | 2023-01-24 | N/A | N/A | 2023-01-24 | 2023-01-24 | 2023-01-24 | 2023-02-23 | 2023-02-23 | GoP | 48550 | 48550 | - | 48000 | 48000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
94 | Semi-Expendable - Military Police and Security Equipment | FC, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-03 | N/A | 2023-02-06 | 2023-02-06 | 2023-02-06 | N/A | N/A | 2023-02-06 | 2023-02-06 | 2023-02-06 | 2023-03-02 | 2023-03-02 | GoP | 28000 | 28000 | - | 27800 | 27800 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
95 | R&M Buildings | FC, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-04 | N/A | 2023-05-08 | 2023-05-08 | 2023-05-08 | N/A | N/A | 2023-05-08 | 2023-05-29 | 2023-05-29 | 2023-06-02 | 2023-06-02 | GoP | 313707 | 313707 | - | 313167 | 313167 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
96 | R&M Motor Vehicles (Ford Ranger) | FC, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-12 | N/A | 2023-04-17 | 2023-04-17 | 2023-04-17 | N/A | N/A | 2023-04-17 | 2023-05-18 | 2023-05-18 | 2023-06-02 | 2023-06-02 | GoP | 61045 | 61045 | - | 60700 | 60700 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
97 | Semi-Expendable ICT Equipment | FC, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-12 | N/A | 2023-04-13 | 2023-04-13 | 2023-04-13 | N/A | N/A | 2023-04-13 | 2023-05-18 | 2023-05-18 | 2023-06-02 | 2023-06-02 | GoP | 25300 | 25300 | - | 25100 | 25100 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
98 | ICT Software | FC, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-11 | N/A | 2023-04-12 | 2023-04-12 | 2023-04-12 | N/A | N/A | 2023-04-12 | 2023-05-18 | 2023-05-18 | 2023-06-02 | 2023-06-02 | GoP | 50000 | 50000 | - | 49700 | 49700 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
99 | Repair and Maintenance Other Structure | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | 2023-03-07 | 2023-04-03 | 2023-04-11 | 2023-04-11 | 2023-04-14 | 2023-04-14 | GoP | 49845 | 49845 | - | 49575.5 | 49575.5 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
100 | R&M Building | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | 2023-03-07 | 2023-04-03 | 2023-04-11 | 2023-04-11 | 2023-04-14 | 2023-04-14 | GoP | 155790 | 155790 | - | 155512 | 155512 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
101 | Medical, Dental & Laboratory Supplies Expenses | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-24 | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | 2023-02-28 | 2023-03-17 | 2023-03-27 | 2023-03-27 | 2023-03-30 | 2023-03-30 | GoP | 5000 | 5000 | - | 4800 | 4800 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
102 | Other Supplies and Materials Expenses | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-28 | N/A | 2023-03-03 | 2023-03-03 | 2023-03-03 | N/A | 2023-03-03 | 2023-03-17 | 2023-03-27 | 2023-03-27 | 2023-03-30 | 2023-03-30 | GoP | 18920 | 18920 | - | 18500 | 18500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
103 | Semi-Expendable ICT Equipment | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-24 | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | 2023-02-28 | 2023-05-15 | 2023-05-23 | 2023-05-23 | 2023-05-26 | 2023-05-26 | GoP | 27900 | 27900 | - | 27003 | 27003 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
104 | R&M Motor Veh | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-24 | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | 2023-02-28 | 2023-04-03 | 2023-04-11 | 2023-04-11 | 2023-04-14 | 2023-04-14 | GoP | 36748 | 36748 | - | 36490 | 36490 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
105 | R&M Motor Veh | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-04 | N/A | 2023-05-09 | 2023-05-09 | 2023-05-09 | N/A | 2023-05-09 | 2023-06-06 | 2023-06-14 | 2023-06-14 | 2023-06-19 | 2023-06-19 | GoP | 78998 | 78998 | - | 78000 | 78000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
106 | Other Supplies and Materials Expenses | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | 2023-03-07 | 2023-05-05 | 2023-05-15 | 2023-05-15 | 2023-05-19 | 2023-05-19 | GoP | 18380 | 18380 | - | 18015 | 18015 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
107 | Representation Expenses | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | 2023-03-07 | 2023-05-05 | 2023-05-15 | 2023-05-15 | 2023-05-19 | 2023-05-19 | GoP | 21020 | 21020 | - | 20870 | 20870 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
108 | Representation Expenses | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | 2023-03-07 | 2023-05-05 | 2023-05-15 | 2023-05-15 | 2023-05-19 | 2023-05-19 | GoP | 22280 | 22280 | - | 21345 | 21345 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
109 | Other Supplies and Materials Expenses | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | 2023-03-07 | 2023-05-29 | 2023-06-07 | 2023-06-07 | 2023-06-13 | 2023-06-13 | GoP | 30816 | 30816 | - | 30137 | 30137 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
110 | Semi-expendable ICT Equipment | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | 2023-03-07 | 2023-05-29 | 2023-06-07 | 2023-06-07 | 2023-06-13 | 2023-06-13 | GoP | 63600 | 63600 | - | 63000 | 63000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
111 | Semi-expendable ICT Software Subscription | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | 2023-03-07 | 2023-05-29 | 2023-06-07 | 2023-06-07 | 2023-06-13 | 2023-06-13 | GoP | 3120 | 3120 | - | 2970 | 2970 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
112 | Semi-expendable Communication Equipment | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | 2023-03-07 | 2023-05-29 | 2023-06-07 | 2023-06-07 | 2023-06-13 | 2023-06-13 | GoP | 27900 | 27900 | - | 27504 | 27504 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
113 | ICT Software Subscription | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-20 | N/A | 2023-05-25 | 2023-05-25 | 2023-05-25 | N/A | 2023-05-25 | 2023-06-06 | 2023-06-14 | 2023-06-14 | 2023-06-19 | 2023-06-19 | GoP | 3120 | 3120 | - | 3000 | 3000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
114 | R&M Other Structure | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-04 | N/A | 2023-05-09 | 2023-05-09 | 2023-05-09 | N/A | 2023-05-09 | 2023-06-23 | 2023-07-03 | 2023-07-03 | 2023-07-03 | 2023-07-03 | GoP | 66200 | 66200 | - | 65734 | 65734 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
115 | Semi-Expendable Communication Equipment | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-15 | N/A | 2023-04-17 | 2023-04-17 | 2023-04-17 | N/A | 2023-04-20 | 2023-05-29 | 2023-06-06 | 2023-06-06 | 2023-06-09 | 2023-06-09 | GoP | 27900 | 27900 | - | 27500 | 27500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
116 | Enhancement of Safety Equipment | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-20 | N/A | 2023-02-24 | 2023-02-24 | 2023-02-24 | N/A | N/A | 2023-02-24 | 2023-03-22 | 2023-03-22 | 2023-03-24 | 2023-03-24 | GoP | 10000 | 10000 | - | 9850 | 9850 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
117 | Procurement of ICT Software Subscription | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-02 | N/A | 2023-02-06 | 2023-02-06 | 2023-02-06 | N/A | N/A | 2023-02-06 | 2023-02-14 | 2023-02-14 | 2023-03-16 | 2023-03-16 | GoP | 37800 | 37800 | - | 37645 | 37645 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
118 | Internet Expenses | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-20 | N/A | 2023-02-24 | 2023-02-20 | 2023-02-20 | N/A | N/A | 2023-02-27 | 2023-03-22 | 2023-03-22 | 2023-03-24 | 2023-03-24 | GoP | 18000 | 18000 | - | 17900 | 17900 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
119 | Mobile Expenses | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-20 | N/A | 2023-02-24 | 2023-02-20 | 2023-02-20 | N/A | N/A | 2023-02-27 | 2023-03-22 | 2023-03-22 | 2023-03-24 | 2023-03-24 | GoP | 30000 | 30000 | - | 29844 | 29844 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
120 | Procurement of Medical Supplies | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-20 | N/A | 2023-02-24 | 2023-02-20 | 2023-02-20 | N/A | N/A | 2023-02-27 | 2023-03-22 | 2023-03-22 | 2023-03-24 | 2023-03-24 | GoP | 33500 | 33500 | - | 33314 | 33314 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
121 | Procurement of TV load cards | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-20 | N/A | 2023-02-24 | 2023-02-24 | 2023-02-24 | N/A | N/A | 2023-02-27 | 2023-03-24 | 2023-03-24 | 2023-03-27 | 2023-03-27 | GoP | 6000 | 6000 | - | 5880 | 5880 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
122 | Termite Control | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-20 | N/A | 2023-02-24 | 2023-02-24 | 2023-02-24 | N/A | N/A | 2023-02-27 | 2023-03-21 | 2023-03-21 | 2023-03-23 | 2023-03-23 | GoP | 2550 | 2550 | - | 2460 | 2460 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
123 | Procurement of Construction Materials | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-20 | N/A | 2023-02-24 | 2023-02-24 | 2023-02-24 | N/A | N/A | 2023-02-27 | 2023-03-21 | 2023-03-21 | 2023-03-23 | 2023-03-23 | GoP | 309000 | 309000 | - | 308577 | 308577 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
124 | R/M Of Motor Vehicles | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-13 | N/A | 2023-03-17 | 2023-03-17 | 2023-03-17 | N/A | N/A | 2023-03-20 | 2023-05-04 | 2023-05-04 | 2023-05-08 | 2023-05-08 | GoP | 10000 | 10000 | - | 9815 | 9815 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
125 | Procurement of Construction Materials | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-13 | N/A | 2023-03-17 | 2023-03-17 | 2023-03-17 | N/A | N/A | 2023-03-20 | 2023-05-04 | 2023-05-04 | 2023-05-08 | 2023-05-08 | GoP | 85000 | 85000 | - | 84695 | 84695 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
126 | Internet Expenses | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-13 | N/A | 2023-03-17 | 2023-03-17 | 2023-03-17 | N/A | N/A | 2023-03-17 | 2023-05-04 | 2023-05-04 | 2023-05-08 | 2023-05-08 | GoP | 18000 | 18000 | - | 17900 | 17900 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
127 | Mobile Expenses | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-13 | N/A | 2023-03-17 | 2023-03-17 | 2023-03-17 | N/A | N/A | 2023-03-17 | 2023-05-04 | 2023-05-04 | 2023-05-08 | 2023-05-08 | GoP | 30000 | 30000 | - | 29894 | 29894 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
128 | Procurement of Medical Supplies | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-13 | N/A | 2023-03-17 | 2023-03-17 | 2023-03-17 | N/A | N/A | 2023-03-17 | 2023-05-04 | 2023-05-04 | 2023-05-08 | 2023-05-08 | GoP | 17500 | 17500 | - | 17390 | 17390 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
129 | Procurement of TV load cards | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-13 | N/A | 2023-03-17 | 2023-03-17 | 2023-03-17 | N/A | N/A | 2023-03-17 | 2023-05-04 | 2023-05-04 | 2023-05-08 | 2023-05-08 | GoP | 6000 | 6000 | - | 5940 | 5940 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
130 | Termite Control | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-13 | N/A | 2023-03-17 | 2023-03-17 | 2023-03-17 | N/A | N/A | 2023-03-17 | 2023-05-04 | 2023-05-04 | 2023-05-08 | 2023-05-08 | GoP | 2550 | 2550 | - | 2500 | 2500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
131 | Office Supplies | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-13 | N/A | 2023-03-17 | 2023-03-17 | 2023-03-17 | N/A | N/A | 2023-03-17 | 2023-05-04 | 2023-05-04 | 2023-05-08 | 2023-05-08 | GoP | 18815.25 | 18815.25 | - | 18700 | 18700 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
132 | R/M Of Motor Vehicles | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-27 | N/A | 2023-03-31 | 2023-03-31 | 2023-03-31 | N/A | N/A | 2023-03-31 | 2023-05-31 | 2023-05-31 | 2023-06-02 | 2023-06-02 | GoP | 240000 | 240000 | - | 239795 | 239795 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
133 | Other Supplies & Materials Expenses | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-04 | N/A | 2023-04-11 | 2023-04-11 | 2023-04-11 | N/A | N/A | 2023-04-11 | 2023-05-17 | 2023-05-17 | 2023-05-19 | 2023-05-19 | GoP | 19512 | 19512 | - | 19382 | 19382 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
134 | R/M Office Building | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-27 | N/A | 2023-03-31 | 2023-03-31 | 2023-03-31 | N/A | N/A | 2023-03-31 | 2023-05-23 | 2023-05-23 | 2023-05-25 | 2023-05-25 | GoP | 80000 | 80000 | - | 79790 | 79790 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
135 | Proc. Semi-Expendable -ICT Equipment | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-27 | N/A | 2023-03-31 | 2023-03-31 | 2023-03-31 | N/A | N/A | 2023-03-31 | 2023-05-16 | 2023-05-16 | 2023-05-18 | 2023-05-18 | GoP | 311160 | 311160 | - | 310800 | 310800 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
Total Allotted Budget of Procurement Activities | [19 empty] | 11142791.79 |  |  | 11069411.5
Total Contract Price of Procurement Activities Conducted
Total Savings (Total Alloted Budget- Total Contract Price) | [22 empty] | 73380.29
ONGOING PROCUREMENT ACTIVITIES
1 | Enhancement of Street Lights | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-16 | N/A | 2023-02-21 | 2023-02-21 | 2023-02-21 | N/A | N/A | 2023-02-21 | - | - | - | - | GoP | 82260 | 82260 | - | 82164 | 82164 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
2 | Enhancement of Power Supply | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-14 | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | - | - | - | - | GoP | 25000 | 25000 | - | 24950 | 24950 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
3 | Repair & Maintenance of ICT Equipment | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-16 | N/A | 2023-02-21 | 2023-02-21 | 2023-02-21 | N/A | N/A | 2023-02-21 | - | - | - | - | GoP | 252081 | 252081 | - | 251796 | 251796 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
4 | Enhancement of Water Supply System | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-12 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 200000 | 200000 | - | 199600 | 199600 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
5 | Enhancement of Commanders Quarters | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-27 | N/A | 2023-05-03 | 2023-05-03 | 2023-05-03 | N/A | N/A | 2023-05-03 | - | - | - | - | GoP | 50000 | 50000 | - | 49500 | 49500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
6 | ICT Office Supplies | HTRADOC,PA | NO | Shopping 52.1(b) | N/A | 2023-04-24 | N/A | 2023-04-27 | 2023-04-27 | 2023-04-27 | N/A | N/A | 2023-04-27 | - | - | - | - | GoP | 11234 | 11234 | - | 11178 | 11178 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
7 | Office & Janitorial Supplies | HTRADOC,PA | NO | Shopping 52.1(b) | N/A | 2023-04-12 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 469183 | 469183 | - | 468093 | 468093 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
8 | Repair & Maintenance of Vehicle | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-13 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 16200 | 16200 | - | 15810 | 15810 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
9 | Semi- Expendable Disaster Response & Rescue Equipment | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-12 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 150000 | 150000 | - | 149950 | 149950 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
10 | Semi- Expendable Machinery | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-12 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 150000 | 150000 | - | 150000 | 150000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
11 | Printing and Publication of OG7 | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-12 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 100000 | 100000 | - | 99500 | 99500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
12 | Office Equipment | HTRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-12 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 105000 | 105000 | - | 104750 | 104750 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
13 | Enhancement of Furniture & Fixture of AOLS | ALDEC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-14 | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | - | - | - | - | GoP | 39000 | 39000 | - | 38800 | 38800 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
14 | Enhancement of Office Equipment | ALDEC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-16 | N/A | 2023-02-21 | 2023-02-21 | 2023-02-21 | N/A | N/A | 2023-02-21 | - | - | - | - | GoP | 52643 | 52643 | - | 52200 | 52200 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
15 | Enhancement of ICT Equipment ALDEC & AOLS | ALDEC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-13 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 216590 | 216590 | - | 205420 | 205420 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
16 | Enhancement of CCTV | ALDEC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-13 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 15000 | 15000 | - | 12000 | 12000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
17 | R&M Vehicle Ranger | ALDEC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-11 | N/A | 2023-05-11 | 2023-05-11 | 2023-05-11 | N/A | N/A | 2023-05-11 | - | - | - | - | GoP | 92360 | 92360 | - | 89560 | 89560 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
18 | Office Supplies for 2nd Qtr 2023 | ALDEC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-22 | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | - | - | - | - | GoP | 16375 | 16375 | - | 15875 | 15875 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
19 | ICT Training Equipment | CAC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | - | - | - | - | GoP | 46998 | 46998 | - | 46500 | 46500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
20 | R&M of Hi-lux & Motorcycle | CAC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-06-02 | N/A | 2023-06-06 | 2023-06-06 | 2023-06-06 | N/A | N/A | 2023-06-06 | - | - | - | - | GoP | 17500 | 17500 | - | 17250 | 17250 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
21 | Semi-Expendable Furniture & Fixtures | CAC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-23 | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | - | - | - | - | GoP | 73195 | 73195 | - | 72300 | 72300 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
22 | Medical supplies | CAC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-25 | N/A | 2023-05-30 | 2023-05-30 | 2023-05-30 | N/A | N/A | 2023-05-30 | - | - | - | - | GoP | 9798 | 9798 | - | 9798 | 9798 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
23 | Office Supplies | CAC, TRADOC, PA | NO | Shopping 52.1(b) | N/A | 2023-05-29 | N/A | 2023-05-30 | 2023-05-30 | 2023-05-30 | N/A | N/A | 2023-05-30 | - | - | - | - | GoP | 21490 | 21490 | - | 21490 | 21490 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
24 | R&M Motor Vehicle | CAC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | - | - | - | - | GoP | 17500 | 17500 | - | 17500 | 17500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
25 | R&M ICT Equipment | CAC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-06-08 | N/A | 2023-06-13 | 2023-06-13 | 2023-06-13 | N/A | N/A | 2023-06-13 | - | - | - | - | GoP | 86700 | 86700 | - | 86700 | 86700 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
26 | Medical Supplies | CFWDC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-12 | N/A | 2023-04-17 | 2023-04-17 | 2023-04-17 | N/A | N/A | 2023-04-17 | - | - | - | - | GoP | 22000 | 22000 | - | 20000 | 20000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
27 | Covid Mitigation | CFWDC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-12 | N/A | 2023-04-17 | 2023-04-17 | 2023-04-17 | N/A | N/A | 2023-04-17 | - | - | - | - | GoP | 9350 | 9350 | - | 7400 | 7400 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
28 | Enhancement of ICT | CFWDC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-11 | N/A | 2023-05-16 | 2023-05-16 | 2023-05-16 | N/A | N/A | 2023-05-16 | - | - | - | - | GoP | 193600 | 193600 |  | 193100 | 193100 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
29 | ICT Subscription | CFWDC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-11 | N/A | 2023-05-16 | 2023-05-16 | 2023-05-16 | N/A | N/A | 2023-05-16 | - | - | - | - | GoP | 64000 | 64000 | - | 52000 | 52000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
30 | Enhancement of CCTV | CFWDC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-23 | N/A | 2023-05-25 | 2023-05-25 | 2023-05-25 | N/A | N/A | 2023-05-25 | - | - | - | - | GoP | 14000 | 14000 | - | 14000 | 14000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
31 | R&M of Ford Ranger | DACIC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-14 | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | N/A | N/A | 2023-02-17 | - | - | - | - | GoP | 28690 | 28690 | - | 28490 | 28490 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
32 | Parking Bay | DACIC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-13 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 132610 | 132610 | - | 131400 | 131400 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
33 | Drug and medicine | DACIC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-17 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 19500 | 19500 | - | 16000 | 16000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
34 | Quarantine Fcility | DACIC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-13 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 145149 | 145149 | - | 144300 | 144300 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
35 | Enhancement of Health Care (Dental) Equipment | DENTAL TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-24 | N/A | 2023-04-27 | 2023-04-27 | 2023-04-27 | N/A | N/A | 2023-04-27 | - | - | - | - | GoP | 75000 | 75000 | - | 74900 | 74900 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
36 | Procurement of Dental Equipment | DENTAL TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-24 | N/A | 2023-04-27 | 2023-04-27 | 2023-04-27 | N/A | N/A | 2023-04-27 | - | - | - | - | GoP | 120000 | 120000 | - | 118500 | 118500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
37 | R&M Elevated Water Tank | DENTAL TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-08 | N/A | 2023-05-11 | 2023-05-11 | 2023-05-11 | N/A | N/A | 2023-05-11 | - | - | - | - | GoP | 48000 | 48000 | - | 47650 | 47650 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
38 | Sustainment of IFAK | IMTC (P),TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-02 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-03 | - | - | - | - | GoP | 22500 | 22500 | - | 22200 | 22200 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
39 | Enhancement of IMTC Storage Room | IMTC (P),TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-03 | N/A | 2023-02-07 | 2023-02-07 | 2023-02-07 | N/A | N/A | 2023-02-03 | - | - | - | - | GoP | 30000 | 30000 | - | 30000 | 30000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
40 | R& M Of Vehicle (Motorcycle Bajaj) | IMTC (P),TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-22 | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2024-03-28 | - | - | - | - | GoP | 12000 | 12000 | - | 11510 | 11510 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
41 | R& M Of Vehicle (Ford Ranger) | IMTC (P),TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-06-02 | N/A | 2023-06-06 | 2023-06-06 | 2023-06-06 | N/A | N/A | 2023-06-06 | - | - | - | - | GoP | 75700 | 75700 | - | 75465 | 75465 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
42 | Enhancment of Office Equipment | IMTC (P),TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-13 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 49000 | 49000 | - | 47000 | 47000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
43 | Enhancment of ICT Equipment | IMTC (P),TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-13 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 182500 | 182500 | - | 166000 | 166000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
44 | Enhancement of quarter master equipment | LWC,TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-27 | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | - | - | - | - | GoP | 11880 | 11880 | - | 11880 | 11880 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
45 | Enhancement of ICT | LWC,TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-28 | N/A | 2023-05-03 | 2023-05-03 | 2023-05-03 | N/A | N/A | 2023-05-03 | - | - | - | - | GoP | 11880 | 179800 | - | 11880 | 179800 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
46 | R & M of Toyota Innova and Hilux | LWC,TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-25 | N/A | 2023-05-01 | 2023-05-01 | 2023-05-01 | N/A | N/A | 2023-05-01 | - | - | - | - | GoP | 109200 | 109200 | - | 109200 | 109200 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
47 | IFAK | LWC,TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-14 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 33050 | 33050 | - | 33050 | 33050 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
48 | Enhancement of PWD | LWC,TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-14 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 11800 | 11800 | - | 11800 | 11800 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
49 | Enhancement of supply room | LWC,TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-14 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 45000 | 45000 | - | 45000 | 45000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
50 | Grasscutter, 4 stroke, gasoline | LWC,TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-27 | N/A | 2023-05-03 | 2023-05-03 | 2023-05-03 | N/A | N/A | 2023-05-03 | - | - | - | - | GoP | 97750 | 97750 | - | 97750 | 97750 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
51 | R&M of Vehicle (Ambulance) | MEDICAL, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | - | - | - | - | GoP | 21000 | 21000 | - | 20700 | 20700 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
52 | Procurement of Drugs and Medicines | MEDICAL, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-09 | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | - | - | - | - | GoP | 120710 | 120710 | - | 88848 | 88848 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
53 | Procurement of CCTV Camera | MEDICAL, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-09 | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | - | - | - | - | GoP | 30000 | 30000 | - | 26000 | 26000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
54 | R&M of Vehicle (Ambulance) | MEDICAL, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-27 | N/A | 2023-05-03 | 2023-05-03 | 2023-05-03 | N/A | N/A | 2023-05-03 | - | - | - | - | GoP | 72000 | 72000 | - | 69500 | 69500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
55 | Enhancement of Billeting Facility for Female EP | MTS, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-13 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | 2023-06-14 | 2023-06-14 | - | - | GoP | 53000 | 53000 | - | 50000 | 50000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
56 | R&M of Tractor | MTS, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-13 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 62330 | 62330 | - | 59500 | 59500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
57 | Support for Enhancement of Student Barracks | NCOS,ALDEC,TRADOC PA | N/A | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | - | - | - | - | GoP | 3000 | 3000 | - | 2900 | 2900 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
58 | Support for COVID-19 Mitigation and Prevention | NCOS,ALDEC,TRADOC PA | N/A | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | - | - | - | - | GoP | 24100 | 24100 | - | 22131 | 22131 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
59 | Enhancement of Software System | NCOS,ALDEC,TRADOC PA | N/A | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | - | - | - | - | GoP | 38000 | 38000 | - | 36500 | 36500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
60 | Enhancement of NCOS Admin Office | NCOS,ALDEC,TRADOC PA | N/A | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | - | - | - | - | GoP | 262600 | 262600 | - | 262500 | 262500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
61 | Enhancement of Machinery | OCS, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-19 | N/A | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | 2023-05-23 | - | - | - | - | GoP | 112073 | 112073 | - | 111800 | 111800 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
62 | Enhancement of Training Equipment | OCS, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-24 | N/A | 2023-04-27 | 2023-04-27 | 2023-04-27 | N/A | N/A | 2023-04-27 | - | - | - | - | GoP | 70430 | 70430 | - | 69000 | 69000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
63 | Enhancement of Offices (Procurement of Office Partition) | OCS, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-27 | N/A | 2023-05-03 | 2023-05-03 | 2023-05-03 | N/A | N/A | 2023-05-03 | - | - | - | - | GoP | 135688 | 135688 | - | 132000 | 132000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
64 | Installation of Railings for PWD & Senior Citizen (Admin Bldg 2nd Floor CR) | OCS, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-05 | N/A | 2023-05-16 | 2023-05-16 | 2023-05-16 | N/A | N/A | 2023-05-16 | - | - | - | - | GoP | 27000 | 27000 | - | 26940 | 26940 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
65 | R&M of Billeting Facilities (Bldg 5 CR) | OCS, TRADOC,PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-19 | N/A | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | 2023-05-23 | - | - | - | - | GoP | 86480 | 86480 | - | 86050 | 86050 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
66 | Semi-Expandable ICT Equipmnt | SCS, IMTC (P) | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-27 | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | - | - | - | - | GoP | 120000 | 120000 | - | 119000 | 119000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
67 | R&M Building, Support for PWD | SCS, IMTC (P) | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-27 | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | N/A | 2023-02-28 | - | - | - | - | GoP | 155000 | 155000 | - | 155000 | 155000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
68 | R&M Motor Vehicle | SCS, IMTC (P) | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-27 | N/A | 2023-04-27 | 2023-04-27 | 2023-04-27 | N/A | N/A | 2023-04-27 | - | - | - | - | GoP | 80000 | 80000 | - | 77000 | 77000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
69 | Enhancement of EP Barracks | SCS, IMTC (P) | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-19 | N/A | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | 2023-05-23 | - | - | - | - | GoP | 380200 | 380200 | - | 378700 | 378700 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
70 | Enhancement of Officers Barracks | SCS, IMTC (P) | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-18 | N/A | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | 2023-05-23 | - | - | - | - | GoP | 619799 | 619799 | - | 619599 | 619599 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
71 | Enhancement of Student Classrooms | SCS, IMTC (P) | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-18 | N/A | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | 2023-05-23 | - | - | - | - | GoP | 950000 | 950000 | - | 949400 | 949400 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
72 | Enhancement of Comfort Rooms | SCS, IMTC (P) | NO | NP-53.9 - Small Value Procurement | N/A | 2023-06-08 | N/A | 2023-06-13 | 2023-06-13 | 2023-06-13 | N/A | N/A | 2023-06-13 | - | - | - | - | GoP | 450,00.00 | 450000 | - | 449500 | 449500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
73 | Enhancement of ICT equipment | TAC,TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-03 | N/A | 2023-03-13 | 2023-03-13 | 2023-03-13 | N/A | N/A | 2023-03-13 | - | - | - | - | GoP | 140000 | 140000 | - | 139600 | 139600 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
74 | R&M of Toyota Hilux | TAC,TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-02 | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | - | - | - | - | GoP | 50000 | 50000 | - | 49500 | 49500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
75 | R&M of Toyota Innova | TAC,TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-13 | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | N/A | 2023-03-15 | - | - | - | - | GoP | 85000 | 85000 | - | 84500 | 84500 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
76 | Enhancement of CMO Equipment | TAC,TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-13 | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | N/A | 2023-03-15 | - | - | - | - | GoP | 12000 | 12000 | - | 12000 | 12000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
77 | Office Supplies | TAC,TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 03-Apl-23 | N/A | 2023-05-05 | 2023-05-05 | 2023-05-05 | N/A | N/A | 2023-05-05 | - | - | - | - | GoP | 60500 | 60500 | - | 53600 | 53600 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
78 | Repainting of Toyota Hilux | TAC,TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-21 | N/A | 2023-06-05 | 2023-06-05 | 2023-06-05 | N/A | N/A | 2023-06-05 | - | - | - | - | GoP | 23000 | 23000 | - | 23000 | 23000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
79 | Repainting of Toyota Innova | TAC,TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-21 | N/A | 2023-06-06 | 2023-06-06 | 2023-06-06 | N/A | N/A | 2023-06-06 | 2023-06-14 | 2023-06-14 | - | - | GoP | 60000 | 60000 | - | 59680 | 59680 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
80 | Office Supplies | TAC,TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-21 | N/A | 2023-06-05 | 2023-06-05 | 2023-06-05 | N/A | N/A | 2023-06-05 | - | - | - | - | GoP | 60000 | 60000 | - | 60000 | 60000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
81 | Office Supplies | TAC,TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-21 | N/A | 2023-06-05 | 2023-06-05 | 2023-06-05 | N/A | N/A | 2023-06-05 | 2023-06-14 | 2023-06-14 | - | - | GoP | 5000 | 5000 | - | 4985 | 4985 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
82 | Office Supplies | TAC,TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-21 | N/A | 2023-06-05 | 2023-06-05 | 2023-06-05 | N/A | N/A | 2023-06-05 | 2023-06-14 | 2023-06-14 | - | - | GoP | 23000 | 23000 | - | 22960 | 22960 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
83 | R&M Facility (TDC Barracks) | TDC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-03 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | - | - | - | - | GoP | 60000 | 60000 | - | 59800 | 59800 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
84 | R&M Crosswind | TDC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-13 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 52500 | 52500 | - | 52450 | 52450 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
85 | PWD Walkways | TDC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-13 | N/A | 2023-04-13 | 2023-04-13 | 2023-04-13 | N/A | N/A | 2023-04-13 | - | - | - | - | GoP | 12000 | 12000 | - | 11970 | 11970 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
86 | HADR Equipment | TDC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-13 | N/A | 2023-04-13 | 2023-04-13 | 2023-04-13 | N/A | N/A | 2023-04-13 | - | - | - | - | GoP | 12000 | 12000 | - | 11940 | 11940 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
87 | R&M ICT Equipment | TDC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-12 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 65000 | 65000 | - | 64, 800.00 | 64, 800.00 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
88 | Enhanement of Grasscutter | TSSC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-09 | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | - | - | - | - | GoP | 60000 | 60000 | - | 50000 | 50000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
89 | R & M of Vehicle | TSSC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-25 | N/A | 2023-05-30 | 2023-05-30 | 2023-05-30 | N/A | N/A | 2023-05-30 | - | - | - | - | GoP | 193200 | 193200 | - | 193000 | 193000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
90 | Sustainment of IFAK | TSSC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-09 | N/A | 2023-03-14 | 2023-03-14 | 2023-03-14 | N/A | N/A | 2023-03-14 | - | - | - | - | GoP | 24750 | 24750 | - | 21825 | 21825 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
91 | Enhancement of Water System | TSSC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-05-25 | N/A | 2023-05-30 | 2023-05-30 | 2023-05-30 | N/A | N/A | 2023-05-30 | - | - | - | - | GoP | 59588 | 59588 | - | 59288 | 59288 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
92 | R&M Water system | SC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-22 | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | 1934-07-03 | 1934-07-03 | 2023-07-10 | - | GOP | 30074 | 30074 | - | 30033 | 30033 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
93 | R&M of Classroom | SC, TRADOC, PA | NO | Shopping 52.1(b) | N/A | 2023-03-22 | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | 1934-07-03 | 1934-07-03 | 2023-07-10 | - | GOP | 13835 | 13835 | - | 12485 | 12485 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
94 | R&M Classroom 1st Floor | SC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-09 | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | N/A | N/A | 2023-02-14 | - | - | - | - | GOP | 46075 | 46075 | - | 45715 | 45715 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
95 | R&M Facility | SC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-16 | N/A | 2023-02-21 | 2023-02-21 | 2023-02-21 | N/A | N/A | 2023-02-21 | - | - | - | - | GOP | 306697 | 306697 | - | 306591 | 306591 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
96 | R&M Motor Vehicle | SC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-02-16 | N/A | 2023-02-21 | 2023-02-21 | 2023-02-21 | N/A | N/A | 2023-02-21 | - | - | - | - | GOP | 111771 | 111771 | - | 111105 | 111105 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
97 | R&M Classroom | SC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-22 | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | - | - | - | - | GOP | 70110 | 70110 | - | 69960 | 69960 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
98 | R&M Facility | SC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-22 | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | - | - | - | - | GOP | 138068 | 138068 | - | 135068 | 135068 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
99 | Admin and Logistical Requirments | SC, TRADOC, PA | NO | Shopping 52.1(b) | N/A | 2023-03-22 | N/A | 2023-03-28 | 2023-03-28 | 2023-03-28 | N/A | N/A | 2023-03-28 | - | - | - | - | GOP | 37838 | 37838 | - | 29878 | 29878 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
100 | R&M of PC Facility (Admin office/Conference Room) | PC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-04-14 | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | N/A | N/A | 2023-04-18 | - | - | - | - | GoP | 12700 | 12700 | - | 12700 | 12700 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
101 | Installation of CCTV Camera | PC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-15 | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-03-21 | - | - | - | - | GoP | 30000 | 30000 | - | 29800 | 29800 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
102 | Support to Janitorial Supplies | PC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-15 | N/A | 2023-03-21 | 2023-03-21 | 2023-03-21 | N/A | N/A | 2023-03-21 | - | - | - | - | GoP | 12570 | 12570 | - | 12270 | 12270 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
103 | R&M - Vehicle (Ford Ranger) | PC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-06-09 | N/A | 13 June '23 | 13 June '23 | 13 June '23 | N/A | N/A | 13 June '23 | - | - | - | - | GoP | 40000 | 40000 | - | 40000 | 40000 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
104 | Representation Expenses | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-06-23 | N/A | 2023-06-26 | 2023-06-26 | 2023-06-26 | N/A | N/A | 2023-06-26 | - | - | - | - | GoP | 40000 | 40000 | - | 39850 | 39850 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
105 | Semi Expendable ICT Equipment | MC, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-06-23 | N/A | 2023-06-26 | 2023-06-26 | 2023-06-26 | N/A | N/A | 2023-06-26 | - | - | - | - | GoP | 26900 | 26900 | - | 26380 | 26380 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
106 | Training Expenses | VAT G, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-04 | N/A | 2023-03-07 | 2023-03-07 | 2023-03-07 | N/A | N/A | 2023-03-07 | - | - | - | - | GoP | 165360 | 165360 | - | 163729 | 163729 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
107 | R/M Students Mess Hall | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-06-06 | N/A | 2023-06-13 | 2023-06-13 | 2023-06-13 | N/A | N/A | 2023-06-14 | - | - | - | - | GoP | 257185 | 257185 | - | 256790 | 256790 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
108 | R/M Students Charlie Barracks | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-06-06 | N/A | 2023-06-13 | 2023-06-13 | 2023-06-13 | N/A | N/A | 2023-06-14 | - | - | - | - | GoP | 530815 | 530815 | - | 530225 | 530225 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
109 | R/M Students Classroom | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-06-06 | N/A | 2023-06-13 | 2023-06-13 | 2023-06-13 | N/A | N/A | 2023-06-14 | - | - | - | - | GoP | 837061 | 837061 | - | 836625 | 836625 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
110 | R/M Students Bravo Barracks | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-06-06 | N/A | 2023-06-13 | 2023-06-13 | 2023-06-13 | N/A | N/A | 2023-06-14 | - | - | - | - | GoP | 530815 | 530815 | - | 530240 | 530240 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
111 | R/M Students Delta Barracks | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-06-06 | N/A | 2023-06-13 | 2023-06-13 | 2023-06-13 | N/A | N/A | 2023-06-14 | - | - | - | - | GoP | 681185 | 681185 | - | 680515 | 680515 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
112 | R/M Other Structures | MATG, TRADOC, PA | NO | NP-53.9 - Small Value Procurement | N/A | 2023-03-27 | N/A | 2023-03-31 | 2023-03-31 | 2023-03-31 | N/A | N/A | 2023-03-31 | - | - | - | - | GoP | 190000 | 190000 | - | 189739 | 189739 | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On- Going
Total Allotted Budget of Ongoing Procurement Activities | [18 empty] | 12470273
| Prepared By: | [5 empty] | Recommended Approval by: | [12 empty] | Approved by:
| Mary Ann N Oliveros | [5 empty] | DAISY J AGUSTIN | [12 empty] | LUIS REX D BERGANTE
| Cpl (QMS) PA | [5 empty] | LTC (QMS) PA | [12 empty] | Major General PA
| Plans Program, NCO | [5 empty] | AC of S for Logistics, G4 | [12 empty] | Commander
Formulas:
Sub/Open of Bids (Abstract of Canvass) = [Eligibility Check]
Sub/Open of Bids (Abstract of Canvass) = SUM([Eligibility Check])
Bid Evaluation = [Eligibility Check]
Bid Evaluation = [Sub/Open of Bids (Abstract of Canvass)]
Notice to Proceed = [Contract Signing]
Inspection & Acceptance = [Delivery/ Completion]
Inspection & Acceptance = SUM([Delivery/ Completion])
Notice of Award = [Eligibility Check]
Notice of Award = [Bid Evaluation]
Note on G7: ACER: Posting of Philgeps/ Invitation to submit quotation
Note on J7: ACER: RFQ/ Abstract of Canvass

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement