## 1BCT, PA PMR 2ND SEM CY 2022
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (1BCT) Procurement Monitoring Report as of 2nd Semester CY 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-02-13-040-01 | R&M Buildings Quarters | [18 empty] | Procurement of Requierments for CY 2022 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2022-07-22 | N/A | 2022-09-07 | 2022-09-14 | 2022-09-13 | GoP | 160000 | 160000 |  | 159608 | 159608 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-03 | R&M ICT Equipment | [18 empty] | Procurement of Requierments for CY 2022 | G6 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2022-07-22 | N/A | 2022-09-07 | 2022-09-14 | 2022-09-13 | GoP | 123500 | 123500 |  | 123280 | 123280 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-210-02 | R&M Semi Expendable Office equipment | [18 empty] | Procurement of Requierments for CY 2022 | G6 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2022-07-22 | N/A | 2022-09-07 | 2022-09-14 | 2022-09-13 | GoP | 41600 | 41600 |  | 41400 | 41400 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-070-00 | Drugs and Medicines | [18 empty] | Procurement of Requierments for CY 2022 | G1 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2022-07-22 | N/A | 2022-09-07 | 2022-09-14 | 2022-09-13 | GoP | 50000 | 50000 |  | 49800 | 49800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-00 | Office Supplies | [18 empty] | Procurement of Requierments for CY 2022 | G4 | NO | Shopping | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2022-05-16 | N/A | 2022-09-07 | 2022-09-14 | 2022-09-13 | GoP | 202500 | 202500 |  | 202055 | 202055 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-050-03 | R&M Machinery & Equipment | [18 empty] | Procurement of Requierments for CY 2022 | G6 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2022-07-22 | N/A | 2022-09-07 | 2022-09-14 | 2022-09-13 | GoP | 40000 | 40000 |  | 39800 | 39800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-070-00 | Drugs and Medicines | [18 empty] | Procurement of Requierments for CY 2022 | G1 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2022-10-27 | N/A | 2022-11-17 | 2022-11-29 | 2022-11-29 | GoP | 50000 | 50000 |  | 49800 | 49800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-080-00 | Medical and Dental Supplies | [18 empty] | Procurement of Requierments for CY 2022 | G1 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2022-10-27 | N/A | 2022-11-28 | 2022-12-06 | 2022-12-06 | GoP | 50000 | 50000 |  | 49800 | 49800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-03-010-00 | Office Supplies | [18 empty] | Procurement of Requierments for CY 2022 | G4 | NO | Shopping | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2022-11-02 | N/A | 2022-11-17 | 2022-11-29 | 2022-11-29 | GoP | 217500 | 217500 |  | 217008 | 217008 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5-02-13-040-01 | R&M Buildings Quarters | [18 empty] | Procurement of Requierments for CY 2022 | G4 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2022-11-02 | N/A | 2022-12-16 | 2022-12-28 | 2022-12-28 | GoP | 60000 | 60000 |  | 59480 | 59480 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 995100
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 992031
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 3069
0N-GOING PROCUREMENT ACTIVITIES
5-02-03-210-07 | R&M Semi Expendable Communication Equipment | [18 empty] | Procurement of Requierments for CY 2022 | G6 | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2022-10-27 | N/A | N/A | N/A | N/A | GoP | 152000 | 152000 |  | 151520 | 151520 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 152000
`
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | PHILIP R UMBLAS | [21 empty] | LEODEVIC B GUINID
[21 empty] | Captain (QMS) PA | [21 empty] | Colonel INF (GSC) PA
[21 empty] | AC of S for Logistics, G4 | [21 empty] | Commander