## PMR
(AIR) Procurement Monitoring Report as of July 31 to 31 December, 2022
Line item | Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | [5 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[6 empty] | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
1 | Semi-Expendable - Communication Equipment/5-02-03-210-07 | S/D of UHF Base Radio 0-8 KM Motorola GM-338 VHF Base Station and 1 others | HAIR | NO | NP-53.9 - Small Value Procurement | 2022-07-30 | 2022-07-30 | 2022-09-02 | 2022-09-21 | 2022-09-21 | GoP | 498000 | 498000 | 0 | 495750 | 495750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Semi-Expendable - Office Equipment/5-02-03-210-02 | S/D of 6 unit of Phocopying Machine All-in- One Printer with ADF and 3 others | HAIR | NO | NP-53.9 - Small Value Procurement | 2022-07-15 | 2022-07-15 | 2022-08-30 | 2022-09-05 | 2022-09-05 | GoP | 217350 | 217350 | 0 | 215900 | 215900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | Semi-Expendable - Information and Communications Technology Equipment/ 5-02-03-210-03 | S/D of 8 unit of Overhead Projector Native XGA (1024 x 768) (1,920x1,200) and 8 others | HAIR | NO | NP-53.9 - Small Value Procurement | 2022-07-15 | 2022-07-15 | 2022-09-09 | 2022-09-21 | 2022-09-21 | GoP | 525000 | 525000 | 0 | 523100 | 523100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
4 | Medical, Dental and Laboratory Supplies Expenses/ 5-02-03-080-00 | S/D of Proucurement of Rapid Test Device (Nasal) Covid-19 and 1 other | HAIR | NO | NP-53.9 - Small Value Procurement | 2022-09-01 | 2022-09-01 | 2022-11-17 | 2022-11-23 | 2022-11-23 | GoP | 500000 | 500000 | 0 | 443740 | 443740 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | 5-02-010-010-00/ Training Expenses | Catering | 1ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-04 | 2022-07-04 | 2022-07-14 | 2022-07-18 | 2022-07-18 | GoP | 40000 | 40000 | 0 | 39900 | 39900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | 5-02-99-030-00 (Representation Expenses) | Catering | 1ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-04 | 2022-07-04 | 2022-07-14 | 2022-07-18 | 2022-07-18 | GoP | 29750 | 29750 | 0 | 29676 | 29676 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 | 5-02-13-040-01- (Building and other Structure) Building | S/D 6pcs Paint Brush and 8 others | 1ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-06 | 2022-07-06 | 2022-07-28 | 2022-08-02 | 2022-08-02 | GoP | 60000 | 60000 | 0 | 59880 | 59880 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 | Semi-Expendable - Information and Communications Technology Equipment/ 5-02-03-210-03 | 2 set Smart-Phone 6.5" 32gb/3gb RAM and 1 other | 1ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-07 | 2022-07-07 | 2022-07-21 | 2022-07-27 | 2022-07-27 | GoP | 30000 | 30000 | 0 | 29920 | 29920 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | 5-02-03-08-0-00 - Medical and Dental Laboratory Supplies | Isopropyl Alcohol 70% 250ml and 6 others | 1ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-07 | 2022-07-07 | 2022-07-21 | 2022-07-27 | 2022-07-27 | GoP | 6000 | 6000 | 0 | 5984 | 5984 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 | 5-02-03-210-07/ Semi-Expendable - Communications Equipment | 6 set 1-4 watts two way UHF HandHeld Radio and 3 others | 1ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-20 | 2022-07-20 | 2022-08-01 | 2022-08-05 | 2022-08-05 | GoP | 49995 | 49995 | 0 | 49905 | 49905 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | 5-02-010-010-00/ Training Expenses- | Catering | 1ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-18 | 2022-10-18 | 2022-11-14 | 2022-11-18 | 2022-11-18 | GoP | 20000 | 20000 | 0 | 19950 | 19950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | 5-02-99-030-00 (Representation Expenses) | Catering | 1ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-18 | 2022-10-18 | 2022-11-14 | 2022-11-18 | 2022-11-18 | GoP | 19750 | 19750 | 0 | 19703 | 19703 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | 5-02-03-08-0-00 - Procurement of Medical and Dental Laboratory Supplies | Isopropyl Alcohol 70% 250ml and 6 others | 1ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-18 | 2022-10-18 | 2022-11-14 | 2022-11-18 | 2022-11-18 | GoP | 6000 | 6000 | 0 | 5980 | 5980 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 | 5-02-03-210-07/ Semi-Expendable - Communications Equipment | 2 set 1-4 watts two way UHF HandHeld Radio and 6 others | 1ISU | NO | NP-53.9 - Small Value Procurement | 2022-11-11 | 2022-11-11 | 2022-11-29 | 2022-12-07 | 2022-12-07 | GoP | 20000 | 20000 | 0 | 19970 | 19970 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | 5-02-03-210-03/ C4S Enhancement of 2ISU, AIR -SPF | Smart TV 42 inches and 2 others | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-22 | 2022-08-01 | 2022-08-08 | 2022-08-11 | 2022-08-11 | GoP | 100000 | 100000 | 0 | 99800 | 99800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
16 | 5-02-05-040-00 /Cable Satellite, Telegraph & Radio Expenses | 15 pcs cable card 500 | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-25 | 2022-08-04 | 2022-08-08 | 2022-08-11 | 2022-08-11 | GoP | 7500 | 7500 | 0 | 7492.5 | 7492.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | 5-02-05-040-00 /Cable Satellite, Telegraph & Radio Expenses | 15 pcs cable card 500 | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-26 | 2022-11-04 | 2022-11-07 | 2022-11-10 | 2022-11-10 | GoP | 7500 | 7500 | 0 | 7492.5 | 7492.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
18 | Semi-Expendable - ICT Equipment 5-02-03-210-03 | Voice Recorder of 1 pc and Microphone of 3 pcs | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-18 | 2022-07-18 | 2022-08-09 | 2022-07-19 | 2022-07-19 | GoP | 15000 | 15000 | 0 | 14850 | 14850 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | Semi-Expendable - ICT Equipment 5-02-03-210-03 | Wireless Microphone UHF of 3 pcs, Digital Video Camera (e0s 4000d) DSLR of 2 unit and Laptop Intel Core i5 1135G7 8GB RAM 1TB HDD + 256GB SSD Storage MX330 2GB Graphics 15.6" IPS Windows 10 Home OS of 1 unit | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-27 | 2022-07-27 | 2022-08-18 | 2022-08-22 | 2022-08-22 | GoP | 100000 | 100000 | 0 | 99550 | 99550 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
20 | 5-02-99-03-0-00 Representation Expense | Coffee Stick of 6 pcks, Coffee Creamer 5 pck and 6 others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-08-03 | 2022-08-03 | 2022-08-22 | 2022-08-24 | 2022-08-24 | GoP | 18500 | 18500 | 0 | 18305 | 18305 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | 5-02-03-08-0-00 - Procurement of Medical and Dental Laboratory Supplies | Srerile eye pads 10's of 2 pck, Mediplast (standard plastic strip) 100's of 1 pck and 10 others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-08-09 | 2022-08-09 | 2022-08-31 | 2022-09-02 | 2022-09-02 | GoP | 11500 | 11500 | 0 | 11381 | 11381 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
22 | 5-02-99-03-0-00 Representation Expense | Coffee Stick of 15 pcks, Coffee Creamer 5 pck and 6 others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-13 | 2022-09-13 | 2022-09-27 | 2022-09-29 | 2022-09-29 | GoP | 27000 | 27000 | 0 | 26815 | 26815 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
23 | 5-02-03-08-0-00 - Procurement of Medical and Dental Laboratory Supplies | Alcohol 70% Isopropyl 500ml of 18 btl, FaceMask of 7 box and Gloves 1 box | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-13 | 2022-09-13 | 2022-09-27 | 2022-09-29 | 2022-09-29 | GoP | 3500 | 3500 | 0 | 3400 | 3400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
24 | 5-02-13-05-0-02/ R&M of Office Equipment | Refilling of Freon of 1 unit | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-13 | 2022-09-13 | 2022-09-27 | 2022-09-29 | 2022-09-29 | GoP | 2000 | 2000 | 0 | 1900 | 1900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
25 | 5-02-03-99-0-00 - Other Supplies and Materials Expense | Garbage Bag of 2 pck, Stick Broom of 4 pcs and 2 others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-13 | 2022-09-13 | 2022-09-27 | 2022-09-29 | 2022-09-29 | GoP | 2000 | 2000 | 0 | 1910 | 1910 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | 5-02-99-03-0-00 Representation Expense | Rice of 2 sacks, Fruit cocktail of 3 can and 11 others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-27 | 2022-09-27 | 2022-10-13 | 2022-10-17 | 2022-10-17 | GoP | 10000 | 10000 | 0 | 9880 | 9880 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | 5-02-03-08-0-00 - Procurement of Medical and Dental Laboratory Supplies | Rapid Antigen Test Kit 25's of 1 box, PPE Medical Grade Cover All Suit of 6 pcs and 3 others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-03 | 2022-10-03 | 2022-10-25 | 2022-10-27 | 2022-10-27 | GoP | 30000 | 30000 | 0 | 29650 | 29650 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
28 | 5-02-05-02-0-01 - Mobile Expense | Cell Card Prepaid (Globe) of 13 pcs, Cell Card Prepaid (Smart) of 5 pcs and 3 Others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-03 | 2022-10-03 | 2022-10-25 | 2022-10-27 | 2022-10-27 | GoP | 15000 | 15000 | 0 | 14890 | 14890 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
29 | 5-02-03-01-0-00 - Office Supplies Expense | Paper, Multi Copy 80gsm,A4 of 5 rem, White Board marker (Black) of 3 pcs and 3 others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-03 | 2022-10-03 | 2022-10-25 | 2022-10-27 | 2022-10-27 | GoP | 3000 | 3000 | 0 | 2820 | 2820 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
30 | 5-02-02-01-0-00 - Training Expense | Paper, Multi Copy 80gsm,A4 0f 35 rem, Ink (Epson) (Assorted) of 20 pcs and 8 others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-11 | 2022-10-11 | 2022-10-18 | 2022-10-20 | 2022-10-20 | GoP | 30000 | 30000 | 0 | 29690 | 29690 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
31 | 5-02-99-03-0-00 Representation Expense | Coffee Stick of 7 pcks, Coffee Creamer 6 pck and 6 others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-11 | 2022-10-11 | 2022-10-19 | 2022-10-21 | 2022-10-21 | GoP | 21000 | 21000 | 0 | 20870 | 20870 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | 5-02-99-03-0-00 Representation Expense | Rice of 2 sacks, Fruit cocktail of 3 can and 11 others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-27 | 2022-10-27 | 2022-11-24 | 2022-11-28 | 2022-11-28 | GoP | 10000 | 10000 | 0 | 9850 | 9850 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
33 | 5-02-05-02-0-01 - Mobile Expense | Cell Card Prepaid (Globe) of 13 pcs, Cell Card Prepaid (Smart) of 5 pcs and 3 Others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-11-28 | 2022-11-28 | 2022-12-12 | 2022-12-14 | 2022-12-14 | GoP | 15000 | 15000 | 0 | 14885 | 14885 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
34 | 5-02-99-03-0-00 Representation Expense | Coffee Stick of 7 pcks, Coffee Creamer 6 pck and 6 others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-11-28 | 2022-11-28 | 2022-12-12 | 2022-12-14 | 2022-12-14 | GoP | 21000 | 21000 | 0 | 20880 | 20880 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
35 | 5-02-03-08-0-00 - Procurement of Medical and Dental Laboratory Supplies | Rapid Antigen Test Kit 25's of 1 box, PPE Medical Grade Cover All Suit of 6 pcs and 3 others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-11-28 | 2022-11-28 | 2022-12-12 | 2022-12-14 | 2022-12-14 | GoP | 30000 | 30000 | 0 | 29847 | 29847 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
36 | 5-02-99-03-0-00 Representation Expense | Rice of 8 sacks, Canned Goods of 7 box and 11 others | 10ISU | NO | NP-53.9 - Small Value Procurement | 2022-12-13 | 2022-12-13 | 2022-12-22 | 2022-12-26 | 2022-12-26 | GoP | 50000 | 50000 | 0 | 49884 | 49884 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
37 | 5-02-13-050-03 /Procurement of ICT Equipment (Semi-Expendeble) | S/D AV15-51-57WC i5-1155G7 8GB 512GB SSD 15.6 Shares Win11 w/ H&S Two (2) others | 11ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-19 | 2022-07-20 | 2022-08-03 | 2022-08-25 | 2022-08-25 | GoP | 100000 | 100000 | 0 | 99776 | 99776 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
38 | 5-02-13-050-03 /Procurement of ICT Equipment (Semi-Expendeble) | S/D Windows-10 Pro Operating System | 11ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-28 | 2022-07-29 | 2022-08-03 | 2022-08-20 | 2022-08-20 | GoP | 15000 | 15000 | 0 | 8499 | 8499 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
39 | 5-02-13-040-01/ R&M (Buildings & Other Structures) Buildings | S/D Latex paint white and four (4) others | 11ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-28 | 2022-07-29 | 2022-08-10 | 2022-08-30 | 2022-08-30 | GoP | 10000 | 10000 | 0 | 9905 | 9905 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
40 | 5-02-13-050-03 /Procurement of ICT Equipment (Semi-Expendeble) | S/D Windows-10 Pro Operating System | 11ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-23 | 2022-09-24 | 2022-10-06 | 2022-10-21 | 2022-10-21 | GoP | 15000 | 15000 | 0 | 10555 | 10555 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
41 | 5-02-03-080-00 / Procurement of Drugs and Medicines | S/D Medical Face Mask KF94 and Four (4) others | 11ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-21 | 2022-10-24 | 2022-10-06 | 2022-11-09 | 2022-11-09 | GoP | 30000 | 30000 | 0 | 29900 | 29900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | 5-02-13-040-01/ R&M (Buildings & Other Structures) Buildings | S/D of ten (10) pcs Poly toff and ten (10) others | 12ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-05 | 2022-09-05 | 2022-09-19 | 2022-09-20 | 2022-09-22 | GoP | 50000 | 50000 | 0 | 49500 | 49500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
43 | 5-02-03-210-03 /Procurement of ICT Equipment (Semi-Expendeble) | S/D of two (2) pcs Satelite Phone | 12ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-05 | 2022-09-05 | 2022-09-11 | 2022-09-12 | 2022-09-18 | GoP | 25000 | 25000 | 0 | 24800 | 24800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
44 | 5-02-03-210-03 /Procurement of ICT Equipment (Semi-Expendeble) | S/D of two (2) pcs Satelite Phone | 12ISU | NO | NP-53.9 - Small Value Procurement | 2022-08-30 | 2022-08-30 | 2022-09-14 | 2022-09-20 | 2022-09-22 | GoP | 5000 | 5000 | 0 | 4900 | 4900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
45 | 5-02-03-210-03 /Procurement of ICT Equipment (Semi-Expendeble) | S/D of two (2) pcs Satelite Phone | 12ISU | NO | NP-53.9 - Small Value Procurement | 2022-08-30 | 2022-08-30 | 2022-09-27 | 2022-09-28 | 2022-09-30 | GoP | 25000 | 25000 | 0 | 24800 | 24800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
46 | 5-02-13-210-02 /R&M of Office Equipment (Semi-Expendable) | S/D of two (2) pcs Aircon Compressor | 12ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-27 | 2022-09-27 | 2022-10-20 | 2022-10-28 | 2022-11-02 | GoP | 10500 | 10500 | 0 | 10400 | 10400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
47 | 5-02-13-210-02 /R&M of Office Equipment (Semi-Expendable) | S/D of two (2) pcs Aircon Compressor | 12ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-27 | 2022-09-27 | 2022-10-20 | 2022-10-28 | 2022-11-02 | GoP | 10500 | 10500 | 0 | 10300 | 10300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
48 | 5-02-13-060-01 /R&M (Transpo Equipment) Motor Vehicles | S/D of two (2) pcs Tire (Toyota Hilux 265/65 R17) and one (1) other | 12ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-29 | 2022-09-29 | 2022-10-20 | 2022-10-28 | 2022-11-02 | GoP | 26000 | 26000 | 0 | 25700 | 25700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
49 | 5-02-13-060-01 /R&M (Transpo Equipment) Motor Vehicles | S/D of three (3) set of Horn and Twelve (12) others | 12ISU | NO | NP-53.9 - Small Value Procurement | 2022-11-21 | 2022-11-21 | 2022-12-05 | 2022-12-07 | 2022-12-08 | GoP | 30000 | 30000 | 0 | 29850 | 29850 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
50 | Semi-Expendable - ICT Equipment/5-02-03-210-00 | S/D of 41 pcs Motorola CP 1660 Handheld Radio Ear Piece with ln-Line Microphone PTT/VOX Flexible Whip Antenna Battery Li'ion 1500 mAh min 1700 mAh type Battery Clip with Rapid Charger & 1 other | 15AIBN | NO | NP-53.9 - Small Value Procurement | 2022-09-12 | 2022-09-12 | 2022-11-29 | 2022-12-09 | 2022-12-09 | GoP | 926420 | 926420 | 0 | 919950 | 919950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of On-going Procurement Activities | [11 empty] | 3829765 | 3829765 |  | 3744235 | 3744235
Line item | Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | [5 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[6 empty] | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
1 | 5-02-13-040-01/ R&M (Buildings & Other Structures) Buildings | S/D of 839 CHB 4x8x6 and 19 others | HAIR | NO | NP-53.9 - Small Value Procurement | 2022-09-01 | 2022-09-01 | 2022-12-15 | 2022-12-19 | N/A | GoP | 285800 | 285800 | 0 | 284711 | 284711 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | 5-02-03-210-07/ Semi-Expendable - Communications Equipment | Motorola CP1660 Radio and 5 others | HAIR | NO | NP-53.9 - Small Value Procurement | 2022-08-25 | 2022-08-25 | 2022-12-15 | 2022-12-19 | N/A | GoP | 600000 | 600000 |  | 595400 | 595400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | Semi-Expendable - Communication Equipment/5-02-03-210-07 | S/D of 6 Set Desktop Computer C24-1650 AIO 23.8 FHD LED(1920X1080)Display Intel Core I5 11355G7 8GB SODIMN DDR4 256 SSD 1 TB HDD & 15 Others | HAIR | NO | NP-53.9 - Small Value Procurement | 2022-09-21 | 2022-09-21 | N/A | N/A | N/A | GoP | 899500 | 899500 | 0 | 893560 | 893560 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
4 | Semi-Expendable - Office Equipment/5-02-03-210-02 | S/D of 1 Unit Aircon 2.5 HP Split Type and 5 others | HAIR | NO | NP-53.9 - Small Value Procurement | 2022-11-10 | 2022-11-10 | 2022-12-23 | N/A | N/A | GoP | 108000 | 108000 | 0 | 106800 | 106800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | Semi-Expendable - Information and Communications Technology Equipment/ 5-02-03-210-03 | S/D Laptop AMD Ryzen 75800H, 16GB of RAM 512 OF Storage & AMD Radeon Graphics and 7 others | HAIR | NO | NP-53.9 - Small Value Procurement | 2022-11-10 | 2022-11-10 | N/A | N/A | N/A | GoP | 371910 | 371910 | 0 | 369800 | 369800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | Semi-Expendable - Information and Communications Technology Equipment/ 5-02-03-210-03 | S/D 1 pc of 8-Input Professional Mixer with USB and 7 others | HAIR | NO | NP-53.9 - Small Value Procurement | 2022-11-25 | 2022-11-26 | N/A | N/A | N/A | GoP | 200000 | 200000 | 0 | 199500 | 199500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 | 5-02-13-040-01- (Building and other Structure) Building | S/D 5 pcs of Ceramic Tiles Floor Tiles (0.60 x 0.60m) and 61 others | HAIR | NO | NP-53.9 - Small Value Procurement | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 286700 | 286700 | 0 | 283900 | 283900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 | 5-02-13-040-01- (Building and other Structure) Building | S/D of Paint Brush #2 and 16 Others | HAIR | NO | NP-53.9 - Small Value Procurement | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 150000 | 150000 | 0 | 148400 | 148400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | Semi-Expendable - ICT Equipment/5-02-03-210-00 | S/D of 10 pcs XiR M3688 UHF Base Radio with auto wire and connectors and 4 others | HAIR | NO | NP-53.9 - Small Value Procurement | 2022-11-24 | 2022-11-24 | N/A | N/A | N/A | GoP | 600000 | 600000 | 0 | 597800 | 597800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 | (5-02)-13-060-01 Additional Admin and Operational Support for 2ISU -SPF | 4 PCS Yokohama Geolandar 265/65R17, 4 pcs yokohama 205/65R16 and 4 pcs yokohama 205/65R15 | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-12 | 2022-07-29 | 2022-08-02 | 2022-08-04 | N/A | GoP | 105000 | 105000 | 0 | 104500 | 104500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | 5-02-13-050-03/ R&M of ICT Equipment | 2 pcs RAM Kingston 8GB PC and 2 pcs 32GB memory card | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-25 | 2022-08-04 | 2022-08-08 | 2022-08-11 | N/A | GoP | 10000 | 10000 | 0 | 10000 | 10000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | 5-02-13-050-07/ R&M of Radio | 6 pcs of hand held radio baterry and 1 antenna | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-25 | 2022-08-04 | 2022-08-08 | 2022-08-11 | N/A | GoP | 10000 | 10000 | 0 | 9950 | 9950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | 5-02-010-010-00/ Training Expenses-( Tradecraft Refresher training and GAD Seminar) - Office Supplies | 2 ream A4 bond paper and 7 line items | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-25 | 2022-07-29 | 2022-08-02 | 2022-08-04 | N/A | GoP | 8000 | 8000 | 0 | 7955 | 7955 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 | 5-02-13-040-01/ R&M of 2ISU Admin Building | 125 pcs tiles and 6 line items | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-25 | 2022-08-15 | 2022-08-16 | 2022-08-18 | N/A | GoP | 30000 | 30000 | 0 | 29170 | 29170 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | 5-0-13-060-01 /R&M (M Repair & Maintanace of Vehicles Repair & Maintanace of Vehicles) -SPF | Air Cleaner Assembly and 39 others | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-29 | 2022-08-03 | 2022-08-17 | 2022-08-19 | N/A | GoP | 122270 | 122270 | 0 | 121770 | 121770 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
16 | 5-02-010-010-00/ Training Expenses-( Tradecraft Refresher training and GAD Seminar) - Catering | Catering | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-08-05 | 2022-08-17 | N/A | 2022-08-27 | N/A | GoP | 27000 | 27000 | 0 | 26955 | 26955 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | 5-02-13-050-03/ R&M of ICT Equipment | 2 pcs RAM Kingston 8GB PC1333 and 2 pcs 32GB memory card | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-26 | 2022-11-04 | 2022-11-10 | 2022-11-15 | N/A | GoP | 10000 | 10000 | 0 | 10000 | 10000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
18 | 5-02-010-010-00/ Training Expenses-(Cyber Security and GIS training) - Office Supplies | 3 ream A4 bond paper and 6 line items | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-26 | 2022-11-04 | 2022-11-07 | 2022-11-10 | N/A | GoP | 3400 | 3400 | 0 | 3370 | 3370 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | 5-02-010-010-00/ Training Expenses-( Cyber Security and GIS training) - Catering | Catering | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-25 | 2022-11-07 | 2022-11-08 | 2022-11-15 | N/A | GoP | 6600 | 6600 | 0 | 6600 | 6600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
20 | 5-02-99-030-00/ Additional MOWEL Support -SPF (Rep-Ex) | Catering | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-27 | 2022-11-09 | N/A | 2022-11-17 | N/A | GoP | 10000 | 10000 | 0 | 10000 | 10000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | 5-02-99-030-00/ Rep-Ex- Unit Anniversarry Celebration | Catering | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-27 | 2022-11-09 | N/A | 2022-11-17 | N/A | GoP | 25000 | 25000 | 0 | 24950 | 24950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
22 | 5-02-13-040-01 /R&M Buildings | Tiles 60 X 60 100 pcs and 19 Others | 7ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-01 | 2022-09-01 | 2022-09-17 | N/A | N/A | GoP | 60000 | 60000 | 0 | 59885 | 59885 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
23 | 5-02-13-040-01 /R&M Buildings | Tiles 40 X 40 100 pcs and 17 Others | 7ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-18 | 2022-10-18 | 2022-11-30 | N/A | N/A | GoP | 50000 | 50000 | 0 | 49420 | 49420 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
24 | 5-02-03-990-00 (Other Supplies and materials Expenses) | S/D 10 bags of Choco Biscut and 6 others | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-04 | 2022-07-04 | 2022-08-05 | N/A | N/A | GoP | 4200 | 4200 | 0 | 4199 | 4199 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
25 | 5-02-02-010-00 (Training Expenses) | S/D 67 ctns Bottled Water and 6 others | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-04 | 2022-07-04 | 2022-08-05 | N/A | N/A | GoP | 60000 | 60000 | 0 | 59941 | 59941 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | 5-02-02-010-00 (Training Expenses) | S/D 2 pcs Plaque | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-04 | 2022-07-04 | 2022-08-23 | N/A | N/A | GoP | 10000 | 10000 | 0 | 10000 | 10000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | 5-02-03-070-00 (Drugs and Medicines Expenses) | 1 box of Diclofenac Systemic and 3 others | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-04 | 2022-07-04 | 2022-08-01 | N/A | N/A | GoP | 3000 | 3000 | 0 | 3000 | 3000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
28 | 5-02-13-050-03 (ICT Expenses) | S/D 1 pc Power Supply and 1 other | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-25 | 2022-07-25 | 2022-09-20 | N/A | N/A | GoP | 3500 | 3500 | 0 | 3500 | 3500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
29 | 5-02-13-060-01 (R&M - Motor Vehicles) | S/D 1 pc Battery and 7 others | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-25 | 2022-07-25 | 2022-09-12 | N/A | N/A | GoP | 13000 | 13000 | 0 | 13000 | 13000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
30 | 5-02-05-030-00 (Internet Subscription Expenses) | S/D 9 Internet Load (Prepaid Card) | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-04 | 2022-07-04 | 2022-08-05 | N/A | N/A | GoP | 9000 | 9000 | 0 | 9000 | 9000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
31 | 5-02-05-040-00 (Cable, Satellite, Telegraph and Radio Expenses) | S/D 3 Cable Load (Prepaid Card) | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-04 | 2022-07-04 | 2022-08-05 | N/A | N/A | GoP | 3000 | 3000 | 0 | 3000 | 3000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | 5-02-03-210-03 (Semi-Expandable M&E - ICT Equipment) | S/D 2 pcs Laptop and 2 others | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-15 | 2022-07-15 | 2022-07-27 | N/A | N/A | GoP | 100000 | 100000 | 0 | 99850 | 99850 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
33 | 5-02-99-030-00 (Representation Expenses) | S/D 50 pax meals and 1 other | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-19 | 2022-09-19 | 2022-10-27 | N/A | N/A | GoP | 20000 | 20000 | 0 | 20000 | 20000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
34 | 5-02-03-080-00 (Medical, Dental and Laboratory Supplies Expenses) | S/D 8 box Alcohol 60ml and 11 others | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-19 | 2022-09-19 | 2022-10-18 | N/A | N/A | GoP | 40000 | 40000 | 0 | 39994 | 39994 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
35 | 5-02-05-020-01 (Mobile Expenses) | S/D 30 pcs Cell Card Globe | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-19 | 2022-09-19 | 2022-10-18 | N/A | N/A | GoP | 15000 | 15000 | 0 | 15000 | 15000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
36 | 5-02-03-990-00 (Other Supplies and materials Expenses) | S/D 10 bags of Choco Biscut and 6 others | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-14 | 2022-10-14 | 2022-11-15 | N/A | N/A | GoP | 3600 | 3600 | 0 | 3599 | 3599 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
37 | 5-02-02-010-00 (Training Expenses) | S/D 84 bags of Choco Biscut and 6 others | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-14 | 2022-10-14 | 2022-11-22 | N/A | N/A | GoP | 32500 | 37500 | 0 | 32388 | 32388 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
38 | 5-02-02-010-00 (Training Expenses) | S/D 1 pc plaque | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-14 | 2022-10-14 | 2022-11-22 | N/A | N/A | GoP | 5000 | 5000 | 0 | 5000 | 5000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
39 | 5-02-13-060-01 (R&M - Motor Vehicles) | S/D 1 pc Battery and 7 others | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-11-14 | 2022-11-14 | 2022-11-21 | N/A | N/A | GoP | 13000 | 13000 | 0 | 13000 | 13000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
40 | 5-02-99-030-00 (Representation Expenses) | S/D 14 pcs Keso de bola 500g and 6 others | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-14 | 2022-10-14 | 2022-11-02 | N/A | N/A | GoP | 25000 | 25000 | 0 | 24974 | 24974 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
41 | 5-02-03-070-00 (Drugs and Medicines Expenses) | 1 box of Diclofenac Systemic and 3 others | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-14 | 2022-10-14 | 2022-11-15 | N/A | N/A | GoP | 3000 | 3000 | 0 | 3000 | 3000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | 5-02-05-030-00 (Internet Subscription Expenses) | S/D 9 Internet Load (Prepaid Card) | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-14 | 2022-10-14 | 2022-12-15 | N/A | N/A | GoP | 9000 | 9000 | 0 | 9000 | 9000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
43 | 5-02-05-040-00 (Cable, Satellite, Telegraph and Radio Expenses) | S/D 3 Cable Load (Prepaid Card) | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-10-14 | 2022-10-14 | 2022-12-15 | N/A | N/A | GoP | 3000 | 3000 | 0 | 3000 | 3000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
44 | 5-02-99-030-00 (Representation Expenses) | S/D 50 pax meals and 1 other | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-11-04 | 2022-11-04 | 2022-12-13 | N/A | N/A | GoP | 20000 | 20000 | 0 | 20000 | 20000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
45 | 5-02-03-080-00 (Medical, Dental and Laboratory Supplies Expenses) | S/D 8 gal Alcohol 60ml and 3 others | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-11-04 | 2022-11-04 | 2022-12-02 | N/A | N/A | GoP | 30000 | 30000 | 0 | 30000 | 30000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
46 | 5-02-05-020-01 (Mobile Expenses) | S/D 30 pcs Cell Card Globe | 8ISU | NO | NP-53.9 - Small Value Procurement | 2022-11-04 | 2022-11-04 | 2022-12-02 | N/A | N/A | GoP | 15000 | 15000 | 0 | 15000 | 15000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
47 | 5-02-02-010-00 (Training Expenses) | S/D 20 packs of 3 in 1 Coffee and 8 others | 9ISU | NO | NP-53.9 - Small Value Procurement | 2022-07-29 | 2022-07-29 | 2022-08-08 | N/A | N/A | GoP | 25000 | 25000 | 0 | 25000 | 25000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
48 | 5-02-03-210-03 (Semi-Expendable -ICT Equipment) | S/D 2 pcs of Cellphone and 4 others | 9ISU | NO | NP-53.9 - Small Value Procurement | 2022-08-16 | 2022-08-16 | 2022-08-26 | N/A | N/A | GoP | 100000 | 100000 | 0 | 100000 | 100000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
49 | 5-02-13-050-03 (ICT Expenses) | S/D 2 pcs of Hard disk 1TB intel solid | 9ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-16 | 2022-09-16 | 2022-09-30 | N/A | N/A | GoP | 10000 | 10000 | 0 | 10000 | 10000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
50 | 5-02-03-990-00 (Other Supplies and materials Expenses) | S/D 20 packs of Cup Cake and 10 others | 9ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-16 | 2022-09-16 | 2022-09-26 | N/A | N/A | GoP | 42000 | 42000 | 0 | 42000 | 42000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
51 | 5-02-99-030-00 (Representation Expenses) | S/D 15 cases of Mineral water 500 ml and 12 others | 9ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-16 | 2022-09-16 | 2022-09-26 | N/A | N/A | GoP | 49000 | 49000 | 0 | 49000 | 49000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
52 | 5-02-03-990-00 (Other Supplies and materials Expenses) | S/D 21 packs of Cup Cake and 9 others | 9ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-30 | 2022-09-30 | 2022-10-13 | N/A | N/A | GoP | 40000 | 40000 | 0 | 40000 | 40000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
53 | 5-02-03-080-00 (Medical, Dental and Laboratory Supplies Expenses) | S/D 15 pcs of PPE Suits and 2 others | 9ISU | NO | NP-53.9 - Small Value Procurement | 2022-09-30 | 2022-09-30 | 2022-10-19 | N/A | N/A | GoP | 30000 | 30000 | 0 | 30000 | 30000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
54 | 5-02-02-010-00 (Training Expenses) | S/D 20 packs of 3 in 1 Coffee and 8 others | 9ISU | NO | NP-53.9 - Small Value Procurement | 2022-11-11 | 2022-11-11 | 2022-11-19 | N/A | N/A | GoP | 25000 | 25000 | 0 | 25000 | 25000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
55 | 5-02-03-990-00 (Other Supplies and materials Expenses) | S/D 21 packs of Cup Cake and 9 others | 9ISU | NO | NP-53.9 - Small Value Procurement | 2022-12-02 | 2022-12-02 | 2022-12-12 | N/A | N/A | GoP | 40000 | 40000 | 0 | 40000 | 40000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
56 | 5-02-03-080-00 (Medical, Dental and Laboratory Supplies Expenses) | S/D 15 Gal of Alcohol and 3 others | 9ISU | NO | NP-53.9 - Small Value Procurement | 2022-12-02 | 2022-12-02 | 2022-12-12 | N/A | N/A | GoP | 30000 | 30000 | 0 | 30000 | 30000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
57 | 5-02-99-030-00 (Representation Expenses) | S/D 10 packs of Assorted Cup Cake and 5 others | 9ISU | NO | NP-53.9 - Small Value Procurement | 2022-12-02 | 2022-12-02 | 2022-12-13 | N/A | N/A | GoP | 10000 | 10000 | 0 | 10000 | 10000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
58 | 5-02-99-030-00 (Representation Expenses) | S/D 15 cases of Mineral water 500 ml and 12 others | 9ISU | NO | NP-53.9 - Small Value Procurement | 2022-12-13 | 2022-12-13 | 2022-12-20 | N/A | N/A | GoP | 50000 | 50000 | 0 | 50000 | 50000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
59 | 5-02-13-050-07/ R&M of Radio | 6 pcs of hand held radio baterry and 1 antenna | 2ISU | NO | NP-53.9 - Small Value Procurement | 2022-11-03 | 2022-11-11 | 2022-11-15 | 2022-11-17 | N/A | GoP | 10000 | 10000 | 0 | 9950 | 9950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
60 | 5-02-13-040-01- (Building and other Structure) Building | S/D of Paint Brush #2 and 16 others | K9Bn | NO | NP-53.9 - Small Value Procurement | 2022-11-02 | 2022-11-28 | N/A | N/A | N/A | GoP | 150000 | 150000 | 0 | 148400 | 148400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of On-going Procurement Activities | [11 empty] | 5029980 | 5034980 | 0 | 5003191 | 5003191
| Prepared by: | [11 empty] | Certified Correct By
| Ryan N Aggabao | [11 empty] | JIMMY C ALMORATO
| TSg (MI) PA | [11 empty] | Major (INF) PA
| Procurement NCO | [11 empty] | AC of S for Logistics, G4
Formulas:
Notice of Award = [1]pmr!AG9
Contract Signing = [1]pmr!AH9
Contract Signing = [Notice of Award]
Notice to Proceed = [1]pmr!AI9
Delivery/ Completion = [1]pmr!AJ9
Inspection & Acceptance = [1]pmr!AK9

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement