## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (ASPA) Procurement Monitoring Report as of December 31, 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| SD of 100 box face mask and 3 others | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-18 | 2022-12-28 | N/A | N/A | GoP | 91000 | 91000 | 0 | 90000 | 90000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 2 ea Gigabit switch 24 port and 1 other | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-18 | 2022-12-13 | N/A | N/A | GoP | 53777.43 | 53777.43 | 0 | 53477.43 | 53477.43 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 10 Windows 10 Operationg System and 1 other | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-18 | 2022-12-07 | N/A | N/A | GoP | 87500 | 87500 | 0 | 87100 | 87100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 1 ea Dining Table and 1 other | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-19 | N/A | N/A | GoP | 64500 | 64500 | 0 | 63400 | 63400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 4 ea Scanner and 2 others | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-14 | N/A | N/A | GoP | 391500 | 391500 | 0 | 390700 | 390700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CATERING SERVICES | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-14 | N/A | N/A | GoP | 73260 | 73260 | 0 | 73200 | 73200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 25 pack Palabok Pasta and 38 others | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-28 | N/A | N/A | GoP | 368282.99 | 368282.99 | 0 | 366482.1 | 366482.1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 2 ea Water Dispenser and 2 others | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-22 | N/A | N/A | GoP | 122495 | 122495 | 0 | 120995 | 120995 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 5 Drums Kyocera Taskalfa 4200 i | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-22 | N/A | N/A | GoP | 408069.9 | 408069.9 | 0 | 407368.5 | 407368.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 900 reams A4 Bond Paper and 34 others | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-28 | N/A | N/A | GoP | 700493.7 | 700493.7 | 0 | 698693.7 | 698693.7 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 8 ea Doors and 1 other | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-28 | N/A | N/A | GoP | 50840 | 50840 | 0 | 50400 | 50400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 100 each Notebook & 29 others | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2022-12-13 | N/A | N/A | N/A | GoP | 207568.94 | 207568.94 | 0 | 205652.94 | 205652.94 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[38 empty] | 2619287.96 | 2619287.96
| S/D of 2 boxes CLIP, BACKFOLD, 32MM & 58 others | [19 empty] | 15FAU, ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-02 | 2022-08-02 | 2022-08-30 | 2022-09-06 | 2022-09-06 | GoP | 57694 | 57694 | 0 | 56783.2 | 56783.2 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 boxes CLIP, BACKFOLD, 32MM & 58 others | [19 empty] | 15FAU, ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-13 | 2022-09-13 | 2022-10-04 | 2022-10-11 | 2022-10-11 | GoP | 57694 | 57694 | 0 | 57022.6 | 57022.6 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 1 unit Photocopying Machine | [19 empty] | 2FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-08 | 2022-07-08 | 2022-07-21 | 2022-07-26 | 2022-07-26 | GoP | 25000 | 25000 | 0 | 24800 | 24800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 1 can Insecticide and 24 others | [19 empty] | 2FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-21 | 2022-07-21 | 2022-07-28 | 2022-08-02 | 2022-08-02 | GoP | 12625 | 12625 | 0 | 12180 | 12180 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 30 Sign Pen Blue 18 others | [19 empty] | 2FAU | NO | NP-52.1b | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-18 | 2022-07-18 | 2022-07-28 | 2022-08-02 | 2022-08-02 | GoP | 57815 | 57815 | 0 | 57815 | 57815 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 6 pcs cellcard-Smart and 2 other | [19 empty] | 2FAU | NO | NP-52.1b | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-18 | 2022-07-18 | 2022-07-28 | 2022-08-02 | 2022-08-02 | GoP | 9000 | 9000 | 0 | 9000 | 9000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 1 unit CPU Core i5 | [19 empty] | 2FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-18 | 2022-07-18 | 2022-07-28 | 2022-08-02 | 2022-08-02 | GoP | 40000 | 40000 | 0 | 39650 | 39650 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 10 cavs Rice | [19 empty] | 2FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-15 | 2022-07-15 | 2022-07-28 | 2022-08-02 | 2022-08-02 | GoP | 10000 | 10000 | 0 | 9990 | 9990 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 1 can Insecticide and 24 others | [19 empty] | 2FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-20 | 2022-10-20 | 2022-10-27 | 2022-11-02 | 2022-11-02 | GoP | 12625 | 12625 | 0 | 12535 | 12535 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 30 can Pineapple Juice and 2 others | [19 empty] | 2FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-17 | 2022-10-17 | 2022-10-21 | 2022-10-24 | 2022-10-24 | GoP | 4000 | 4000 | 0 | 3750 | 3750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 1 unit CPU | [19 empty] | 2FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-17 | 2022-10-17 | 2022-10-21 | 2022-10-25 | 2022-10-25 | GoP | 40000 | 40000 | 0 | 39800 | 39800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 30 Sign Pen Blue 18 others | [19 empty] | 2FAU | NO | NP-52.1b | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-17 | 2022-10-17 | 2022-11-04 | 2022-11-08 | 2022-11-08 | GoP | 57815 | 57815 | 0 | 57650 | 57650 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 6 pcs cellcard-Smart and 2 other | [19 empty] | 2FAU | NO | NP-52.1b | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-17 | 2022-10-17 | 2022-11-10 | 2022-11-15 | 2022-11-15 | GoP | 9000 | 9000 | 0 | 8985 | 8985 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[38 empty] | 393268 | 393268
| S/D of 1 ea Server | [19 empty] | 17FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-10 | 2022-02-11 | 2022-02-18 | 2022-02-24 | 2022-02-24 | GoP | 14998 | 14998 | 0 | 14940 | 14940 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 10 cases Softdrinks & 10 others | [19 empty] | 17FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-10 | 2022-02-11 | 2022-02-18 | 2022-02-24 | 2022-02-24 | GoP | 25210 | 25210 | 0 | 25130 | 25130 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 40 rms Bond Paper A4 Multicopy 80 gsm and 22 others | [19 empty] | 17FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-10 | 2022-02-11 | 2022-02-18 | 2022-02-24 | 2022-02-24 | GoP | 25222.11 | 25222.11 | 0 | 25120.11 | 25120.11 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 30 pcs Spaghetti Pasta (1kg) and 6 others | [19 empty] | 17FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-10 | 2022-02-11 | 2022-02-18 | 2022-02-24 | 2022-02-24 | GoP | 15580 | 15580 | 0 | 15530 | 15530 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 ea Shredder Machine and 4 others | [19 empty] | 17FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-15 | 2022-02-16 | 2022-02-18 | 2022-02-24 | 2022-02-24 | GoP | 151402 | 151402 | 0 | 151124 | 151124 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 250 pcs Hollow Blocks & 13 others | [19 empty] | 17FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-10 | 2022-05-11 | 2022-05-13 | 2022-05-18 | 2022-05-18 | GoP | 86087.71 | 86087.71 | 0 | 85887.71 | 85887.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 15 box Mineral Water 230ml and 24 others | [19 empty] | 17FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-10 | 2022-05-11 | 2022-05-13 | 2022-05-18 | 2022-05-18 | GoP | 65656 | 65656 | 0 | 65471 | 65471 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 4 box Pineapple Juice in can and 12 others | [19 empty] | 17FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-06 | 2022-07-07 | 2022-08-03 | 2022-08-12 | 2022-08-12 | GoP | 25980 | 25980 | 0 | 25800 | 25800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 ea 5 Seater Gang Chair (for PWD) | [19 empty] | 17FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-06 | 2022-07-07 | 2022-08-03 | 2022-08-12 | 2022-08-12 | GoP | 14000 | 14000 | 0 | 13800 | 13800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 2 ea Fire Extinguisher | [19 empty] | 17FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-06 | 2022-07-07 | 2022-08-03 | 2022-08-12 | 2022-08-12 | GoP | 29600 | 29600 | 0 | 29400 | 29400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 10 pack Spaghetti Pasta and 14 others | [19 empty] | 17FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-10-21 | 2022-10-24 | 2022-11-14 | 2022-11-16 | GoP | 30450 | 30450 | 0 | 30380 | 30380 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[38 empty] | 484185.82 | 484185.82
| Repair and Maintenance of ICT Equipment | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-13 | 2022-07-27 | 2022-07-27 | 2022-07-29 | 2022-07-29 | GoP | 10000 | 10000 | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-13 | 2022-07-27 | 2022-07-27 | 2022-07-29 | 2022-07-29 | GoP
| Office Supplies Expenses | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-13 | 2022-07-27 | 2022-07-27 | 2022-07-29 | 2022-07-29 | GoP | 33192 | 33192 | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-13 | 2022-07-27 | 2022-07-27 | 2022-07-29 | 2022-07-29 | GoP
| Medical and Dental Laboratory Supplies Expenses | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-13 | 2022-07-27 | 2022-07-27 | 2022-08-01 | 2022-08-01 | GoP | 7200 | 7200 | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-13 | 2022-07-27 | 2022-07-27 | 2022-08-01 | 2022-08-01 | GoP | 10000 | 10000 | N/A | 9950 | 9950
| Auditing Services | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-13 | 2022-08-01 | 2022-08-01 | 2022-08-03 | 2022-08-03 | GoP | 100000 | 100000 | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-13 | 2022-08-01 | 2022-08-01 | 2022-08-03 | 2022-08-03 | GoP | 33192 | 33192 | N/A | 33020 | 33020
| Other Supplies and Material Exepenses | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-13 | 2022-07-27 | 2022-07-27 | 2022-08-01 | 2022-08-01 | GoP | 17500 | 17500 | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-13 | 2022-07-27 | 2022-07-27 | 2022-08-01 | 2022-08-01 | GoP | 7200 | 7200 | N/A | 7140 | 7140
| Repair and Maintenance of Motor Vehicle | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-27 | 2022-08-01 | 2022-08-01 | 2022-08-03 | 2022-08-03 | GoP | 17004 | 17004 | 14FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-27 | 2022-08-01 | 2022-08-01 | 2022-08-03 | 2022-08-03 | GoP | 100000 | 100000 | N/A | 99400 | 99400
| Auditing Services | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | 2022-10-10 | 2022-10-10 | 2022-10-14 | 2022-10-14 | GoP | 100000 | 100000 | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | 2022-10-10 | 2022-10-10 | 2022-10-14 | 2022-10-14 | GoP | 17500 | 17500 | N/A | 17443 | 17443
| Repair and Maintenance of Office Equipment | 14FAU | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | 2022-10-10 | 2022-10-10 | 2022-10-14 | 2022-10-14 | GoP | 7100 | 7100 | 14FAU | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | 2022-10-10 | 2022-10-10 | 2022-10-14 | 2022-10-14 | GoP | 17004 | 17004 | N/A | 16904 | 16904
| Repair and Maintenance of Motor Vehicle | 14FAU | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | 2022-10-10 | 2022-10-10 | 2022-10-14 | 2022-10-14 | GoP | 15100 | 15100 | 14FAU | NO | Negotiated 53.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | 2022-10-10 | 2022-10-10 | 2022-10-14 | 2022-10-14 | GoP | 100000 | 100000 | N/A | 99994 | 99994
| Other Supplies and Material Exepenses | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | 2022-10-10 | 2022-10-10 | 2022-10-14 | 2022-10-14 | GoP | 17500 | 17500 | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | 2022-10-10 | 2022-10-10 | 2022-10-14 | 2022-10-14 | GoP | 7100 | 7100 | N/A | 7094 | 7094
| Office Supplies Expenses | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | 2022-10-10 | 2022-10-10 | 2022-10-14 | 2022-10-14 | GoP | 37450 | 37450 | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | 2022-10-10 | 2022-10-10 | 2022-10-14 | 2022-10-14 | GoP | 15100 | 15100 | N/A | 15097 | 15097
| Representation Expenses | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 15 N ov 22 | 2022-12-05 | 2022-12-05 | 2022-12-12 | 2022-12-12 | GoP | 15855 | 15855 | 14FAU |  | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 15 N ov 22 | 2022-12-05 | 2022-12-05 | 2022-12-12 | 2022-12-12 | GoP | 17500 | 17500 | N/A | 17422 | 17422
| Representation Expenses | 14FAU | NO | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-23 | 2022-12-05 | 2022-12-05 | 2022-12-09 | 2022-12-09 | GoP | 25000 | 25000 | 14FAU | 24928 | Shopping 52.1(b) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-23 | 2022-12-05 | 2022-12-05 | 2022-12-09 | 2022-12-09 | GoP | 37450 | 37450 | N/A | 37360 | 37360
[38 empty] | 362046 | 362046 | N/A | 15783 | 15783
| S/D of 30 rms A4 Bond paper (subs 20) and 27 others | [19 empty] | 6FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-17 | 2022-02-18 | 2022-02-24 | 2022-03-03 | 2022-03-03 | GoP | 18796 | 18796 | 0 | 18790 | 18790 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 ea MS Office 365 (5 devices for 1 year) & Anti-virus (5 devices for 2 years) | [19 empty] | 6FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-04 | 2022-03-05 | 2022-03-12 | 2022-02-18 | 2022-02-18 | GoP | 19450 | 19450 | 0 | 19440 | 19440 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 5 rms bond paper long (subs 20) & 17 others | [19 empty] | 6FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-29 | 2022-04-30 | 2022-05-07 | 2022-05-13 | 2022-05-13 | GoP | 15811 | 15811 | 0 | 15809 | 15809 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 ea OS Professional Windows 10 & OS Home Windows 10 | [19 empty] | 6FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-26 | 2022-05-27 | 2022-06-03 | 2022-06-10 | 2022-06-10 | GoP | 20560 | 20560 | 0 | 20550 | 20550 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 3 rms bond paper short(subs 20) & 17 others | [19 empty] | 6FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-10 | 2022-06-11 | 2022-06-18 | 2022-06-24 | 2022-06-24 | GoP | 23899 | 23899 | 0 | 23881 | 23881 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 1 ea OS Professional Windows 10 & OS Home Windows 10 | [19 empty] | 6FAU | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-13 | 2022-06-14 | 2022-06-20 | 2022-06-27 | 2022-06-27 | GoP | 20010 | 20010 | 0 | 20000 | 20000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[38 empty] | 118526 | 118526
| GRAND TOTALS >>>>> | [36 empty] | 3858787.78 | 3858787.78
Total Alloted Budget of Procurement Activities | [37 empty] | 11813415.34
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 3975090.29
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 7838325.05
0N-GOING PROCUREMENT ACTIVITIES
| SD of 100 box face mask and 3 others | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-18 | 2022-12-28 | N/A | N/A | GoP | 91000 | 91000 | 0 | 90000 | 90000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 2 ea Gigabit switch 24 port and 1 other | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-18 | 2022-12-13 | N/A | N/A | GoP | 53777.43 | 53777.43 | 0 | 53477.43 | 53477.43 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 10 Windows 10 Operationg System and 1 other | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-18 | 2022-12-07 | N/A | N/A | GoP | 87500 | 87500 | 0 | 87100 | 87100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 1 ea Dining Table and 1 other | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-19 | N/A | N/A | GoP | 64500 | 64500 | 0 | 63400 | 63400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 4 ea Scanner and 2 others | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-14 | N/A | N/A | GoP | 391500 | 391500 | 0 | 390700 | 390700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CATERING SERVICES | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-14 | N/A | N/A | GoP | 73260 | 73260 | 0 | 73200 | 73200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 25 pack Palabok Pasta and 38 others | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-28 | N/A | N/A | GoP | 368282.99 | 368282.99 | 0 | 366482.1 | 366482.1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 2 ea Water Dispenser and 2 others | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-22 | N/A | N/A | GoP | 122495 | 122495 | 0 | 120995 | 120995 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 5 Drums Kyocera Taskalfa 4200 i | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-22 | N/A | N/A | GoP | 408069.9 | 408069.9 | 0 | 407368.5 | 407368.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 900 reams A4 Bond Paper and 34 others | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-28 | N/A | N/A | GoP | 700493.7 | 700493.7 | 0 | 698693.7 | 698693.7 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SD of 8 ea Doors and 1 other | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-24 | 2022-11-24 | 2022-12-28 | N/A | N/A | GoP | 50840 | 50840 | 0 | 50400 | 50400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| S/D of 100 each Notebook & 29 others | [19 empty] | ASPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2022-12-13 | N/A | N/A | N/A | GoP | 207568.94 | 207568.94 | 0 | 205652.94 | 205652.94 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 2619287.96
| Prepared by: | [32 empty] | Certified Correct By | [6 empty] | Noted By
| CLAIRE R AURE-REYES | [32 empty] | JOHN KENNETH D BABICA | [6 empty] | MANOLO V SANTIAGO
| Major (QMS) PA | [32 empty] | Major (INF) PA | [6 empty] | Colonel CE (GSC) PA
| Operations Officer | [32 empty] | Executive Officer | [6 empty] | Commanding Officer

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement