## Sheet1
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | FCPA Procurement Monitoring Report (2nd Semester) as of December 31, 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
5-02-13-060-01 | SD of 2 pcs Oil Filter & 33 others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-07-12 | 2022-08-12 | 2022-08-19 | 2022-08-19 | GoP | 134480 | 134480 | 0 | 128280 | 128280 | 0 | [7 empty] | N/A
5-02-13-060-01 | SD of 98 pcs Engine Oil (Diesel) & 82 others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-29 | 2022-07-29 | 2022-09-07 | 2022-09-14 | 2022-09-14 | GoP | 566369 | 566369 | 0 | 553169 | 553169 | 0 | [7 empty] | N/A
5-02-13-060-01 | SD of 91 pcs Engine Oil 1ltr & 69 others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-29 | 2022-07-29 | 2022-09-07 | 2022-09-14 | 2022-09-14 | GoP | 553439 | 553439 | 0 | 549339 | 549339 | 0 | [7 empty] | N/A
5-02-13-040-01 | SD of 60 sq.mtrs Pre-Painted Corrugated Roof #24 & 80 others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-09-12 | 2022-09-19 | 2022-09-19 | GoP | 685695 | 685695 | 0 | 677295 | 677295 | 0 | [7 empty] | N/A
5-02-13-040-01 | SD of 35 Hardiflex 1/4'' X 4' X 8' & 60 others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-24 | 2022-06-24 | 2022-08-10 | 2022-08-18 | 2022-08-18 | GoP | 243860 | 243860 | 0 | 236819 | 236819 | 0 | [7 empty] | N/A
5-02-03-030-00 | SD of 11x14 7/8 (4ply) CARBONLESS & 5 others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-24 | 2022-08-24 | 2022-10-14 | 2022-10-21 | 2022-10-21 | GoP | 998020 | 998020 | 0 | 998020 | 998020 | 0 | [7 empty] | N/A
5-02-13-050-03 | Desktop Core i3 10100 3.6ghz, Prime h510m-k 16gb ram and 1 other | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-31 | 2022-08-31 | 2022-11-04 | 2022-11-11 | 2022-11-11 | GoP | 198000 | 198000 | 0 | 194000 | 194000 | 0 | [7 empty] | N/A
5-02-03-030-00 | Continuos Form and 2 others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-31 | 2022-08-31 | 2022-10-14 | 2022-10-21 | 2022-10-21 | GoP | 555980 | 555980 | 0 | 547500 | 547500 | 0 | [7 empty] | N/A
5-02-03-030-00 | SD of Continuous form 11 11x14 7/8 (4PLY) Carboneless and 2 others | [19 empty] | FCPA | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-13 | 2022-09-13 | 2022-10-12 | 2022-10-19 | 2022-10-19 | GoP | 551996 | 551996 | 0 | 548883 | 548883 | 0 | [7 empty] | N/A
5-02-13-040-01 | Procurement of SIX HUNDRED THIRTY-EIGHT (638) CHB4" and 39 Other Line Items | [19 empty] | 1FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-05 | 2022-07-05 | 2022-08-11 | 2022-08-15 | 2022-08-15 | GoP | 329425 | 329425 | 0 | 329062 | 329062 | 0 | [7 empty] | N/A
5-02-13-040-01 | Procurement of SIX HUNDRED THIRTY-EIGHT (638) CHB4" and 39 Other Line Items | [19 empty] | 1FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-04 | 2022-11-04 | 2022-11-17 | 2022-11-22 | 2022-11-22 | GoP | 376389 | 376389 | 0 | 376389 | 376389 | 0 | [7 empty] | N/A
5-02-13-060-01 | Vehicle Parts & Accessories | [19 empty] | 2FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 26 Jul 22 | 04 Aug 22 | 04 Aug 22 | 09 Aug 22 | 09 Aug 22 | GoP | 37500 | 37200 | 0 | 37500 | 37200 | 0 | [7 empty] | N/A
5-02-13-040-01 | R&M-Buildings | [19 empty] | 2FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-20 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-08 | GoP | 309773 | 309200 | 0 | 309773 | 309200 | 0 | [7 empty] | N/A
5-02-99-030-00 | Representation Exp/Catering | [19 empty] | 2FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-24 | 2022-12-09 | 2022-12-12 | 2022-12-13 | 2022-12-13 | GoP | 50000 | 50000 | 0 | 50000 | 50000 | 0 | [7 empty] | N/A
5-02-13-050-03 | ICT Equipment | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-04-06 | 2022-09-22 | 2022-09-22 | 2022-09-30 | 2022-09-30 | GoP | 30000 | 30000 | 0 | 29720 | 29720 | 0 | [7 empty] | N/A
5-02-13-040-01 | R&M Building & Other Structures | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-30 | 2022-08-19 | 2022-08-19 | 2022-08-30 | 2022-08-30 | GoP | 100000 | 100000 | 0 | 99125 | 99125 | 0 | [7 empty] | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-01 | 2022-09-08 | 2022-09-08 | 2022-09-16 | 2022-09-16 | GoP | 20000 | 20000 | 0 | 19675 | 19675 | 0 | [7 empty] | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-01 | 2022-09-08 | 2022-09-08 | 2022-09-16 | 2022-09-16 | GoP | 30000 | 30000 | 0 | 29360 | 29360 | 0 | [7 empty] | N/A
5-02-03-010-00 | Office Supplies | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-15 | 2022-10-18 | 2022-10-18 | 2022-10-25 | 2022-10-25 | GoP | 78050 | 78050 | 0 | 77000 | 77000 | 0 | [7 empty] | N/A
5-02-03-990-00 | Other Supplies and Materials Expenses | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-15 | 2022-10-18 | 2022-10-18 | 2022-10-25 | 2022-10-25 | GoP | 20000 | 20000 | 0 | 19750 | 19750 | 0 | [7 empty] | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-15 | 2022-10-18 | 2022-10-18 | 2022-10-25 | 2022-10-25 | GoP | 30000 | 30000 | 0 | 29625 | 29625 | 0 | [7 empty] | N/A
5-02-13-060-01 | R&M Motor Veh | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-15 | 2022-11-02 | 2022-11-02 | 2022-11-10 | 2022-11-10 | GoP | 17500 | 17500 | 0 | 17200 | 17200 | 0 | [7 empty] | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-15 | 2022-09-08 | 2022-09-08 | 2022-09-16 | 2022-09-16 | GoP | 33000 | 33000 | 0 | 32610 | 32610 | 0 | [7 empty] | N/A
5-02-13-060-01 | R&M Motor Veh | [19 empty] | 7FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-19 | 2022-09-08 | 2022-09-08 | 2022-09-16 | 2022-09-16 | GoP | 17500 | 17500 | 0 | 17200 | 17200 | 0 | [7 empty] | N/A
5-02-99-070-01 | ICT Subscription | [19 empty] | 8FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-28 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-12 | GoP | 5000 | 5000 | 0 | 5000 | 5000 | 0 | [7 empty] | N/A
5-02-05-030-00 | Internet Expense | [19 empty] | 8FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-28 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-12 | GoP | 6000 | 6000 | 0 | 6000 | 6000 | 0 | [7 empty] | N/A
5-02-03-130-00 | 6 units ABC Dry Chemicals, 10lbs | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-02 | 2022-06-02 | 2022-07-05 | 2022-07-07 | 2022-07-07 | GoP | 6000 | 6000 | 0 | 5958 | 5958 | 0 | [7 empty] | N/A
5-02-02-010-00 | 5 case Mineral Water (350ml) & 8 other LI | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-02 | 2022-06-02 | 2022-07-05 | 2022-07-07 | 2022-07-07 | GoP | 30000 | 30000 | 0 | 29930 | 29930 | 0 | [7 empty] | N/A
5-02-13-040-01 | 60 pcs Ordinary Plywood 1/4x4x8 & 12 other LI | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-02 | 2022-06-02 | 2022-07-06 | 2022-07-07 | 2022-07-07 | GoP | 70050 | 70050 | 0 | 69910 | 69910 | 0 | [7 empty] | N/A
5-02-03-010-00 | 3 box Carbon Film & 24 other LI | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-02 | 2022-06-02 | 2022-07-06 | 2022-07-07 | 2022-07-07 | GoP | 54750 | 54750 | 0 | 54645 | 54645 | 0 | [7 empty] | N/A
5-02-03-210-03 | 1 unit Digital Camera (CMOS, Full HD Res) & 2 other LI | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-02 | 2022-06-02 | 2022-07-05 | 2022-07-07 | 2022-07-07 | GoP | 73700 | 73700 | 0 | 73520 | 73520 | 0 | [7 empty] | N/A
5-02-13-050-03 | 3 unit Windows 10 Genuine (OS) | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-02 | 2022-06-02 | 2022-08-04 | 2022-07-05 | 2022-07-05 | GoP | 9423 | 9423 | 0 | 9393 | 9393 | 0 | [7 empty] | N/A
5-02-03-010-00 | 10 bot Ink, Epson Black (003, 65ml) & 18 other LI | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-11 | 2022-06-12 | 2022-08-26 | 2022-08-31 | 2022-08-31 | GoP | 55000 | 55000 | 0 | 54850 | 54850 | 0 | [7 empty] | N/A
5-02-03-220-01 | 16 pcs Office Chair | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-05 | 2022-09-06 | 2022-10-05 | 2022-10-07 | 2022-10-07 | GoP | 50048 | 50048 | 0 | 49952 | 49952 | 0 | [7 empty] | N/A
5-02-13-040-01 | 35 cans Latex Paint (4L) & 11 other LI | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-05 | 2022-09-06 | 2022-10-05 | 2022-10-07 | 2022-10-07 | GoP | 54526 | 54526 | 0 | 54404 | 54404 | 0 | [7 empty] | N/A
5-02-03-010-00 | 3 box Carbon Film & 24 other LI | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-05 | 2022-09-06 | 2022-10-07 | 2022-10-12 | 2022-10-12 | GoP | 54750 | 54750 | 0 | 54640 | 54640 | 0 | [7 empty] | N/A
5-02-02-010-00 | 5 case Mineral Water (350ml) & 8 other LI | [19 empty] | 9FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-05 | 2022-09-06 | 2022-10-05 | 2022-10-07 | 2022-10-07 | GoP | 35000 | 35000 | 0 | 34916 | 34916 | 0 | [7 empty] | N/A
5-02-13-060-01 | Repair and Maintenance of Vehicle | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-05-24 | 2022-05-25 | 2022-07-05 | 2022-07-07 | 2022-07-07 | GoP | 45000 | 45000 | 0 | 44730 | 44730 | 0 | [7 empty] | N/A
5-02-13-050-10 | Repair and Maintenance Military Pol & Security Equipment | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-15 | 2022-06-16 | 2022-09-26 | 2022-09-28 | 2022-09-28 | GoP | 9500 | 9500 | 0 | 9300 | 9300 | 0 | [7 empty] | N/A
5-02-99-070-01 | Repair and Maintenance of ICT | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-15 | 2022-06-16 | 2022-08-24 | 2022-08-26 | 2022-08-26 | GoP | 11000 | 11000 | 0 | 10800 | 10800 | 0 | [7 empty] | N/A
5-02-13-050-02 | Repair and Maintenance of Office Equipment | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-15 | 2022-06-16 | 2022-08-22 | 2022-08-24 | 2022-08-24 | GoP | 18350 | 18350 | 0 | 18140 | 18140 | 0 | [7 empty] | N/A
5-02-13-040-01 | Repair and Maintenance of Other Structure | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-15 | 2022-06-16 | 2022-09-23 | 2022-09-26 | 2022-09-26 | GoP | 14000 | 14000 | 0 | 13725 | 13725 | 0 | [7 empty] | N/A
5-02-13-060-01 | Repair and Maintenance of Vehicle | [19 empty] | 10FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-14 | 2022-11-15 | 2022-12-14 | 2022-12-16 | 2022-12-16 | GoP | 25000 | 25000 | 0 | 24900 | 24900 | 0 | [7 empty] | N/A
5-02-13-040-01 | R&M-Buildings | [19 empty] | 12FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-02 | 2022-08-02 | 2022-08-24 | 2022-09-02 | 2022-09-02 | GoP | 100000 | 100000 | 0 | 99395 | 99395 | 0 | [7 empty] | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-13 | 2022-07-14 | 2022-07-27 | 2022-08-01 | 2022-08-01 | GoP | 10980 | 10980 | 0 | 10927 | 10927 | 0 | [7 empty] | N/A
5-02-99-030-00 | Representation Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-10 | 2022-08-10 | 2022-08-24 | 2022-08-31 | 2022-08-31 | GoP | 10260 | 10260 | 0 | 10190 | 10190 | 0 | [7 empty] | N/A
5-02-03-080-00 | Medical and Dental Laboratory Supplies Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-10 | 2022-08-10 | 2022-08-24 | 2022-08-31 | 2022-08-31 | GoP | 49490 | 49490 | 0 | 49238 | 49238 | 0 | [7 empty] | N/A
5-02-13-040-01 | Repair and Maintenance of Building | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-17 | 2022-08-17 | 2022-08-31 | 2022-08-31 | 2022-08-31 | GoP | 23999.5 | 23999.5 | 0 | 23919 | 23919 | 0 | [7 empty] | N/A
5-02-13-060-01 | Repair and Maintenance of Motor Vehicle | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-31 | 2022-08-31 | 2022-09-13 | 2022-09-19 | 2022-09-19 | GoP | 21990 | 21990 | 0 | 21914 | 21914 | 0 | [7 empty] | N/A
5-02-13-050-02 | Repair and Maintenance of Office Equipment | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-27 | 2022-07-27 | 2022-08-09 | 2022-08-12 | 2022-08-12 | GoP | 8700 | 8700 | 0 | 8620 | 8620 | 0 | [7 empty] | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-10 | 2022-08-10 | 2022-08-24 | 2022-08-31 | 2022-08-31 | GoP | 20194 | 20194 | 0 | 20066 | 20066 | 0 | [7 empty] | N/A
5-02-03-010-00 | Office Supplies Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-31 | 2022-08-31 | 2022-09-19 | 2022-09-26 | 2022-09-26 | GoP | 17346.97 | 17346.97 | 0 | 17276.97 | 17276.97 | 0 | [7 empty] | N/A
5-02-03-990-00 | Other Supplies and Materials Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-17 | 2022-09-17 | 2022-09-27 | 2022-10-14 | 2022-10-14 | GoP | 10195 | 10195 | 0 | 10145 | 10145 | 0 | [7 empty] | N/A
5-02-03-010-00 | Representation Expenses | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-09-17 | 2022-09-17 | 2022-09-27 | 2022-10-14 | 2022-10-14 | GoP | 11386 | 11386 | 0 | 11306 | 11306 | 0 | [7 empty] | N/A
5-02-13-050-03 | Repair and Maintenance of ICT Equipment | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-09 | 2022-11-09 | 2022-11-22 | 2022-11-28 | 2022-11-28 | GoP | 38955 | 38955 | 0 | 38865 | 38865 | 0 | [7 empty] | N/A
5-02-13-040-01 | Repair and Maintenance of Building | [19 empty] | 14FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-09 | 2022-11-09 | 2022-11-17 | 2022-11-22 | 2022-11-22 | GoP | 21140 | 21140 | 0 | 21040 | 21040 | 0 | [7 empty] | N/A
5-02-13-050-03 | SD of 2 set Wifi Mesh Router & 4 others | [19 empty] | 15FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-31 | 2022-08-31 | 2022-09-23 | 2022-09-30 | 2022-09-30 | GoP | 171000 | 171000 | 0 | 170000 | 170000 | 0 | [7 empty] | N/A
5-02-13-050-03 | S/D of 3 set Desktop Core i5-9500 @ 3.00Ghz, 8GB DDR4, 256 SSD & 1 other | [19 empty] | 15FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-04 | 2022-11-04 | 2022-11-25 | 2022-12-02 | 2022-12-02 | GoP | 191950 | 191950 | 0 | 187100 | 187100 | 0 | [7 empty] | N/A
5-02-13-040-01 | SD of 75 pcs of Hardieflex 1/2 x 4 x 8 and 94 others | [19 empty] | 15FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-31 | 2022-08-31 | 2022-10-06 | 2022-10-13 | 2022-10-13 | GoP | 532000 | 532000 | 0 | 531341 | 531341 | 0 | [7 empty] | N/A
5-02-13-040-01 | R&M-Buildings | [19 empty] | 16FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-01 | 2022-07-02 | 2022-07-25 | 2022-07-27 | 2022-07-27 | GoP | 60950 | 60950 | 0 | 60817 | 60817 | 0 | [7 empty] | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | 17FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-01 | 2022-06-01 | 2022-07-06 | 2022-07-20 | 2022-07-20 | GoP | 20000 | 20000 | 0 | 19775 | 19775 | 0 | [7 empty] | N/A
5-02-02-010-00 | Training Expenses | [19 empty] | 17FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-06-01 | 2022-06-01 | 2022-07-26 | 2022-08-09 | 2022-08-09 | GoP | 60000 | 60000 | 0 | 59825 | 59825 | 0 | [7 empty] | N/A
5-02-13-040-01 | R/M Bldg | [19 empty] | 17FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-19 | 2022-11-19 | 2022-12-07 | 2022-12-21 | 2022-12-21 | GoP | 15000 | 15000 | 0 | 14808 | 14808 | 0 | [7 empty] | N/A
5-02-13-060-01 | R/M Motor Vehicles | [19 empty] | 17FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-19 | 2022-11-19 | 2022-12-07 | 2022-12-21 | 2022-12-21 | GoP | 43000 | 43000 | 0 | 42800 | 42800 | 0 | [7 empty] | N/A
5-02-13-050-03 | R/M ICT Eqpmt | [19 empty] | 17FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-11-19 | 2022-11-19 | 2022-12-07 | 2022-12-21 | 2022-12-21 | GoP | 20000 | 20000 | 0 | 19976 | 19976 | 0 | [7 empty] | N/A
5-02-03-010-00 | Office Supplies | [19 empty] | 17FSFO | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-12-09 | 2022-12-09 | 2022-12-20 | 2002-01-03 | 2023-01-03 | GoP | 20000 | 20000 | 0 | 19725 | 19725 | 0 | [7 empty] | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 8072609.47
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 8001075.97
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 71533.5
0N-GOING PROCUREMENT ACTIVITIES
Total Alloted Budget of On-going Procurement Activities | [37 empty] | #REF!
| Prepared by: | [32 empty] | Certified Correct By | [6 empty] | Noted By
| Jojiemae G Collado | [32 empty] | JESUS B BINARAO | [6 empty] | SEIGFRED C TUBALADO
| TSg (FS) PA | [32 empty] | Major (FS) PA | [6 empty] | Colonel (MNSA) INF PA
| Logistics, NCO | [32 empty] | Logistics, Officer | [6 empty] | Director, FCPA