## v2
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | 113th Contracting Office-TRADOC, PA Procurement Monitoring Report CY 22 01 (Jul - 31 Dec 2022)
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| Procurement of FIVE (5) Grass Cutter 4 Stroke, Gasoline | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-19 |  |  | 2022-08-16 |  |  |  | 2022-08-16 | 2022-08-16 | 2022-09-28 | 2022-10-12 |  | GoP | 47250 | 47250 |  | 47000 | 47000 |  | Santa Clara Trading
| Procurement of TEN (10) tin Latex paint, white gloss & 11 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-07 |  |  | 2022-07-12 |  |  |  | 2022-07-12 | 2022-07-12 | 2022-09-15 | 2022-09-21 |  | GoP | 36600 | 36600 |  | 36600 | 36600 |  | Everybody's Trading & Gen Mdse
| Procurement of EIGHT (8) set Aluminum Door, 0.70m x 2.10m and 49 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-06 |  |  | 2022-07-12 |  |  |  | 2022-07-12 | 2022-07-12 | 2022-10-12 | 2022-10-26 | 2022-08-02 | GoP | 748594.1 | 748594.1 |  | 748594 | 748594 |  | Everybody's Trading & Gen Mdse
| Procurement of FOUR (4)box facemask disposable & 3 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-15 |  |  | 2022-07-19 |  |  |  | 2022-07-19 | 2022-07-19 | 2022-09-01 | 2022-09-15 | 2022-08-02 | GoP | 17200 | 17200 |  | 16900 | 16900 |  | MARY ROCHE MARKETING
| Mobile Expenses | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-08-09 | 2022-08-09 | 2022-08-11 | 2022-08-11 | MOOE-2022 | 37500 | 37500 |  | 37200 | 37200
| Semi Disaster Resp & Rescue Equipment | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-08-09 | 2022-08-09 | 2022-08-11 | 2022-08-11 | MOOE-2022 | 10000 | 10000 |  | 9800 | 9800
| Medical Supplies | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-08-09 | 2022-08-09 | 2022-08-11 | 2022-08-11 | MOOE-2022 | 30000 | 30000 |  | 29792 | 29792
| Repair and Maintenance of Building | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-12 | 2022-08-11 | 2022-08-11 | 2022-08-15 | 2022-08-15 | MOOE-2022 | 80000 | 80000 |  | 79490 | 79490
| Repair and Maintenance of Vehicle | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-18 | 2022-09-26 | 2022-09-26 | 2022-09-28 | 2022-09-28 | MOOE-2022 | 140000 | 140000 |  | 139500 | 139500
| Repair and Maintenance of Other Structure | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-07-18 | 2022-08-19 | 2022-08-19 | 2022-08-22 | 2022-08-22 | MOOE-2022 | 70000 | 70000 |  | 69660 | 69660
| Semi Expendable of ICT | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-08-03 | 2022-09-16 | 2022-09-16 | 2022-09-19 | 2022-09-19 | MOOE-2022 | 212280 | 212280 |  | 211680 | 211680
| Medical Supplies | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-18 | 2022-11-09 | 2022-11-09 | 2022-11-11 | 2022-11-11 | MOOE-2022 | 20000 | 20000 |  | 19800 | 19800
| Mobile Expenses | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-18 | 2022-11-15 | 2022-11-15 | 2022-11-17 | 2022-11-17 | MOOE-2022 | 37500 | 37500 |  | 37380 | 37380
| ELECTRICITY EXPENSE | [19 empty] | TRADOC | NO | Direct Contracting | [13 empty] | MOOE-2022 | 119929.3 | 119929.3 |  | 119929.3 | 119929.3
| WATER EXPENSE | [19 empty] | TRADOC | NO | Direct Contracting | [13 empty] | MOOE-2022 | 52462.03 | 52462.03 |  | 52462.03 | 52462.03
| ELECTRICITY EXPENSE | [19 empty] | TRADOC | NO | Direct Contracting | [13 empty] | MOOE-2022 | 158996.3 | 158996.3 |  | 158996.3 | 158996.3
| ELECTRICITY EXPENSE | [19 empty] | TRADOC | NO | Direct Contracting | [13 empty] | MOOE-2022 | 179291.02 | 179291.02 |  | 179291.02 | 179291.02
| ELECTRICITY EXPENSE | [19 empty] | TRADOC | NO | Direct Contracting | [13 empty] | MOOE-2022 | 211809.2 | 211809.2 |  | 211809.2 | 211809.2
| ELECTRICITY EXPENSE | [19 empty] | TRADOC | NO | Direct Contracting | [13 empty] | MOOE-2022 | 173823.54 | 173823.54 |  | 173823.54 | 173823.54
Total Alloted Budget of Procurement Activities | [37 empty] | 2383235.49
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 2379707.39
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 3528.1
0N-GOING PROCUREMENT ACTIVITIES
| Procurement of SIX (6) bottles Epson 003continuous ink, cyan 0ml & 11 Other Line Items | [19 empty] | TRADOC | NO | Shopping |  | 2022-07-12 |  |  | 2022-07-12 |  |  |  | 2022-07-12 | 2022-07-12 | 2022-09-05 |  |  | GoP | 20610 | 20610 |  | 20010 | 20010 |  | SANTA CLARA TRADING
| Procurement of ONE HUNDRED EIGHTEEN (118) Ballpen (blue) and 15 Others | [19 empty] | TRADOC | NO | Shopping |  | 2022-09-13 |  |  | 2022-09-13 |  |  |  | 2022-09-13 | 2022-09-13 | 2022-11-15 |  |  | GoP | 22360 | 22360 |  | 22180 | 22180 |  | ALPHA BLUE CONSUMER GOODS TRADING
| Procurement of TWO (2) pack Folder , Ghreen, A4, 50s and 8 Other Line Items | [19 empty] | TRADOC | NO | Shopping |  | 2022-07-19 |  |  | 2022-07-19 |  |  |  | 2022-07-19 | 2022-07-19 | 2022-09-29 |  |  | GoP | 3903.64 | 3903.64 |  | 3900 | 3900 |  | EVERYBODY'S TRADING & GEN. MERCHANDISE
| Procurement of THREE (3) Box Binder Clip , asstd, #2,12s/box and 21 Other Line Items | [19 empty] | TRADOC | NO | Shopping |  | 2022-11-08 |  |  | 2022-11-08 |  |  |  | 2022-11-08 | 2022-11-08 | 2022-12-14 |  |  | GoP | 31300 | 31300 |  | 30994 | 30994 |  | SANTA CLARA TRADING
| Procurement of ONE HUNDRED NINETY (190) Bags Cement and 27 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-12 |  |  | 2022-07-12 |  |  |  | 2022-07-12 | 2022-07-12 | 2022-09-05 |  |  | GoP | 999996 | 999996 |  | 998968 | 998968 |  | THREE-ACES GEN MDSE
| Procurement of THREE (3) External HDD, 1TB & 5 Other line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-12 |  |  | 2022-07-12 |  |  |  | 2022-07-12 | 2022-07-12 | 2022-09-07 |  |  | GoP | 91059 | 91059 |  | 88720 | 88720 |  | ALPHA BLUE CONSUMER GOODS TRADING
| Procurement of THREE (3) set of Printer 3 in 1 continuous ink system | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-12 |  |  | 2022-07-12 |  |  |  | 2022-07-12 | 2022-07-12 | 2022-09-19 |  |  | GoP | 48000 | 48000 |  | 48000 | 48000 |  | Everybody's Trading & Gen Mdse
| Procurement of FIVE HUNDRED (500) copies Signal Operations Manual PAM -0102 and 2 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-12 |  |  | 2022-07-12 |  |  |  | 2022-07-12 | 2022-07-12 | 2022-09-19 |  |  | GoP | 351000 | 351000 |  | 345000 | 345000 |  | LEOFER GRAPHIC PRINTING &ADVERTISING
| Procurement of TWO (2) set CCTVcam (6mm fixed lens, night vision 30 m distance, 4MP OHD,12VIA Power Supply 16x digital zoom, 25GB | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-12 |  |  | 2022-07-12 |  |  |  | 2022-07-12 | 2022-07-12 | 2022-09-29 |  |  | GoP | 20000 | 20000 |  | 20000 | 20000 |  | Everybody's Trading & Gen Mdse
| Procurement of TWO (2) set HEPA and Carbon Filter for aerosol sunction machine (Hiremax) 1 by 2's (20cm x 3 cm) and 7 Other Line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-19 |  |  | 2022-07-19 |  |  |  | 2022-07-19 | 2022-07-19 | 2022-10-12 |  |  | GoP | 100000 | 100000 |  | 99400 | 99400 |  | ST.CLAIRE MEDICINE TRADING
| Procurement of SIX (6) box amoxicillin 500mg 100s & 9 Other Line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-19 |  |  | 2022-07-19 |  |  |  | 2022-07-19 | 2022-07-19 | 2022-10-25 |  |  | GoP | 28000 | 28000 |  | 27500 | 27500 |  | ST.CLAIRE MEDICINE TRADING
| Procurement of ONE (1) lot Enhancement of Comfort Room of Quarantine Facility | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-19 |  |  | 2022-07-19 |  |  |  | 2022-07-19 | 2022-07-19 | 2022-09-29 |  |  | GoP | 140050 | 140050 |  | 140000 | 140000 |  | RS SECRETARIO CONSTRUCTION SSERVICES
| Procurement of FIVE (5) pcs Angle Bar Metal & 10 Other LI | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-19 |  |  | 2022-07-19 |  |  |  | 2022-07-19 | 2022-07-19 |  |  |  | GoP | 30000 | 30000 |  | 30000 | 30000 |  | Everybody's Trading & Gen Mdse
| Procurement of ONE (1) Set Battery,3SMF (Toyota Innova) and 23 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-19 |  |  | 2022-07-19 |  |  |  | 2022-07-19 | 2022-07-19 | 2022-09-16 |  |  | GoP | 55000 | 55000 |  | 55000 | 55000 |  | Everybody's Trading & Gen Mdse
| Procurement of SIX (6) Can acri color (raw slena), 250ml and 40 Other Line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-19 |  |  | 2022-07-19 |  |  |  | 2022-07-19 | 2022-07-19 | 2022-08-23 |  |  | GoP | 749802 | 749802 |  | 749802 | 749802 |  | Everybody's Trading & Gen Mdse
| Procurement of ONE (1) set Stabilizer Link & Bar Bushing for Toyota Hi-Lux (Left & right) | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-12 |  |  | 2022-07-12 |  |  |  | 2022-07-12 | 2022-07-12 | 2022-10-03 |  |  | GoP | 25000 | 25000 |  | 25000 | 25000 |  | Everybody's Trading & Gen Mdse
| Procurement of ONE (1) Unit Keyboard with mouse combo & 13 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-26 |  |  | 2022-07-26 |  |  |  | 2022-07-26 | 2022-07-26 | 2022-10-27 |  |  | GoP | 70000 | 70000 |  | 69200 | 69200 |  | ALPHA BLUE CONSUMER GOODS TRADING
| Procurement of TWO (2) pcs executive chair adjustable high black leather and 2 Other line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-02 |  |  | 2022-08-02 |  |  |  | 2022-08-02 | 2022-08-02 | 2022-10-27 |  |  | GoP | 30000 | 30000 |  | 29800 | 29800 |  | Santa Clara Trading
| Procurement of TWENTY-ONE (21) pc of T6 Tactical Military flash light 9800LM | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-02 |  |  | 2022-08-02 |  |  |  | 2022-08-02 | 2022-08-02 |  |  |  | GoP | 19995 | 19995 |  | 19995 | 19995 |  | Everybody's Trading & Gen Mdse
| Procurement of EIGHT (8) pcs PVC orange 40x3m and 6 other line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-02 |  |  | 2022-08-02 |  |  |  | 2022-08-02 | 2022-08-02 |  |  |  | GoP | 18000 | 18000 |  | 18000 | 18000 |  | Everybody's Trading & Gen Mdse
| Procurement of TWO (2) unit system line Mini Tower server and 19 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-09 |  |  | 2022-08-09 |  |  |  | 2022-08-09 | 2022-08-09 | 2022-10-25 |  |  | GoP | 600000 | 600000 |  | 599980 | 599980 |  | Everybody's Trading & Gen Mdse
| Procurement of ONE (1) E970 SWN LED Monitor 16 inch and 13 Other line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-07-26 |  |  | 2022-07-26 |  |  |  | 2022-07-26 | 2022-07-26 | 2022-10-27 |  |  | GoP | 50000 | 50000 |  | 50000 | 50000 |  | Everybody's Trading & Gen Mdse
| Procurement of FIVE HUNDRED (500) Army Aircraft Maintenance Operation PAM3-0503-0303 | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-16 |  |  | 2022-08-16 |  |  |  | 2022-08-16 | 2022-08-16 | 2022-10-25 |  |  | GoP | 148500 | 148500 |  | 147500 | 147500 |  | LEOFER GRAPHIC PRINTING &ADVERTISING
| Procurement of FOUR (4) pcs switch 28-port Gigabit and 22 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-16 |  |  | 2022-08-16 |  |  |  | 2022-08-16 | 2022-08-16 | 2022-11-14 |  |  | GoP | 596642.9 | 596642.9 |  | 594300 | 594300 |  | ALPHA BLUE CONSUMER GOODS TRADING
| Procurement of TEN (10) pcs chairs Executive w/ handrest leather and 2 other line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-16 |  |  | 2022-08-16 |  |  |  | 2022-08-16 | 2022-08-16 | 2022-11-15 |  |  | GoP | 75600 | 75600 |  | 75600 | 75600 |  | Everybody's Trading & Gen Mdse
| Procurement of FOURTEEN (14) T6 Tactical Military LED Flashlight 980000 LM & 2 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-31 |  |  | 2022-08-31 |  |  |  | 2022-08-31 | 2022-08-31 | 2022-11-15 |  |  | GoP | 19600 | 19600 |  | 19600 | 19600 |  | Everybody's Trading & Gen Mdse
| Procurement of ONE (1) Set Brake Lining (Front ) and 1 Other Line Item | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-31 |  |  | 2022-08-31 |  |  |  | 2022-08-31 | 2022-08-31 | 2022-10-12 |  |  | GoP | 10000 | 10000 |  | 10000 | 10000 |  | Everybody's Trading & Gen Mdse
| Procurement of FIFTY (50) Gel Pen, 5mm Ball, Blue and 7 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-31 |  |  | 2022-08-31 |  |  |  | 2022-08-31 | 2022-08-31 |  |  |  | GoP | 40405 | 40405 |  | 40200 | 40200 |  | Everybody's Trading & Gen Mdse
| Procurement of TWENTY (20) Paint Acri Cilor (raw sienna) 1 liter and 54 other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-31 |  |  | 2022-08-31 |  |  |  | 2022-08-31 | 2022-08-31 | 2022-11-04 |  |  | GoP | 560000 | 560000 |  | 559900 | 559900 |  | GERV'S CONSTRUCTION SUPPLIES TRADING
| Procurement of TEN (10) QDE White 1L and 9 Other LineItems | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-31 |  |  | 2022-08-31 |  |  |  | 2022-08-31 | 2022-08-31 |  |  |  | GoP | 32700 | 32700 |  | 32600 | 32600 |  | GERV'S CONSTRUCTION SUPPLIES TRADING
| Procurement of THREE (3) Air Filter for Toyota Hi lux and 141 Other Line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-31 |  |  | 2022-08-31 |  |  |  | 2022-08-31 | 2022-08-31 | 2022-11-15 |  |  | GoP | 625400 | 625400 |  | 625300 | 625300 |  | 2BB Industrial Supply
| Procurement of FORTY (40) Air Freshener & 86 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-09-06 |  |  | 2022-09-06 |  |  |  | 2022-09-06 | 2022-09-06 | 2022-10-12 |  |  | GoP | 620525 | 620525 |  | 620365 | 620365 |  | Everybody's Trading & Gen Merchandise
| Enhancement of ONE (1) lot Pergola | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-09-13 |  |  | 2022-09-13 |  |  |  | 2022-09-13 | 2022-09-13 | 2022-11-15 |  |  | GoP | 91570 | 91570 |  | 91500 | 91500 |  | R.S Sectretaio Construction Services
| Procurement of FIFTY (50) bags Cement and 20 Other line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-09-20 |  |  | 2022-09-20 |  |  |  | 2022-09-20 | 2022-09-20 | 2022-12-05 |  |  | GoP | 200000 | 200000 |  | 199663 | 199663 |  | THREE-ACES GEN MDSE
| Procurement of TWELVE (12) Unit Office Partition Work Station 90x60x120 & 1 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-09-20 |  |  | 2022-09-20 |  |  |  | 2022-09-20 | 2022-09-20 | 2022-11-15 |  |  | GoP | 139500 | 139500 |  | 139250 | 139250 |  | EVERYBODYS TRADING & GEN MDSE
| Procurement of FOUR (4) Refill of Fire Extinguisher 10 lbs and 1 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-31 |  |  | 2022-08-31 |  |  |  | 2022-08-31 | 2022-08-31 | 2022-12-05 |  |  | GoP | 6000 | 6000 |  | 6000 | 6000 |  | EVERYBODY'S TRADING & GEN MDSE
| Procurement of TWELVE (12) Card Cell Card, Smart, 500 and 1 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-31 |  |  | 2022-08-31 |  |  |  | 2022-08-31 | 2022-08-31 | 2022-12-05 |  |  | GoP | 12000 | 12000 |  | 12000 | 12000 |  | EVERYBODY'S TRADING & GEN MDSE
| Procurement of TEN (10) packs Okra seedlings and 7 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-31 |  |  | 2022-08-31 |  |  |  | 2022-08-31 | 2022-08-31 |  |  |  | GoP | 15000 | 15000 |  | 15000 | 15000 |  | EVERYBODY'S TRADING & GEN MDSE
| Procurement of ONE (1) Box Sign Pen 0.05mm, Blue (12pcs/box) and 11 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-08-31 |  |  | 2022-08-31 |  |  |  | 2022-08-31 | 2022-08-31 | 2022-12-05 |  |  | GoP | 7400 | 7400 |  | 7400 | 7400 |  | EVERYBODY'S TRADING & GEN MDSE
| Procurement of EIGHTEEN (18) pcs Processor, Intel Core 15-11400 11th Gen and 11 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-04 |  |  | 2022-10-04 |  |  |  | 2022-10-04 | 2022-10-04 | 2022-11-14 |  |  | GoP | 945000 | 945000 |  | 944000 | 944000 |  | EVERYBODY'S TRADING & GEN MDSE
| Procurement of EIGHT (8) Processor, Intel Core 15-11400 11th Gen and 16 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-04 |  |  | 2022-10-04 |  |  |  | 2022-10-04 | 2022-10-04 | 2022-11-04 |  |  | GoP | 969000 | 969000 |  | 968400 | 968400 |  | EVERYBODY'S TRADING & GEN MDSE
| Procurement of TWENTY-FIVE (25) Reams Bond Paper, 80gsm, A4 and 3 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-04 |  |  | 2022-10-04 |  |  |  | 2022-10-04 | 2022-10-04 | 2022-12-05 |  |  | GoP | 8900 | 8900 |  | 8775 | 8775 |  | EVERYBODY'S TRADING & GEN MDSE
| Procurement of SEVEN (7) Processor, Intel Core 15-11400 11th Gen and 13 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-04 |  |  | 2022-10-04 |  |  |  | 2022-10-04 | 2022-10-04 | 2022-11-14 |  |  | GoP | 913600 | 913600 |  | 912800 | 912800 |  | EVERYBODY'S TRADING & GEN MDSE
| Procurement of FOUR (4) box face mask lifting Butterfly 3D | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-11 |  |  | 2022-10-11 |  |  |  | 2022-10-11 | 2022-10-11 | 2022-11-15 |  |  | GoP | 17200 | 17200 |  | 17150 | 17150 |  | QUREPLUS CORP.
| Procurement of FORTY TWO (42)pairs tactical boots and 5 other line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-11 |  |  | 2022-10-11 |  |  |  | 2022-10-11 | 2022-10-11 |  |  |  | GoP | 824100 | 824100 |  | 823236 | 823236 |  | THREE-ACES GEN MDSE
| Procurement of FORTY-TWO (42) Barong and pants and 6 Other line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-11 |  |  | 2022-10-11 |  |  |  | 2022-10-11 | 2022-10-11 |  |  |  | GoP | 510300 | 510300 |  | 509796 | 509796 |  | THREE-ACES GEN MDSE
| Procurement of TWO (2) box Rapid Antigen Test Kit (22 Kit per Box) and 1 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-11 |  |  | 2022-10-11 |  |  |  | 2022-10-11 | 2022-10-11 |  |  |  | GoP | 24000 | 24000 |  | 24000 | 24000 |  | AMARDEX DRUGSTORE
| Procurement of ONE HUNDRED TWENTY-NINE (129) pc Pershing Cap | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-18 |  |  | 2022-10-18 |  |  |  | 2022-10-18 | 2022-10-18 | 2022-12-05 |  |  | GoP | 414348 | 414348 |  | 412800 | 412800 |  | Jay-Mark Tailoring
| Procurement of ONE HUNDRED TWENTY-NINE (129) GALA Uniform | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-18 |  |  | 2022-10-18 |  |  |  | 2022-10-18 | 2022-10-18 | 2022-12-05 |  |  | GoP | 739944 | 739944 |  | 739170 | 739170 |  | Jay-Mark Tailoring
| Procurement of FORTY-SEVEN (47) Set Bush Coat and 2 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-18 |  |  | 2022-10-18 |  |  |  | 2022-10-18 | 2022-10-18 |  |  |  | GoP | 587500 | 587500 |  | 587500 | 587500 |  | Dantes executive menswear & bags acc.
| Procurement of ONE HUNDRED TWENTY-NINE (129) Belt Medal w/ OCS Seal and & 5 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-18 |  |  | 2022-10-18 |  |  |  | 2022-10-18 | 2022-10-18 | 2022-12-06 |  |  | GoP | 636346 | 636346 |  | 635830 | 635830 |  | Jay-Mark Tailoring
| Procurement of TWELVE (12) Sanitizer, 60 ml and 3 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-18 |  |  | 2022-10-18 |  |  |  | 2022-10-18 | 2022-10-18 | 2022-12-05 |  |  | GoP | 12500 | 12500 |  | 12500 | 12500 |  | AMARDEX DRUGSTORE
| Procurement of ONE (1) pc Air Filter (Toyota Hi lux) and 17 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-25 |  |  | 2022-10-25 |  |  |  | 2022-10-25 | 2022-10-25 | 2022-12-14 |  |  | GoP | 62000 | 62000 |  | 61800 | 61800 |  | TRQUI AUTO SUPPLY
| Procurement of SIX (6) Set Aluminum Door 0.8x1.6m w/ jamb ang 68 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-25 |  |  | 2022-10-25 |  |  |  | 2022-10-25 | 2022-10-25 |  |  |  | GoP | 816957 | 816957 |  | 815437 | 815437 |  | Everybody's Trading & Gen Mdse
| Procurement of FIFTY (50) Bags Cement and 26 Other line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-25 |  |  | 2022-10-25 |  |  |  | 2022-10-25 | 2022-10-25 |  |  |  | GoP | 500000 | 500000 |  | 499000 | 499000 |  | Everybody's Trading & Gen Mdse
| Procurement of FIVE (500) copies and 2 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-25 |  |  | 2022-10-25 |  |  |  | 2022-10-25 | 2022-10-25 | 2022-12-05 |  |  | GoP | 495560 | 495560 |  | 495000 | 495000 |  | LEOFER GRAPHIC PRINTING &ADVERTISING
| Procurement of TWO HUNDRED FIFTY (250) pcs TRADOC Magazine | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-25 |  |  | 2022-10-25 |  |  |  | 2022-10-25 | 2022-10-25 |  |  |  | GoP | 100000 | 100000 |  | 99500 | 99500 |  | LEOFER GRAPHIC PRINTING &ADVERTISING
| Procuement of ONE (1) Alcohol Dispenser Atomozing Spray with Thermal Scanner with Stand and 2 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-04 |  |  | 2022-11-04 |  |  |  | 2022-11-04 | 2022-11-04 |  |  |  | GoP | 5000 | 5000 |  | 4900 | 4900 |  | ST. CLAIRE MEDICINE TRADING
| Procurement of SIX (6) set Aluminum Door 0.8x1.6m w/ jamb ang 69 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-10-25 |  |  | 2022-10-25 |  |  |  | 2022-10-25 | 2022-10-25 |  |  |  | GoP | 793390 | 793390 |  | 791990 | 791990 |  | GERV'S CONSTRUCTION SUPPLIES TRADING
| Procurement of TWO (2) Office Tables 100cm x 60 cm and 3 other line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-04 |  |  | 2022-11-04 |  |  |  | 2022-11-04 | 2022-11-04 |  |  |  | GoP | 75600 | 75600 |  | 75600 | 75600 |  | Everybody's Trading & Gen Mdse
| Procurement of TWO (2) pack OEM Windows 10 Starter and 6 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-04 |  |  | 2022-11-04 |  |  |  | 2022-11-04 | 2022-11-04 |  |  |  | GoP | 60000 | 60000 |  | 60000 | 60000 |  | Everybody's Trading & Gen Mdse
| Procurement of ONE (1) set Live Network Video Recorder max 200 MBps incoming bandwith to 8MP and 24 Other Line items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-04 |  |  | 2022-11-04 |  |  |  | 2022-11-04 | 2022-11-04 | 2022-11-17 |  |  | GoP | 376389 | 376389 |  | 376389 | 376389 |  | Everybody's Trading & Gen Mdse
| Procurement of SIXTEEN (16) Card Globe & 3 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-08 |  |  | 2022-11-08 |  |  |  | 2022-11-08 | 2022-11-08 |  |  |  | GoP | 16400 | 16400 |  | 16400 | 16400 |  | Everybody's Trading & Gen Mdse
| Procurement of EIGHT (8) liters Diesel Engine Fully Synthetic and 3 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-08 |  |  | 2022-11-08 |  |  |  | 2022-11-08 | 2022-11-08 |  |  |  | GoP | 15000 | 15000 |  | 14940 | 14940 |  | TRQUI AUTO SUPPLY
| Procurement of TWO (2) pc Rotor Disk (Toyota Hi Lux) and 10 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-08 |  |  | 2022-11-08 |  |  |  | 2022-11-08 | 2022-11-08 |  |  |  | GoP | 31600 | 31600 |  | 31490 | 31490 |  | TRQUI AUTO SUPPLY
| Procurement of R & M of Facility (OCS MESSHALL ) Dining Hall | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-15 |  |  | 2022-11-15 |  |  |  | 2022-11-15 | 2022-11-15 |  |  |  | GoP | 999068 | 999068 |  | 998950 | 998950 |  | RS SECRETARIO CONSTRUCTION SSERVICES
| Procurement of ONE (1) Set Freon R22 Refrigerant Hisysglobal & 6 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-15 |  |  | 2022-11-15 |  |  |  | 2022-11-15 | 2022-11-15 |  |  |  | GoP | 25000 | 25000 |  | 24050 | 24050 |  | 2BB Industrial Supply
| Procurement of TWENTY FOUR (24) Air Freshener 330 ml & 1 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-15 |  |  | 2022-11-15 |  |  |  | 2022-11-15 | 2022-11-15 |  |  |  | GoP | 28960 | 28960 |  | 28840 | 28840 |  | Santa Clara Trading
| Procurement of FIVE HUNDRED (500) Graphic Training Aid (Military) and 19 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-22 |  |  | 2022-11-22 |  |  |  | 2022-11-22 | 2022-11-22 |  |  |  | GoP | 499915 | 499915 |  | 499465 | 499465 |  | ALPHA BLUE CONSUMER GOODS TRADING
| Procurement of FORTY (40) Rolls Acetate and 40 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-22 |  |  | 2022-11-22 |  |  |  | 2022-11-22 | 2022-11-22 |  |  |  | GoP | 499453 | 499453 |  | 498193 | 498193 |  | ALPHA BLUE CONSUMER GOODS TRADING
| Procurement of TWO HUNDRED (200) pc Toilet Brush and 25 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-22 |  |  | 2022-11-22 |  |  |  | 2022-11-22 | 2022-11-22 |  |  |  | GoP | 499900 | 499900 |  | 499845 | 499845 |  | EVERYBODY'S TRADING & GEN MDSE
| Procurement of FOUR (4) gal Septic Tank Treatment 4 liters and 12 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-22 |  |  | 2022-11-22 |  |  |  | 2022-11-22 | 2022-11-22 |  |  |  | GoP | 26070 | 26070 |  | 25970 | 25970 |  | EVERYBODY'S TRADING & GEN MDSE
| Procurement of TWO (2) HR ACRI Color Raw Siena and 56 Other Line Items | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement |  | 2022-11-29 |  |  | 2022-11-29 |  |  |  | 2022-11-29 | 2022-11-29 |  |  |  | GoP | 772718 | 772718 |  | 771918 | 771918 |  | RG SANTOS TRADING
| Repair and Maintenance of Vehicle | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-18 | 2022-12-14 | 2022-12-14 | 2022-12-16 | 2022-12-16 | MOOE-2022 | 65000 | 65000 |  | 64800 | 64800
| Repair and Maintenance of Building | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-18 | 2022-12-06 | 2022-12-06 | 2022-12-08 | 2022-12-08 | MOOE-2022 | 130000 | 130000 |  | 129710 | 129710
| Repair and Maintenance of Building | [19 empty] | TRADOC | NO | NP-53.9 - Small Value Procurement | [8 empty] | 2022-10-19 | 2022-12-07 | 2022-12-07 | 2022-12-09 | 2022-12-09 | SPF-2022 | 987568 | 987568 |  | 986756 | 986756
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 21189204.54
|  | Prepared By: | [30 empty] | Noted By:
|  | MARIA VICTORIA C MATILLANO | [30 empty] | PETER ANGELO L RAMOS
|  | MAJ (QMS) PA | [30 empty] | Major General PA
|  | AC of S for Logistics | [30 empty] | Commander

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement